## Summary Staffing Plan May 2012
Stafffing Plan | [6 empty] | OCTOBER 2012 FORECAST to COMPLETE
Through May 31, 2012 | [6 empty] | figures as at May 31, 2012
|  | Values |  |  |  |  | FUNDS REALLOCATED
SCC1 | SCC GROUP DESC | CCE Total | Planned | Actuals | Variance (Plan vs. Actual ) | Availabe funds to complete (CCE less Actual) | Sum of Availabe fund to complete (CCE less Actual) | Planned Cost to Complete | Sum Variance (Avail fund Vs Planned)
8001 | Prelim Engrg | 46220114 | 46220114 | 46220114 | 0 |  | 0 | 0 | 0
8002 | Final Design | 83691705 | 58447440.6333 | 52462997 | 5984443.6333 | 31228708 | 14738330 | 480822.0262 | 14257507.9738
8003 | Project Mgmt | 190892344 | 38836962.3056 | 35279245 | 3557717.3056 | 155613099 | 76864878 | 74918237.4107 | 1946640.5893
8004 | Constr Mgmt | 15549020.675 | 4367331.3333 | 2923031 | 1444300.3333 | 12625989.675 | 106154023 | 102011737.982 | 4142285.018
8005 | Non-Constr Insurance | 6800000 | 6045933.22 | 6045933 | 0.22 | 754067 | 754067 | 0 | 754067
8006 | Legal, Permits, Reviews | 7339321 | 4740315.587 | 776131 | 3652822.0593 | 5403633 | 5756420 | 5952965 | -196545
8007 | Survey, Tests, Investigations | 323758 | 320988 | 260679 | 60309 | 63079 | 74310 | 74310 | 0
8008 | Start-up | 8400328.79 | 29920 | 0 | 29920 | 8400328.79 | 9746877 | 9766683.649 | -19806.649
Grand Total |  | 359216591.465 | 159009005.0793 | 143968130 | 14729512.5515 | 214088904.465 | 214088905 | 193204756.0679 | 20884148.9321

## Detailed Forecast January 2013
CCE ESTIMATE | [6 empty] | ACTUAL COSTS | [6 empty] | Stafffing Plan | [6 empty] | as per Cost Report through May 31, 2012 |  |  |  | OCTOBER 2012 FORECAST to COMPLETE
Through May 31, 2012 | [6 empty] | Through May 31, 2012 | [6 empty] | Through May 31, 2012 | [10 empty] | figures as at May 31, 2012
Sum of CCE Total | [6 empty] | Sum of Actual Total | [12 empty] | Values |  |  |  |  | FUNDS REALLOCATED
SCC1 | SCC GROUP DESC | SCC2 | SCC2 Desc | SCC3 | Group | Total | SCC1 | SCC GROUP DESC | SCC2 | SCC2 Desc | SCC3 | Group | Total | SCC1 | SCC GROUP DESC | SCC2 | SCC2 Desc | SCC3 | Group | CCE Total | Planned | Sum of Actual Total | Sum of Variance (Plan vs. Actual thru 05/31/12) | Sum of Availabe fund to complete (CCE less Actual) | Sum of Availabe fund to complete (CCE less Actual) | Planned Cost to Complete | Sum Variance (Avail fund Vs Planned)
8001 | Prelim Engrg | 8001 | (blank) | 8001 | Prelim Engrg | 46220114 | 8001 | Prelim Engrg | 8001 | (blank) | 8001 | Prelim Engrg | 46220114 | 8001 | Prelim Engrg | 8001 | (blank) | 8001 | Prelim Engrg | 46220114 | 46220114 | 46220114 | 0 |  | 0 | 0 | 0
|  | 8001 Total |  |  |  | 46220114 |  |  | 8001 Total |  |  |  | 46220114 |  |  | 8001 Total |  |  |  | 46220114 | 46220114 | 46220114 | 0 |  | 0 | 0 | 0
8001 Total | [5 empty] | 46220114 | 8001 Total | [5 empty] | 46220114 | 8001 Total | [5 empty] | 46220114 | 46220114 | 46220114 | 0 |  | 0 | 0 | 0
8002 | Final Design | 8002.1 | SFMTA | 8002.11 | SFMTA-PM |  | 8002 | Final Design | 8002.1 | SFMTA | 8002.11 | SFMTA-PM |  | 8002 | Final Design | 8002.1 | SFMTA | 8002.11 | SFMTA-PM | [6 empty] | 0 | 0
|  |  |  | 8002.12 | SFMTA-Engrg | 8081775 |  |  |  |  | 8002.12 | SFMTA-Engrg | 8081775 |  |  |  |  | 8002.12 | SFMTA-Engrg | 8081775 | 4000830 | 8081775 | -4080945 | 0 | 0 | 0 | 0
|  |  |  | 8002.13 | SFMTA-CM | 0 |  |  |  |  | 8002.13 | SFMTA-CM | 0 |  |  |  |  | 8002.13 | SFMTA-CM | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 8002.14 | SFMTA-DPT | 0 |  |  |  |  | 8002.14 | SFMTA-DPT | 0 |  |  |  |  | 8002.14 | SFMTA-DPT | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 8002.1 Total |  |  |  | 8081775 |  |  | 8002.1 Total |  |  |  | 8081775 |  |  | 8002.1 Total |  |  |  | 8081775 | 4000830 | 8081775 | -4080945 | 0 | 0 | 0 | 0
|  | 8002.2 | City/County | 8002.21 | City Attorney | 0 |  |  | 8002.2 | City/County | 8002.21 | City Attorney | 0 |  |  | 8002.2 | City/County | 8002.21 | City Attorney | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 8002.23 | Arts commission | 653000 |  |  |  |  | 8002.23 | Arts commission | 653000 |  |  |  |  | 8002.23 | Arts commission | 653000 | 653000 | 653000 | 0 | 0 | 0 | 0 | 0
|  |  |  | 8002.24 | Risk | 45000 |  |  |  |  | 8002.24 | Risk | 0 |  |  |  |  | 8002.24 | Risk | 45000 | 43500 | 0 | 43500 | 45000 | 0 | 0 | 0 | remaining $45,000 budget transferred to 8003.24
|  |  |  | 8002.25 | City Auditor | 200220 |  |  |  |  | 8002.25 | City Auditor | 121897 |  |  |  |  | 8002.25 | City Auditor | 200220 | 193546 | 121897 | 71649 | 78323 | 50000 | 50000 | 0 | $28,323 transferred to 8003.25 City Auditor
|  |  |  | 8002.26 | Dept. of Tech | 140534 |  |  |  |  | 8002.26 | Dept. of Tech | 124613 |  |  |  |  | 8002.26 | Dept. of Tech | 140534 | 140534 | 124613 | 15921 | 15921 | 0 | 0 | 0 | remaining $15,921 budget transferred to 8003.26
|  |  |  | 8002.27 | Fire Dept. | 34540 |  |  |  |  | 8002.27 | Fire Dept. | 34540 |  |  |  |  | 8002.27 | Fire Dept. | 34540 | 33388.6667 | 34540 | -1151.3333 | 0 |  | 0 | 0
|  |  |  | 8002.28 | SF PUC | 32959 |  |  |  |  | 8002.28 | SF PUC | 21728 |  |  |  |  | 8002.28 | SF PUC | 32959 | 31860.3667 | 21728 | 10132.3667 | 11231 | 0 | 0 | 0 | remaining $11,231 budget transferred to 8007.28
|  |  |  | 8002.29 | Dept of Public Health | 1267 |  |  |  |  | 8002.29 | Dept of Public Health | 1267 |  |  |  |  | 8002.29 | Dept of Public Health | 1267 | 1267 | 1267 | 0 | 0 | 0 | 0 | 0
|  | 8002.2 Total |  |  |  | 1107520 |  |  | 8002.2 Total |  |  |  | 957045 |  |  | 8002.2 Total |  |  |  | 1107520 | 1097096.0333 | 957045 | 140051.0333 | 150475 | 50000 | 50000 | 0
|  | 8002.3 | DPW | 8002.31 | DPW | 3612836 |  |  | 8002.3 | DPW | 8002.31 | DPW | 2844328 |  |  | 8002.3 | DPW | 8002.31 | DPW | 3612836 | 3172091 | 2844328 | 327763 | 768508 | 768508 | 428622.0262 | 339885.9738
|  | 8002.3 Total |  |  |  | 3612836 |  |  | 8002.3 Total |  |  |  | 2844328 |  |  | 8002.3 Total |  |  |  | 3612836 | 3172091 | 2844328 | 327763 | 768508 | 768508 | 428622.0262 | 339885.9738
|  | 8002.4 | SFCTA | 8002.41 | SFCTA | 20000 |  |  | 8002.4 | SFCTA | 8002.41 | SFCTA | 0 |  |  | 8002.4 | SFCTA | 8002.41 | SFCTA | 20000 | 19333.3333 | 0 | 19333.3333 | 20000 | 0 | 0 | 0 | transferred remaining budget $20,000 to 8003.641 - contingency
|  | 8002.4 Total |  |  |  | 20000 |  |  | 8002.4 Total |  |  |  | 0 |  |  | 8002.4 Total |  |  |  | 20000 | 19333.3333 | 0 | 19333.3333 | 20000 | 0 | 0 | 0
|  | 8002.6 | Project ODCs | 8002.61 | Project ODCs | 4147303 |  |  | 8002.6 | Project ODCs | 8002.61 | Project ODCs | 2717688 |  |  | 8002.6 | Project ODCs | 8002.61 | Project ODCs | 4147303 | 4009059.5667 | 2717688 | 1291371.5667 | 1429615 | 0 | 0 | 0 | transferred remaining budget $1,429,615 to 8004.061 - construction ODC's
|  | 8002.6 Total |  |  |  | 4147303 |  |  | 8002.6 Total |  |  |  | 2717688 |  |  | 8002.6 Total |  |  |  | 4147303 | 4009059.5667 | 2717688 | 1291371.5667 | 1429615 | 0 | 0 | 0
|  | 8002.81 | DP1 | 8002.811 | DP1 - Labor | 6227095 |  |  | 8002.81 | DP1 | 8002.811 | DP1 - Labor | 5820643 |  |  | 8002.81 | DP1 | 8002.811 | DP1 - Labor | 6227095 | 4748252 | 5820643 | -1072391 | 406452 | 0 | 0 | 0 | transferred remaining budget $406453 to 8004.811 design support during construction
|  |  |  | 8002.812 | DP1 - ODCs | 264388 |  |  |  |  | 8002.812 | DP1 - ODCs | 195334 |  |  |  |  | 8002.812 | DP1 - ODCs | 264388 | 251169 | 195334 | 55835 | 69054 | 2200 | 2200 | 0 | transferred remaining budget $66,854 to 8004.812 design support during construction
[5 empty] | Alloc cntcy/Options | 8517 | [5 empty] | Alloc cntcy/Options | [6 empty] | Alloc cntcy/Options | 8517 |  |  | 0 | 8517 | 8517 | 0 | 8517
|  | 8002.81 Total |  |  |  | 6500000 |  |  | 8002.81 Total |  |  |  | 6015977 |  |  | 8002.81 Total |  |  |  | 6500000 | 4999421 | 6015977 | -1016556 | 484023 | 10717 | 2200 | 8517
|  | 8002.82 | DP2 | 8002.821 | DP2 - Labor | 34633412 |  |  | 8002.82 | DP2 | 8002.821 | DP2 - Labor | 23583946 |  |  | 8002.82 | DP2 | 8002.821 | DP2 - Labor | 34633412 | 26155887 | 23583946 | 2571941 | 11049466 | 1849041 | 0 | 1849041 | $9,200,425 of remianing budget transferred to 8004.821 - design support during construction
|  |  |  | 8002.822 | DP2 - ODCs | 1802600 |  |  |  |  | 8002.822 | DP2 - ODCs | 728114 |  |  |  |  | 8002.822 | DP2 - ODCs | 1802600 | 1622340 | 728114 | 894226 | 1074486 | 972986 | 0 | 972986 | transferred $101,500 to 8004.822 - design support during construction
|  |  |  | 8002.823 | Alloc cntcy/Options | 3513947 |  |  |  |  | 8002.823 | Alloc cntcy/Options | [5 empty] | 8002.823 | Alloc cntcy/Options | 3513947 | 2986854.95 |  | 2986854.95 | 3513947 | 3513947 | 0 | 3513947
|  | 8002.82 Total |  |  |  | 39949959 |  |  | 8002.82 Total |  |  |  | 24312060 |  |  | 8002.82 Total |  |  |  | 39949959 | 30765081.95 | 24312060 | 6453021.95 | 15637899 | 6335974 | 0 | 6335974
|  | 8002.83 | DP3 | 8002.831 | DP3 - Labor | 16075680 |  |  | 8002.83 | DP3 | 8002.831 | DP3 - Labor | 7511963.01 |  |  | 8002.83 | DP3 | 8002.831 | DP3 - Labor | 16075680 | 6902635 | 7511963.01 | -609328.01 | 8563716.99 | 3964537 | 0 | 3964537 | $4,599,180 of remaining budget transferred to 8004.831 - design support during construction
|  |  |  | 8002.832 | DP3 - ODCs | 424400 |  |  |  |  | 8002.832 | DP3 - ODCs | 22160.99 |  |  |  |  | 8002.832 | DP3 - ODCs | 424400 | 233420 | 22160.99 | 211259.01 | 402239.01 | 189149 | 0 | 189149 | transferred $213,090 of remaining budget to 8004.832 - design support during construction
|  |  |  | 8002.833 | Alloc cntcy/Options | 3419445 |  |  |  |  | 8002.833 | Alloc cntcy/Options | [5 empty] | 8002.833 | Alloc cntcy/Options | 3419445 | 3248472.75 |  | 3248472.75 | 3419445 | 3419445 | 0 | 3419445
|  | 8002.83 Total |  |  |  | 19919525 |  |  | 8002.83 Total |  |  |  | 7534124 |  |  | 8002.83 Total |  |  |  | 19919525 | 10384527.75 | 7534124 | 2850403.75 | 12385401 | 7573131 | 0 | 7573131
|  | 8002.9 | Alloc Cntcy | 8002.9 | Alloc Cntcy | 352787 |  |  | 8002.9 | Alloc Cntcy | 8002.9 | Alloc Cntcy | 0 |  |  | 8002.9 | Alloc Cntcy | 8002.9 | Alloc Cntcy | 352787 | 0 | 0 | 0 | 352787 | 0 | 0 | 0 | transferred remaining budget $ 352,787 to 8006.18 - contingency
|  | 8002.9 Total |  |  |  | 352787 |  |  | 8002.9 Total |  |  |  | 0 |  |  | 8002.9 Total |  |  |  | 352787 | 0 | 0 | 0 | 352787 | 0 | 0 | 0
8002 Total | [5 empty] | 83691705 | 8002 Total | [5 empty] | 52462997 | 8002 Total | [5 empty] | 83691705 | 58447440.6333 | 52462997 | 5984443.6333 | 31228708 | 14738330 | 480822.0262 | 14257507.9738
8003 | Project Mgmt | 8003.1 | SFMTA | 8003.11 | SFMTA-PM | 18034926 | 8003 | Project Mgmt | 8003.1 | SFMTA | 8003.11 | SFMTA-PM | 6874676 | 8003 | Project Mgmt | 8003.1 | SFMTA | 8003.11 | SFMTA-PM | 18034926 | 4510875 | 6874676 | -2363801 | 11160250 | 11160250 | 11686119.4755 | -525869.4755 | Reforecasted plan to to complete
|  |  |  | 8003.12 | SFMTA-Engrg | 0 |  |  |  |  | 8003.12 | SFMTA-Engrg | 0 |  |  |  |  | 8003.12 | SFMTA-Engrg | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Reforecasted plan to to complete
|  |  |  | 8003.13 | SFMTA-CM | 0 |  |  |  |  | 8003.13 | SFMTA-CM | 0 |  |  |  |  | 8003.13 | SFMTA-CM | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Reforecasted plan to to complete
|  |  |  | 8003.14 | SFMTA-DPT | 937346 |  |  |  |  | 8003.14 | SFMTA-DPT | 837858 |  |  |  |  | 8003.14 | SFMTA-DPT | 937346 | 679280 | 837858 | -158578 | 99488 | 99488 | 277200 | -177712
|  | 8003.1 Total |  |  |  | 18972272 |  |  | 8003.1 Total |  |  |  | 7712534 |  |  | 8003.1 Total |  |  |  | 18972272 | 5190155 | 7712534 | -2522379 | 11259738 | 11259738 | 11963319.4755 | -703581.4755
|  | 8003.2 | City/County | 8003.23 | Arts commission | 4186488 |  |  | 8003.2 | City/County | 8003.23 | Arts commission | 303104 |  |  | 8003.2 | City/County | 8003.23 | Arts commission | 4186488 | 1124149.5556 | 303104 | 821045.5556 | 3883384 | 3883384 | 3883384 | 0
|  | 8003.2 Total |  |  |  | 4186488 |  |  |  |  | 8003.24 | Risk | [5 empty] | 8003.24 | Risk | [5 empty] | 45000 | 45000 | 0 | $45,000 budget transferred from 8002.24
|  | 8003.61 | Project ODCs | 8003.611 | Project ODCs | 3502737 |  |  |  |  | 8003.25 | City Auditor | [5 empty] | 8003.25 | City Auditor | [5 empty] | 28323 | 28323 | 0 | $28,323 budget transferred from 8002.25 City Auditor
|  | 8003.61 Total |  |  |  | 3502737 |  |  |  |  | 8003.26 | Dept of Tech | [5 empty] | 8003.26 | Dept of Tech | [5 empty] | 15921 | 15921 | 0
|  | 8003.62 | Aon Risk Ins. Study | 8003.621 | Aon Risk Ins. Study | 25000 |  |  |  |  | 8003.29 | Dept of Public Health | [5 empty] | 8003.29 | Dept of Public Health | [5 empty] | 0 | 0 | 0
|  | 8003.62 Total |  |  |  | 25000 |  |  | 8003.2 Total |  |  |  | 303104 |  |  | 8003.2 Total |  |  |  | 4186488 | 1124149.5556 | 303104 | 821045.5556 | 3883384 | 3972628 | 3972628 | 0
|  | 8003.63 | Consultants | 8003.631 | PMCM-Labor | 107079723 |  |  | 8003.61 | Project ODCs | 8003.611 | Project ODCs | 0 |  |  | 8003.61 | Project ODCs | 8003.611 | Project ODCs | 3502737 | 940549.75 | 0 | 940549.75 | 3502737 | 3502737 | 3502737 | 0
|  |  |  | 8003.632 | PMCM-ODCs | 25712136 |  |  | 8003.61 Total |  |  |  | 0 |  |  | 8003.61 Total |  |  |  | 3502737 | 940549.75 | 0 | 940549.75 | 3502737 | 3502737 | 3502737 | 0
|  |  |  | 8003.633 | Anil Verma | 395270 |  |  | 8003.62 | Aon Risk Ins. Study | 8003.621 | Aon Risk Ins. Study | 25000 |  |  | 8003.62 | Aon Risk Ins. Study | 8003.621 | Aon Risk Ins. Study | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0
|  |  |  | 8003.634 | PCC | 17112873 |  |  | 8003.62 Total |  |  |  | 25000 |  |  | 8003.62 Total |  |  |  | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0
|  | 8003.63 Total |  |  |  | 150300002 |  |  | 8003.63 | Consultants | 8003.631 | PMCM-Labor | 20486324.23 |  |  | 8003.63 | Consultants | 8003.631 | PMCM-Labor | 107079723 | 20284112.3333 | 20486324.23 | -202211.8967 | 86593398.77 | 31848807 | 31124495.9352 | 724311.0648 | transferred $1,346,548 to 8008.13, transferred $53,398,044 to 8004.712
|  | 8003.64 | Contingency | 8003.641 | Contingency | 13905845 |  |  |  |  | 8003.632 | PMCM-ODCs | 2675350.77 |  |  |  |  | 8003.632 | PMCM-ODCs | 25712136 | 6904184.6667 | 2675350.77 | 4228833.8967 | 23036785.23 | 23036785 | 23036785 | 0
|  | 8003.64 Total |  |  |  | 13905845 |  |  |  |  | 8003.633 | Anil Verma | 395204 |  |  |  |  | 8003.633 | Anil Verma | 395270 | 395270 | 395204 | 66 | 66 | 66 | 0 | 66
8003 Total | [5 empty] | 190892344 |  |  |  |  | 8003.634 | PCC | 3681728 |  |  |  |  | 8003.634 | PCC | 17112873 | 3973541 | 3681728 | 291813 | 13431145 | 1318272 | 1318272 | 0 | Reforecasted $1,318,272 for 8003, and. $12,112,873 tranferred to 8004.713
8004 | Constr Mgmt | 8004.1 | SFMTA | 8004.11 | SFMTA-PM | 0 |  |  | 8003.63 Total |  |  |  | 27238607 |  |  | 8003.63 Total |  |  |  | 150300002 | 31557108 | 27238607 | 4318501 | 123061395 | 56203930 | 55479552.9352 | 724377.0648
|  |  |  | 8004.12 | SFMTA-Engrg | 0 |  |  | 8003.64 | Contingency | 8003.641 | Contingency | 0 |  |  | 8003.64 | Contingency | 8003.641 | Contingency | 13905845 | 0 | 0 | 0 | 13905845 | 1925845 | 0 | 1925845 | IN: $20,000 transferred from 8002.41, OUT: Reallocated to CM $12,000,000 to 8004.641
|  |  |  | 8004.13 | SFMTA-CM | 3902472.675 |  |  | 8003.64 Total |  |  |  | 0 |  |  | 8003.64 Total |  |  |  | 13905845 | 0 | 0 | 0 | 13905845 | 1925845 | 0 | 1925845
|  |  |  | 8004.14 | SFMTA-DPT | 0 | 8003 Total | [5 empty] | 35279245 | 8003 Total | [5 empty] | 190892344 | 38836962.3056 | 35279245 | 3557717.3056 | 155613099 | 76864878 | 74918237.4107 | 1946640.5893
|  |  |  | 8004.15 | SFMTA-Engrg IRP | 50000 | 8004 | Constr Mgmt | 8004.1 | SFMTA | 8004.11 | SFMTA-PM | 0 | 8004 | Constr Mgmt | 8004.1 | SFMTA | 8004.11 | SFMTA-PM | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 8004.1 Total |  |  |  | 3952472.675 |  |  |  |  | 8004.12 | SFMTA-Engrg | 0 |  |  |  |  | 8004.12 | SFMTA-Engrg | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 8004.3 | DPW | 8004.31 | BOE | 1727944 |  |  |  |  | 8004.13 | SFMTA-CM | 533057 |  |  |  |  | 8004.13 | SFMTA-CM | 3902472.675 | 1261346 | 533057 | 728289 | 3369415.675 | 3369416 | 14162346.5751 | -10792930.5751 | Reforecasted plan to to complete
|  |  |  | 8004.32 | BOA | 0 |  |  |  |  | 8004.14 | SFMTA-DPT | 0 |  |  |  |  | 8004.14 | SFMTA-DPT | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  |  |  | 8004.33 | BCM | 6752300 |  |  |  |  | 8004.15 | SFMTA-Engrg IRP | 7263 |  |  |  |  | 8004.15 | SFMTA-Engrg IRP | 50000 | 50000 | 7263 | 42737 | 42737 | 42737 | 42737 | 0 | IRP contract
|  |  |  | 8004.34 | BCM (SAR) | 2182046 |  |  | 8004.1 Total |  |  |  | 540320 |  |  | 8004.1 Total |  |  |  | 3952472.675 | 1311346 | 540320 | 771026 | 3412152.675 | 3412153 | 14205083.5751 | -10792930.5751
|  |  |  | 8004.35 | BSM | 417129 |  |  | 8004.3 | DPW | 8004.31 | BOE | 0 |  |  | 8004.3 | DPW | 8004.31 | BOE | 1727944 | 0 | 0 | 0 | 1727944 | 1727944 | 1727944 | 0
|  | 8004.3 Total |  |  |  | 11079419 |  |  |  |  | 8004.32 | BOA | 0 |  |  |  |  | 8004.32 | BOA | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 8004.61 | ODCs | 8004.61 | Project ODCs | 417129 |  |  |  |  | 8004.33 | BCM | 2052256 |  |  |  |  | 8004.33 | BCM | 6752300 | 2219200 | 2052256 | 166944 | 4700044 | 4700044 | 4735200 | -35156
|  | 8004.61 Total |  |  |  | 417129 |  |  |  |  | 8004.34 | BCM (SAR) | 293879 |  |  |  |  | 8004.34 | BCM (SAR) | 2182046 | 585919.7593 | 293879 | 292040.7593 | 1888167 | 1888167 | 600000 | 1288167 | Reforecasted plan to to complete
|  | 8004.71 | Consultants | 8004.711 | IRP APTA | 100000 |  |  |  |  | 8004.35 | BSM | 9268 |  |  |  |  | 8004.35 | BSM | 417129 | 112006.8611 | 9268 | 102738.8611 | 407861 | 407861 | 407861 | 0
|  |  |  | 8004.712 | PMCM | 0 |  |  | 8004.3 Total |  |  |  | 2355403 |  |  | 8004.3 Total |  |  |  | 11079419 | 2917126.6204 | 2355403 | 561723.6204 | 8724016 | 8724016 | 7471005 | 1253011
|  |  |  | 8004.713 | PCC | 0 |  |  | 8004.61 | ODCs | 8004.61 | Project ODCs | 0 |  |  | 8004.61 | ODCs | 8004.61 | Project ODCs | 417129 | 112006.8611 | 0 | 112006.8611 | 417129 | 1846744 | 1200000 | 646744 | $1,429,615 budget transferred from 8002.61 project ODC's
|  | 8004.71 Total |  |  |  | 100000 |  |  | 8004.61 Total |  |  |  | 0 |  |  | 8004.61 Total |  |  |  | 417129 | 112006.8611 | 0 | 112006.8611 | 417129 | 1846744 | 1200000 | 646744
8004 Total | [5 empty] | 15549020.675 |  |  | 8004.64 | Contingency | 8004.641 | Contingency |  |  |  | 8004.64 | Contingency | 8004.641 | Contingency | [5 empty] | 12000000 | 0 | 12000000 | Reallocation from PM contingency IN: $12,000,000 from 8003.641
8005 | Non-Constr Insurance | 8005 | Non-Constr Insurance | 8005 | Non-Constr Insurance | 6800000 |  |  | 8004.64 Total | [6 empty] | 8004.64 Total | [8 empty] | 12000000 | 0 | 12000000
|  | 8005 Total |  |  |  | 6800000 |  |  | 8004.71 | Consultants | 8004.711 | IRP APTA | 27308 |  |  | 8004.71 | Consultants | 8004.711 | IRP APTA | 100000 | 26851.8519 | 27308 | -456.1481 | 72692 | 72692 | 72692 | 0
8005 Total | [5 empty] | 6800000 |  |  |  |  | 8004.712 | PMCM | 0 |  |  |  |  | 8004.712 | PMCM | 0 |  | 0 | 0 | 0 | 53398044 | 52013382.4069 | 1384661.5931 | $53,398,044 budget transferred from 8003.631
8006 | Legal, Permits, Reviews | 8006.1 | City Attorney-PE | 8006.11 | City Attorney-PE | 96981 |  |  |  |  | 8004.713 | PCC | 0 |  |  |  |  | 8004.713 | PCC | 0 |  | 0 | 0 | 0 | 12112873 | 12112873 | 0 | Reallocation from PM 12,112,873 transferred from 8003.634
|  |  | City Attorney - FD | 8006.12 | City Attorney - FD | 705187 |  |  | 8004.71 Total |  |  |  | 27308 |  |  | 8004.71 Total |  |  |  | 100000 | 26851.8519 | 27308 | -456.1481 | 72692 | 65583609 | 64198947.4069 | 1384661.5931
|  |  | City Attorney - Const. | 8006.13 | City Attorney - Const. | 280000 |  |  | 8004.81 | Consultants | 8004.811 | DP1 |  |  |  | 8004.81 | Consultants | 8004.811 | DP1 | 0 |  |  | 0 | 0 | 406452 | 795000 | -388548 | $406452 budget transferred from 8002.811
|  |  | SF Plannning | 8006.14 | SF Plannning | 236666 |  |  |  |  | 8004.812 | DP1 - ODC's | [5 empty] | 8004.812 | DP1 - ODC's | [5 empty] | 66854 | 27507 | 39347 | $66,854 budget transferred from 8002.812
|  |  | BART | 8006.16 | BART | 1797783 |  |  |  |  | 8004.813 | Alloc cntcy/Options | [5 empty] | 8004.813 | Alloc cntcy/Options | [5 empty] | 0 | 0 | 0
|  |  | Dept. of Bldg. Inspection | 8006.17 | Dept. of Bldg. Inspection | 1039943 |  |  | 8004.81 Total | [6 empty] | 8004.81 Total |  |  |  | 0 |  |  | 0 | 0 | 473306 | 822507 | -349201
|  |  | Legal Permit Contingency | 8006.18 | Legal Permit Contingency | 1159557 |  |  | 8004.82 | Consultants | 8004.821 | DP2 |  |  |  | 8004.82 | Consultants | 8004.821 | DP2 | [5 empty] | 9200425 | 9200425 | 0 | $9,200,425 budget transferred from 8002.821
|  |  | Remaining Allowance | 8006.15 | Remaining Allowance | 2023204 |  |  |  |  | 8004.822 | DP2 - ODC's | [5 empty] | 8004.822 | DP2 - ODC's | [5 empty] | 101500 | 101500 | 0 | $101,500 budget transferred from 8002.822
|  | 8006.1 Total |  |  |  | 7339321 |  |  |  |  | 8004.823 | Alloc cntcy/Options | [5 empty] | 8004.823 | Alloc cntcy/Options | [5 empty] | 0 | 0 | 0
8006 Total | [5 empty] | 7339321 |  |  | 8004.82 Total | [6 empty] | 8004.82 Total | [8 empty] | 9301925 | 9301925 | 0
8007 | Survey, Tests, Investigations | 8007.1 | SFPUC - CM 1250 | 8007.11 | SFPUC - CM 1250 | 55936 |  |  | 8004.83 | Consultants | 8004.831 | DP3 |  |  |  | 8004.83 | Consultants | 8004.831 | DP3 | 0 |  |  |  |  | 4599180 | 4599180 | 0 | $4,599,180 budget transferred from 8002.831 final design
|  |  | DPW - Matls Testing | 8007.12 | DPW - Matls Testing | 83100 |  |  |  |  | 8004.832 | DP3 - ODC's | [5 empty] | 8004.832 | DP3 - ODC's | [5 empty] | 213090 | 213090 | 0 | $213,090 budget transferred from 8002.832 final design
|  |  | PUC 1251 | 8007.13 | PUC 1251 | 120784 |  |  |  |  | 8004.833 | Alloc cntcy/Options | [5 empty] | 8004.833 | Alloc cntcy/Options | [5 empty] | 0 | 0 | 0
|  |  | JOC 15&22 Potholing UTL1 | 8007.14 | JOC 15&22 Potholing UTL1 | 63938 |  |  | 8004.83 Total | [6 empty] | 8004.83 Total |  |  |  | 0 |  |  |  |  | 4812270 | 4812270 | 0
|  |  | Remaining Allowance | 8007.15 | Remaining Allowance | 0 | 8004 Total | [5 empty] | 2923031 | 8004 Total | [5 empty] | 15549020.675 | 4367331.3333 | 2923031 | 1444300.3333 | 12625989.675 | 106154023 | 102011737.982 | 4142285.018
|  | 8007.1 Total |  |  |  | 323758 | 8005 | Non-Constr Insurance | 8005 | Non-Constr Insurance | 8005 | Non-Constr Insurance | 6045933 | 8005 | Non-Constr Insurance | 8005 | Non-Constr Insurance | 8005 | Non-Constr Insurance | 6800000 | 6045933.22 | 6045933 | 0.22 | 754067 | 754067 | 0 | 754067
8007 Total | [5 empty] | 323758 |  |  | 8005 Total |  |  |  | 6045933 |  |  | 8005 Total |  |  |  | 6800000 | 6045933.22 | 6045933 | 0.22 | 754067 | 754067 | 0 | 754067
8008 | Start-up | 8008.1 | Contingency | 8008.14 | Contingency | 1358422 | 8005 Total | [5 empty] | 6045933 | 8005 Total | [5 empty] | 6800000 | 6045933.22 | 6045933 | 0.22 | 754067 | 754067 | 0 | 754067
|  |  | DPT | 8008.12 | DPT | 49727.2 | 8006 | Legal, Permits, Reviews | 8006.1 | City Attorney-PE | 8006.11 | City Attorney-PE | 96981 | 8006 | Legal, Permits, Reviews | 8006.1 | City Attorney-PE | 8006.11 | City Attorney-PE | 96981 | 96981 | 96981 | 0 | 0 | 0 | 0 | 0
|  |  | Escalcation on Base | 8008.15 | Escalcation on Base | 0 |  |  |  | City Attorney - FD | 8006.12 | City Attorney - FD | 532723 |  |  |  | City Attorney - FD | 8006.12 | City Attorney - FD | 705187 | 681680.7667 | 532723 | 148957.7667 | 172464 | 172464 | 0 | 172464
|  |  | PMCM | 8008.13 | PMCM | 0 |  |  |  | City Attorney - Const. | 8006.13 | City Attorney - Const. | 0 |  |  |  | City Attorney - Const. | 8006.13 | City Attorney - Const. | 280000 | 75185.1852 | 0 | 75185.1852 | 280000 | 280000 | 3000000 | -2720000
|  |  | Remaining Allowance | 8008.16 | Remaining Allowance | 0 |  |  |  | SF Plannning | 8006.14 | SF Plannning | 0 |  |  |  | SF Plannning | 8006.14 | SF Plannning | 236666 | 228777.1333 | 0 | 228777.1333 | 236666 | 236666 | 236666 | 0
|  |  | SFMTA | 8008.11 | SFMTA | 6992179.59 |  |  |  | BART | 8006.16 | BART | 146427 |  |  |  | BART | 8006.16 | BART | 1797783 | 1797783 | 146427 | 1651356 | 1651356 | 1651356 | 1651356 | 0 | Contract value with BART
|  | 8008.1 Total |  |  |  | 8400328.79 |  |  |  | Dept. of Bldg. Inspection | 8006.17 | Dept. of Bldg. Inspection |  |  |  |  | Dept. of Bldg. Inspection | 8006.17 | Dept. of Bldg. Inspection | 1039943 | 1005278.2333 |  | 1005278.2333 | 1039943 | 1039943 | 1039943 | 0 | Contract value with DBI
8008 Total | [5 empty] | 8400328.79 |  |  |  | Legal Permit Contingency | 8006.18 | Legal Permit Contingency |  |  |  |  | Legal Permit Contingency | 8006.18 | Legal Permit Contingency | 1159557 | 311362.5278 |  |  |  | 0 | 0 | 0 | Reallocated to Reamining Allowance
Grand Total | [5 empty] | 359216591.465 |  |  |  | Remaining Allowance | 8006.15 | Remaining Allowance | 0 |  |  |  | Remaining Allowance | 8006.15 | Remaining Allowance | 2023204 | 543267.7407 | 0 | 543267.7407 | 2023204 | 2350991 | 0 | 2350991 | IN: $352,787 from 8002.9, OUT: reallocated to 8006.29 $25,000
[10 empty] | Dept of Public Health | 8006.29 | Dept of Public Health |  |  |  |  | Dept of Public Health | 8006.29 | Dept of Public Health | [5 empty] | 25000 | 25000 | 0 | $25,000 budget transferred from 8006.15 - remaining allowance
[9 empty] | 8006.1 Total |  |  |  | 776131 |  |  | 8006.1 Total |  |  |  | 7339321 | 4740315.587 | 776131 | 3652822.0593 | 5403633 | 5756420 | 5952965 | -196545
[7 empty] | 8006 Total | [5 empty] | 776131 | 8006 Total | [5 empty] | 7339321 | 4740315.587 | 776131 | 3652822.0593 | 5403633 | 5756420 | 5952965 | -196545
[7 empty] | 8007 | Survey, Tests, Investigations | 8007.1 | SFPUC - CM 1250 | 8007.11 | SFPUC - CM 1250 | 55936 | 8007 | Survey, Tests, Investigations | 8007.1 | SFPUC - CM 1250 | 8007.11 | SFPUC - CM 1250 | 55936 | 55936 | 55936 | 0 | 0 | 0 | 0 | 0
[10 empty] | DPW - Matls Testing | 8007.12 | DPW - Matls Testing | 20021 |  |  |  | DPW - Matls Testing | 8007.12 | DPW - Matls Testing | 83100 | 80330 | 20021 | 60309 | 63079 | 63079 | 63079 | 0
[10 empty] | PUC 1251 | 8007.13 | PUC 1251 | 120784 |  |  |  | PUC 1251 | 8007.13 | PUC 1251 | 120784 | 120784 | 120784 | 0 | 0 | 0 | 0 | 0
[10 empty] | JOC 15&22 Potholing UTL1 | 8007.14 | JOC 15&22 Potholing UTL1 | 63938 |  |  |  | JOC 15&22 Potholing UTL1 | 8007.14 | JOC 15&22 Potholing UTL1 | 63938 | 63938 | 63938 | 0 | 0 | 0 | 0 | 0
[10 empty] | Remaining Allowance | 8007.15 | Remaining Allowance | 0 |  |  |  | Remaining Allowance | 8007.15 | Remaining Allowance | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | PUC 1300 | 8007.28 | PUC Inspections |  |  |  |  | PUC 1300 | 8007.28 | PUC Inspections | [5 empty] | 11231 | 11231 | 0 | $11,231 budget transferred from 8002.28
[9 empty] | 8007.1 Total |  |  |  | 260679 |  |  | 8007.1 Total |  |  |  | 323758 | 320988 | 260679 | 60309 | 63079 | 74310 | 74310 | 0
[7 empty] | 8007 Total | [5 empty] | 260679 | 8007 Total | [5 empty] | 323758 | 320988 | 260679 | 60309 | 63079 | 74310 | 74310 | 0
[7 empty] | 8008 | Start-up | 8008.1 | SFMTA | 8008.11 | SFMTA | 0 | 8008 | Start-up | 8008.1 | SFMTA | 8008.11 | SFMTA | 6992179.59 | 29920 | 0 | 29920 | 6992179.59 | 6992180 | 7011986.79 | -19806.79
[10 empty] | Contingency | 8008.14 | Contingency | 0 |  |  |  | Contingency | 8008.14 | Contingency | 1358422 | 0 | 0 | 0 | 1358422 | 1358422 | 1358422 | 0
[10 empty] | DPT | 8008.12 | DPT | 0 |  |  |  | DPT | 8008.12 | DPT | 49727.2 | 0 | 0 | 0 | 49727.2 | 49727 | 49727 | 0
[10 empty] | PMCM | 8008.13 | PMCM | 0 |  |  |  | PMCM | 8008.13 | PMCM | 0 |  | 0 | 0 | 0 | 1346548 | 1346547.859 | 0.14103 | $1,346,528 budget transferred from 8003.631
[10 empty] | Escalcation on Base | 8008.15 | Escalcation on Base | 0 |  |  |  | Escalcation on Base | 8008.15 | Escalcation on Base | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Remaining Allowance | 8008.16 | Remaining Allowance | 0 |  |  |  | Remaining Allowance | 8008.16 | Remaining Allowance | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 8008.1 Total |  |  |  | 0 |  |  | 8008.1 Total |  |  |  | 8400328.79 | 29920 | 0 | 29920 | 8400328.79 | 9746877 | 9766683.649 | -19806.649
[7 empty] | 8008 Total | [5 empty] | 0 | 8008 Total | [5 empty] | 8400328.79 | 29920 | 0 | 29920 | 8400328.79 | 9746877 | 9766683.649 | -19806.649
[7 empty] | Grand Total | [5 empty] | 143968130 | Grand Total | [5 empty] | 359216591.465 | 159009005.0793 | 143968130 | 14729512.5515 | 214088904.465 | 214088905 | 193204756.0679 | 20884148.9321

## CCE
HARD CODED
[16 empty] | CCE ESTIMATE Thru 05/31/12 | [7 empty] | PLANNED THROUGH 05/31/12 |  |  | ACTUAL THROUGH 5/31/12
[6 empty] | CCE |  | Staffing Plan (Proposed) |  |  |  | Yellow = Labor |  | Variance |  |  | Group | 2010 Update | 2011-2012 Update | Accrual | CCE Total | CCE Subtotal | tbd1 | Planned Total | Planned Subtotal | tbd2 | Actual | Accrual | Actual Total | Actual Subtotal | Variance (Plan vs. Actual thru 05/31/12) | Availabe fund to complete (CCE less Actual) | Estimate to complete | R | Remark | SCC1 | SCC2 | SCC3 | Group | SCC GROUP DESC | SCC2 Desc
[12 empty] | White = Non-Labor |  | from CCE
80 | Professional Services
| 80.01 | Prelim Engrg |  |  |  | 52562827 |  | 80.01 | Prelim Engrg |  |  | 46350794 |  | -6212033 |  | 80.01 | Prelim Engrg |  |  |  | 46220114 | 46220114 |  | 46220114 | 46220114 |  |  |  | 46220114 | 46220114 | 0 |  |  |  |  | 8001 | 8001 | 8001 | Prelim Engrg | Prelim Engrg
| 80.02 | Final Design |  |  |  | 87659910 |  | 80.02 | Final Design |  |  | 89505857.0823 |  | 1845947.0823 |  | 80.02 | Final Design |  |  |  |  | 83691705 |  |  | 58447440.6333 |  |  |  |  | 52462997
|  | 1 | SFMTA |  | 10734385 |  |  |  | SFMTA |  | 10503168.195 | [5 empty] | SFMTA
|  |  | PM | 4956999 |  |  |  |  | PM | 0 |  |  | -4956999 |  |  |  | PM | [18 empty] | 8002 | 8002.1 | 8002.11 | SFMTA-PM | Final Design | SFMTA
|  |  | Engrg | 3851590 |  |  |  |  | Engrg | 10503168.195 |  |  | 6651578.195 | 4.4M 80.02 Engineering Labor |  |  | Engrg | 10503168.195 | -2421393.195 |  | 8081775 |  |  | 4000830 |  |  | 8081775 |  | 8081775 |  | -4080945 | 0 |  |  |  | 8002 | 8002.1 | 8002.12 | SFMTA-Engrg | Final Design | SFMTA
|  |  | CM | 962898 |  |  |  |  | CM | 0 |  |  | -962898 | 2.9M Albert Hoe |  |  | CM | 0 |  |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8002 | 8002.1 | 8002.13 | SFMTA-CM | Final Design | SFMTA
|  |  | DPT | 962898 |  |  |  |  | DPT | 0 |  |  | -962898 |  |  |  | DPT | 0 |  |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8002 | 8002.1 | 8002.14 | SFMTA-DPT | Final Design | SFMTA
[18 empty] | 0 |  |  | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
|  | 2 | City/County |  | 938534 |  |  |  | City/County |  | 1273993 |  | 335459 |  |  |  | City/County | 0 |  |  | 0 | [7 empty] | 0 |  | 0 | 0
|  |  | City Att's Ofc | 0 |  |  |  |  | City Att (Allow for Contracts) | 285000 | [6 empty] | City Attorney | 285000 | -285000 |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8002 | 8002.2 | 8002.21 | City Attorney | Final Design | City/County
|  |  | Arts | 653000 |  |  | Per Agreement w/ Arts Comm |  | Arts Commission | 653000 | [6 empty] | Arts commission | 653000 | 0 |  | 653000 |  |  | 653000 |  |  | 653000 |  | 653000 |  | 0 | 0 |  |  |  | 8002 | 8002.2 | 8002.23 | Arts commission | Final Design | City/County
|  |  | Risk | 45000 |  |  | Budget Revision |  | Risk | 45000 | [6 empty] | Risk | 45000 |  |  | 45000 |  |  | 43500 |  |  | 0 |  | 0 |  | 43500 | 45000 |  |  |  | 8002 | 8002.2 | 8002.24 | Risk | Final Design | City/County
|  |  | Auditor | 100000 |  |  | Budget Revision |  | City Auditor | 100000 | [6 empty] | City Auditor | 100000 | 100220 |  | 200220 |  |  | 193546 |  |  | 121897 |  | 121897 |  | 71649 | 78323 |  |  |  | 8002 | 8002.2 | 8002.25 | City Auditor | Final Design | City/County
|  |  | Dept of Tech | 140534 |  |  | Memo - Budget Rev? Telephones |  | Dept of Tech | 140534 | [6 empty] | Dept. of Tech | 140534 |  |  | 140534 |  |  | 140534 |  |  | 124613 |  | 124613 |  | 15921 | 15921 |  |  |  | 8002 | 8002.2 | 8002.26 | Dept. of Tech | Final Design | City/County
[9 empty] | Fire Department | 16500 | [6 empty] | Fire Dept. | 16500 | 18040 |  | 34540 |  |  | 33388.6667 |  |  | 34540 |  | 34540 |  | -1151.3333 | 0 |  |  |  | 8002 | 8002.2 | 8002.27 | Fire Dept. | Final Design | City/County
[9 empty] | PUC | 32959 | [6 empty] | SF PUC | 32959 |  |  | 32959 |  |  | 31860.3667 |  |  | 21728 |  | 21728 |  | 10132.3667 | 11231 |  |  |  | 8002 | 8002.2 | 8002.28 | SF PUC | Final Design | City/County
[9 empty] | Dept. of Public Health | 1000 | [6 empty] | Dept of Public Health | 1000 | 267 |  | 1267 |  |  | 1267 |  |  | 1267 |  | 1267 |  | 0 | 0 |  |  |  | 8002 | 8002.2 | 8002.29 | Dept of Public Health | Final Design | City/County
|  | 3 | DPW |  | 4859007 | [15 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
|  |  | BOE | 1392573 |  |  | Allowance |  | DPW |  | 3600712.8873 |  | -1258294.1127 |  |  |  | DPW | 3600712.8873 | 12123.1127 |  | 3612836 |  |  | 3172091 |  |  | 2844328 |  | 2844328 |  | 327763 | 768508 |  |  |  | 8002 | 8002.3 | 8002.31 | DPW | Final Design | DPW
|  |  | BOA | 1155478 |  |  | Allowance | [13 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
|  |  | BCM | 1155478 |  |  | Allowance | [13 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
|  |  | BSM | 1155478 |  |  | Allowance | [13 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
[21 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
|  | 33 | SFCTA (+ Other Agencies) |  | 1155478 |  | Allowance - Ridership projections? | [13 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
[9 empty] | SFCTA |  | 1155478 |  | 0 |  |  |  | SFCTA | 1155478 | -1135478 |  | 20000 |  |  | 19333.3333 |  |  |  |  | 0 |  | 19333.3333 | 20000 |  |  |  | 8002 | 8002.4 | 8002.41 | SFCTA | Final Design | SFCTA
|  | 5 | Project ODCs |  | 3504022 | [15 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
[9 empty] | Project ODCs |  | 6504021 |  | 2999999 |  |  |  | Project ODCs | 6504021 | -2356718 |  | 4147303 |  |  | 4009059.5667 |  |  | 2717688 |  | 2717688 |  | 1291371.5667 | 1429615 |  |  |  | 8002 | 8002.6 | 8002.61 | Project ODCs | Final Design | Project ODCs
|  | 7 | Consultants |  | 66468484 | [15 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
[9 empty] | Consultants | [11 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
|  |  | DP1 | [5 empty] | Alloc Cntcy | [7 empty] | Alloc Cntcy |  | 352787 |  | 352787 |  |  | 0 |  |  |  |  | 0 |  | 0 | 352787 |  |  |  | 8002 | 8002.9 | 8002.9 | Alloc Cntcy | Final Design | Alloc Cntcy
|  |  | Labor | 5530612 |  |  | Total Agreemt = 6,500,000 |  | DP1 |  | 6500000 | [5 empty] | DP1 |  |  |  | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Final Design
|  |  | ODCs | 264388 |  |  |  |  | Labor | 5530612 |  |  | 0 |  |  |  | Labor | 5530612 | 696483 |  | 6227095 |  |  | 4748252 |  |  | 5820643 |  | 5820643 |  | -1072391 | 406452 |  |  |  | 8002 | 8002.81 | 8002.811 | DP1 - Labor | Final Design | DP1
|  |  | Alloc Cntcy/Options | 705000 |  |  |  |  | ODCs | 264388 | [6 empty] | ODCs | 264388 |  |  | 264388 |  |  | 251169 |  |  | 195334 |  | 195334 |  | 55835 | 69054 |  |  |  | 8002 | 8002.81 | 8002.812 | DP1 - ODCs | Final Design | DP1
[9 empty] | Alloc Cntcy/Options | 705000 | [6 empty] | Alloc cntcy/Options | 705000 | -696483 |  | 8517 | [9 empty] | 0 | 8517 |  |  |  | 8002 | 8002.81 | 8002.812 | Alloc cntcy/Options | Final Design | DP1
|  |  | DP2 | [17 empty] | 0 | [9 empty] | 0 | 0 | [7 empty] | Final Design
|  |  | Labor | 34157952 |  |  | Total Agreemt = 39,949,959 |  | DP2 |  | 39949959 | [5 empty] | DP2 |  |  |  | 0 | [7 empty] | 0 |  | 0 | 0
|  |  | ODCs | 1802600 |  |  |  |  | Labor | 34157952 |  |  | 0 |  |  |  | Labor | 34157952 | 475460 |  | 34633412 |  |  | 26155887 |  |  | 23583946 |  | 23583946 |  | 2571941 | 11049466 |  |  |  | 8002 | 8002.82 | 8002.821 | DP2 - Labor | Final Design | DP2
|  |  | Alloc Cntcy/Options | 3989407 |  |  |  |  | ODCs | 1802600 | [6 empty] | ODCs | 1802600 |  |  | 1802600 |  |  | 1622340 |  |  | 728114 |  | 728114 |  | 894226 | 1074486 |  |  |  | 8002 | 8002.82 | 8002.822 | DP2 - ODCs | Final Design | DP2
[9 empty] | Alloc Cntcy/Options | 3989407 | [6 empty] | Alloc cntcy/Options | 3989407 | -475460 |  | 3513947 |  |  | 2986854.95 | [6 empty] | 2986854.95 | 3513947 |  |  |  | 8002 | 8002.82 | 8002.823 | Alloc cntcy/Options | Final Design | DP2
|  |  | DP3 | [17 empty] | 0 | [9 empty] | 0 | 0
|  |  | Labor | 14896400 |  |  | Total Agreemt = 19,919,525 |  | DP3 |  | 19919525 | [5 empty] | DP3 |  |  |  | 0 | [9 empty] | 0 | 0
|  |  | ODCs | 424400 |  |  |  |  | Labor | 14896400 |  |  | 0 |  |  |  | Labor | 14896400 | 1179280 |  | 16075680 |  |  | 6902635 |  |  | 7511963.01 |  | 7511963.01 |  | -609328.01 | 8563716.99 |  |  |  | 8002 | 8002.83 | 8002.831 | DP3 - Labor | Final Design | DP3
|  |  | Alloc Cntcy/Options | 4598725 |  |  |  |  | ODCs | 424400 | [6 empty] | ODCs | 424400 |  |  | 424400 |  |  | 233420 |  |  | 22160.99 |  | 22160.99 |  | 211259.01 | 402239.01 |  |  |  | 8002 | 8002.83 | 8002.832 | DP3 - ODCs | Final Design | DP3
[9 empty] | Alloc Cntcy/Options | 4598725 | [6 empty] | Alloc cntcy/Options | 4598725 | -1179280 |  | 3419445 |  |  | 3248472.75 | [6 empty] | 3248472.75 | 3419445 |  |  |  | 8002 | 8002.83 | 8002.833 | Alloc cntcy/Options | Final Design | DP3
|  |  | Systra | 99000 |  |  | Simulation?
[9 empty] | Systra |  | 99000 |  | 0 | [7 empty] | 0
0
| 80.03 | Project Mgmt |  |  |  | 171988680 |  | 80.03 | Project Mgmt |  |  | 179499342.3917 |  | 7510662.3917 |  | 80.03 | Project Mgmt |  |  |  |  | 195485344.6379 |  |  | 38836962.3056 |  |  |  |  | 35279245
0
|  | 1 | SFMTA |  | 21824462 |  |  |  | SFMTA |  | 16917114.7538 | [5 empty] | SFMTA |  |  |  | 0 | [18 empty] | Project Mgmt
|  |  | PM | 18572456 |  |  |  |  | PM | 15960634.7538 |  |  | -2611821.2462 |  | Only SFMTA PM staff (not CM or Engrg) |  | PM | 18034926 |  |  | 18034926 |  |  | 4510875 |  |  | 6874676 |  | 6874676 |  | -2363801 | 11160250 |  |  |  | 8003 | 8003.1 | 8003.11 | SFMTA-PM | Project Mgmt | SFMTA
|  |  | Engrg | 0 |  |  |  |  | Engrg | 0 |  |  |  | 16M SFMTA PM |  |  | Engrg |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 8003 | 8003.1 | 8003.12 | SFMTA-Engrg | Project Mgmt | SFMTA
|  |  | CM | 3252006 |  |  |  |  | CM | 0 |  |  |  | 2.0M Safety Rep. 80.03 |  |  | CM |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  | 8003 | 8003.1 | 8003.13 | SFMTA-CM | Project Mgmt | SFMTA
|  |  | DPT | 0 |  |  |  |  | DPT | 956480 |  |  | 956480 |  |  |  | DPT | 956480 | -19134 |  | 937346 |  |  | 679280 |  |  | 837858 |  | 837858 |  | -158578 | 99488 |  |  |  | 8003 | 8003.1 | 8003.14 | SFMTA-DPT | Project Mgmt | SFMTA
[21 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Project Mgmt
|  | 2 | City/County |  | 4186488 |  | Per Agreement w/ Arts Comm |  | City/County (Arts Comm) |  | 4186488 | [5 empty] | Arts commission | 4186488 |  |  | 4186488 |  |  | 1124149.5556 |  |  | 303104 |  | 303104 |  | 821045.5556 | 3883384 |  |  |  | 8003 | 8003.2 | 8003.23 | Arts commission | Project Mgmt | City/County
[17 empty] | Risk | [18 empty] | 8003 | 8003.2 | 8003.24 | Risk | Project Mgmt | City/County
[17 empty] | City Auditor | [18 empty] | 8003 | 8003.2 | 8003.25 | City Auditor | Project Mgmt | City/County
[36 empty] | 8003 | 8003.2 | 8003.26 | Dept of Tech | Project Mgmt | City/County
[17 empty] | Dept of Public Health | [18 empty] | 8003 | 8003.2 | 8003.29 | Dept of Public Health | Project Mgmt | City/County
[21 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 | [7 empty] | Project Mgmt
|  | 5 | Project ODCs |  | 6502737 |  |  |  | Project ODCs |  | 3502737 | [5 empty] | Project ODCs | 3502737 |  |  | 3502737 |  |  | 940549.75 |  |  | 0 |  | 0 |  | 940549.75 | 3502737 |  |  |  | 8003 | 8003.61 | 8003.611 | Project ODCs | Project Mgmt | Project ODCs
[9 empty] | Aon Risk Ins. Study | [7 empty] | Aon Risk Ins. Study | 0 | 25000 |  | 25000 |  |  | 25000 |  |  | 25000 |  | 25000 |  | 0 | 0 |  |  |  | 8003 | 8003.62 | 8003.621 | Aon Risk Ins. Study | Project Mgmt | Aon Risk Ins. Study
|  | 7 | Consultants |  | 139474993 |  |  |  | Consultants |  | 154893002.6379 | [12 empty] | 0 |  |  |  |  | 0 |  | 0 | 0 | [7 empty] | Project Mgmt
[9 empty] | Contingency | [7 empty] | Contingency | 0 | 13905845 |  | 13905845 |  |  | 0 |  |  |  |  | 0 |  | 0 | 13905845 |  |  |  | 8003 | 8003.64 | 8003.641 | Contingency | Project Mgmt | Contingency
|  |  | PMCM (AECOM-EPC) |  |  |  | Per Agreement |  | PMCM | [11 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Project Mgmt
|  |  | Labor | 123292518 |  |  |  |  | Labor | 111672723.6379 |  |  | 4167410.6379 |  |  |  | PMCM-Labor | 111672723.6379 |  |  | 111672723.6379 |  |  | 20284112.3333 |  |  | 20486324.23 |  | 20486324.23 |  | -202211.8967 | 91186399.4079 |  |  |  | 8003 | 8003.63 | 8003.631 | PMCM-Labor | Project Mgmt | Consultants
|  |  | PMCM ODCs & 2009 | 15787205 |  |  |  | 137384859.6379 | PMCM ODCs & 2009 | 25712136 | Offset PCC Contract Value and added the $825K reduction from SFMTA PM Labor with correct resource |  |  |  |  | 137384859.6379 | PMCM-ODCs | 25712136 |  |  | 25712136 |  |  | 6904184.6667 |  |  | 2675350.77 |  | 2675350.77 |  | 4228833.8967 | 23036785.23 |  |  |  | 8003 | 8003.63 | 8003.632 | PMCM-ODCs | Project Mgmt | Consultants
[21 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Project Mgmt
|  |  | Anil Verma | 395270 |  |  | Per Agreement |  | Anil Verma | 395270 | [6 empty] | Anil Verma | 395270 |  |  | 395270 |  |  | 395270 |  |  | 395204 |  | 395204 |  | 66 | 66 |  |  |  | 8003 | 8003.63 | 8003.633 | Anil Verma | Project Mgmt | Consultants
[21 empty] | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Project Mgmt
|  |  | PCC | 0 |  |  |  |  | PCC | 17112873 | PCC Backup Labor total is higher than contract value. Contract value included here |  |  |  | Moved from CM to PM |  | PCC | 17112873 |  |  | 17112873 |  |  | 3973541 |  |  | 3681728 |  | 3681728 |  | 291813 | 13431145 |  |  |  | 8003 | 8003.63 | 8003.634 | PCC | Project Mgmt | Consultants
[9 empty] | Subtotal: | 154893002.6379 | [10 empty] | 0 | [7 empty] | 0
0
| 80.04 | Constr Mgmt |  |  |  | 18259482 |  | 80.04 | Constr Mgmt |  |  | 16938695.5623 |  | -1320786.4377 |  | 80.04 | Constr Mgmt |  |  |  |  | 15549020.675 |  |  | 4367331.3333 |  |  |  |  | 2923031
|  | 1 | SFMTA |  | 1251387 |  |  |  | SFMTA |  | 5430024.675 | [5 empty] | SFMTA
|  |  | PM | 0 |  |  |  |  | PM | 0 | [6 empty] | PM | 0 | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8004 | 8004.1 | 8004.11 | SFMTA-PM | Constr Mgmt | SFMTA
|  |  | Engrg | 0 |  |  |  |  | Engrg | 0 | [6 empty] | Engrg | 0 | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8004 | 8004.1 | 8004.12 | SFMTA-Engrg | Constr Mgmt | SFMTA
|  |  | CM | 417129 |  |  |  |  | CM | 5430024.675 |  |  | 5012895.675 |  |  |  | CM | 5430024.675 | -1527552 |  | 3902472.675 |  |  | 1261346 |  |  | 533057 |  | 533057 |  | 728289 | 3369415.675 |  |  |  | 8004 | 8004.1 | 8004.13 | SFMTA-CM | Constr Mgmt | SFMTA
|  |  | DPT | 834258 |  |  |  |  | DPT | 0 | [6 empty] | DPT | 0 | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8004 | 8004.1 | 8004.14 | SFMTA-DPT | Constr Mgmt | SFMTA
[9 empty] | Engrg - IRP | [7 empty] | SFMTA-Engrg IRP |  | 50000 |  | 50000 |  |  | 50000 |  |  | 7263 |  | 7263 |  | 42737 | 42737 |  |  |  | 8004 | 8004.1 | 8004.15 | SFMTA-Engrg IRP | Constr Mgmt | SFMTA
|  | 3 | DPW |  | 6590966 |  |  |  | DPW |  | 11091541.8873 | [5 empty] | DPW |  | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0
|  |  | BOE | 0 |  |  |  |  | BOE | 3600712.8873 |  |  | 3600712.8873 |  |  |  | BOE | 3600712.8873 | -1872768.8873 |  | 1727944 |  |  | 0 |  |  | 0 |  | 0 |  | 0 | 1727944 |  |  |  | 8004 | 8004.3 | 8004.31 | BOE | Constr Mgmt | DPW
|  |  | BOA | 0 |  |  |  |  | BOA | 0 | [6 empty] | BOA | 0 | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8004 | 8004.3 | 8004.32 | BOA | Constr Mgmt | DPW
|  |  | BCM | 6054537 |  |  | Allowance |  | BCM | 6954400 |  |  | 899863 |  |  |  | BCM | 6954400 | -202100 |  | 6752300 |  |  | 2219200 |  |  | 2052256 |  | 2052256 |  | 166944 | 4700044 |  |  |  | 8004 | 8004.3 | 8004.33 | BCM | Constr Mgmt | DPW
|  |  | BCM | 119300 |  |  | MOU - Environmental |  | BCM | 119300 | [6 empty] | BCM | 119300 | 2062746 |  | 2182046 |  |  | 585919.7593 |  |  | 293879 |  | 293879 |  | 292040.7593 | 1888167 |  |  |  | 8004 | 8004.3 | 8004.34 | BCM (SAR) | Constr Mgmt | DPW
|  |  | BSM | 417129 |  |  | Allowance |  | BSM | 417129 | [6 empty] | BSM | 417129 | 0 |  | 417129 |  |  | 112006.8611 |  |  | 9268 |  | 9268 |  | 102738.8611 | 407861 |  |  |  | 8004 | 8004.3 | 8004.35 | BSM | Constr Mgmt | DPW
[19 empty] | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0
|  | 5 | Project ODCs |  | 417129 |  |  |  | ODCs |  | 417129 | [5 empty] | Project ODCs | 417129 | 0 |  | 417129 |  |  | 112006.8611 |  |  |  |  | 0 |  | 112006.8611 | 417129 |  |  |  | 8004 | 8004.61 | 8004.61 | Project ODCs | Constr Mgmt | ODCs
[18 empty] | 0 | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0
|  | 7 | Consultants |  | 10000000 |  |  |  | Consultants |  | 0 | [7 empty] | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Constr Mgmt | Consultants
[9 empty] | IRP APTA | [7 empty] | IRP APTA | 0 | 100000 |  | 100000 |  |  | 26851.8519 |  |  | 27308 |  | 27308 |  | -456.1481 | 72692 |  |  |  | 8004 | 8004.71 | 8004.711 | IRP APTA | Constr Mgmt | Consultants
|  |  | PMCM (AECOM-EPC) | 0 |  |  |  |  | PMCM | 0 |  |  | 0 |  |  |  | PMCM |  | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8004 | 8004.71 | 8004.712 | PMCM | Constr Mgmt | Consultants
[18 empty] | 0 | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 | [7 empty] | Constr Mgmt | Consultants
|  |  | PCC | 10000000 |  |  | Neilson directed to 80.04 |  | PCC | 0 |  |  |  |  | Moved from CM to PM |  | PCC |  | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8004 | 8004.71 | 8004.713 | PCC | Constr Mgmt | Consultants
[21 empty] | 0 | [9 empty] | 0 | 0 |  |  |  | 8004 | 8004.81 | 8004.811 | DP1 | Constr Mgmt | Consultants
[36 empty] | 8004 | 8004.81 | 8004.812 | DP1 - ODC's | Constr Mgmt | Consultants
[36 empty] | 8004 | 8004.81 | 8004.813 | Alloc cntcy/Options | Constr Mgmt | Consultants
[36 empty] | 8004 | 8004.82 | 8004.821 | DP2 | Constr Mgmt | Consultants
[36 empty] | 8004 | 8004.82 | 8004.822 | DP2 - ODC's | Constr Mgmt | Consultants
[36 empty] | 8004 | 8004.82 | 8004.823 | Alloc cntcy/Options | Constr Mgmt | Consultants
[21 empty] | 0 | [14 empty] | 8004 | 8004.83 | 8004.831 | DP3 | Constr Mgmt | Consultants
[36 empty] | 8004 | 8004.83 | 8004.832 | DP3 - ODC's | Constr Mgmt | Consultants
[36 empty] | 8004 | 8004.83 | 8004.833 | Alloc cntcy/Options | Constr Mgmt | Consultants
[36 empty] | 8004 | 8004.64 | 8004.641 | Contingency | Constr Mgmt | Contingency
| 80.05 | Non-Constr Insurance |  |  |  | 7019120 |  | 80.05 | Non-Constr Insurance |  |  | 6800000 |  | -219120 |  | 80.05 | Non-Constr Insurance | 0 | 6800000 |  | 6800000 | 6800000 |  | 6045933.22 | 6045933.22 |  | 6045933 |  | 6045933 | 6045933 | 0.22 | 754067 |  |  |  | 8005 | 8005 | 8005 | Non-Constr Insurance | Non-Constr Insurance | Non-Constr Insurance
Awarded Contract Value
| 80.06 | Legal, Permits, Reviews |  |  |  | 9925546 |  | 80.06 | Legal, Permits, Reviews |  |  | 9925546 |  | 0 |  | 80.06 | Legal, Permits, Review |  |  |  |  | 7339321 |  |  | 4740315.587 |  |  |  |  | 776131
[9 empty] | City attorney-PE | [7 empty] | City Attorney-PE |  | 96981 |  | 96981 |  |  | 96981 |  |  | 96981 |  | 96981 |  | 0 | 0 |  |  |  | 8006 | 8006.1 | 8006.11 | City Attorney-PE | Legal, Permits, Reviews | City Attorney-PE
[9 empty] | City attorney - FD | [7 empty] | City Attorney - FD |  | 705187 |  | 705187 |  |  | 681680.7667 |  |  | 532723 |  | 532723 |  | 148957.7667 | 172464 |  |  |  | 8006 | 8006.1 | 8006.12 | City Attorney - FD | Legal, Permits, Reviews | City Attorney - FD
[9 empty] | City Attorney - Const. | [7 empty] | City Attorney - Const. |  | 280000 |  | 280000 |  |  | 75185.1852 |  |  | 0 |  | 0 |  | 75185.1852 | 280000 |  |  |  | 8006 | 8006.1 | 8006.13 | City Attorney - Const. | Legal, Permits, Reviews | City Attorney - Const.
[9 empty] | SF Plannning | [7 empty] | SF Plannning |  | 236666 |  | 236666 |  |  | 228777.1333 |  |  | 0 |  | 0 |  | 228777.1333 | 236666 |  |  |  | 8006 | 8006.1 | 8006.14 | SF Plannning | Legal, Permits, Reviews | SF Plannning
|  |  | Legal, Permits | 8925546 |  |  |  |  | Remaining Allowance | 8127763 | [6 empty] | Remaining Allowance | 8127763 | -6104559 |  | 2023204 |  |  | 543267.7407 |  |  |  |  | 0 |  | 543267.7407 | 2023204 |  |  |  | 8006 | 8006.1 | 8006.15 | Remaining Allowance | Legal, Permits, Reviews | Remaining Allowance
|  |  | BART | 1000000 |  |  | As per Budget Rev, add'l 797,783 |  | BART | 1797783 | [6 empty] | BART | 1797783 | 0 |  | 1797783 |  |  | 1797783 |  |  | 146427 |  | 146427 |  | 1651356 | 1651356 |  |  |  | 8006 | 8006.1 | 8006.16 | BART | Legal, Permits, Reviews | BART
[9 empty] | Dept. of Bldg. Inspection | [7 empty] | Dept. of Bldg. Inspection |  | 1039943 |  | 1039943 |  |  | 1005278.2333 | [6 empty] | 1005278.2333 | 1039943 |  |  |  | 8006 | 8006.1 | 8006.17 | Dept. of Bldg. Inspection | Legal, Permits, Reviews | Dept. of Bldg. Inspection
[9 empty] | Legal Permit Contingency | [7 empty] | Legal Permit Contingency |  | 1159557 |  | 1159557 |  |  | 311362.5278 | [11 empty] | 8006 | 8006.1 | 8006.18 | Legal Permit Contingency | Legal, Permits, Reviews | Legal Permit Contingency
[36 empty] | 8006 | 8006.1 | 8006.29 | Dept of Public Health | Legal, Permits, Reviews | Dept of Public Health
0
| 80.07 | Survey, Tests, Investigations |  |  |  | 14971137 |  | 80.07 | Survey, Tests, Investigations |  |  | 14971137 |  | 0 |  | 80.07 | Survey, Tests & Investigations |  |  |  |  | 323758 |  |  | 320988 |  |  |  |  | 260679
[21 empty] | 0 | [9 empty] | 0 | 0
|  |  | SFPUC - CM | 65000 |  |  | MOU |  | SFPUC - CM 1250 | 65000 | [6 empty] | SFPUC - CM 1250 | 65000 | -9064 |  | 55936 |  |  | 55936 |  |  | 55936 |  | 55936 |  | 0 | 0 |  |  |  | 8007 | 8007.1 | 8007.11 | SFPUC - CM 1250 | Survey, Tests, Investigations | SFPUC - CM 1250
|  |  | DPW - Matls Testing | 83100 |  |  | MOU |  | DPW - Matls Testing | 83100 | [6 empty] | DPW - Matls Testing | 83100 | 0 |  | 83100 |  |  | 80330 |  |  | 20021 |  | 20021 |  | 60309 | 63079 |  |  |  | 8007 | 8007.1 | 8007.12 | DPW - Matls Testing | Survey, Tests, Investigations | DPW - Matls Testing
[9 empty] | PUC 1251 | [7 empty] | PUC 1251 |  | 120784 |  | 120784 |  |  | 120784 |  |  | 120784 |  | 120784 |  | 0 | 0 |  |  |  | 8007 | 8007.1 | 8007.13 | PUC 1251 | Survey, Tests, Investigations | PUC 1251
[9 empty] | JOC 15&22 Potholing UTL1 | [7 empty] | JOC 15&22 Potholing UTL1 |  | 63938 |  | 63938 |  |  | 63938 |  |  | 63938 |  | 63938 |  | 0 | 0 |  |  |  | 8007 | 8007.1 | 8007.14 | JOC 15&22 Potholing UTL1 | Survey, Tests, Investigations | JOC 15&22 Potholing UTL1
[36 empty] | 8007 | 8007.1 | 8007.28 | PUC Inspections | Survey, Tests, Investigations | PUC 1300
|  |  | Other | 14823037 |  |  |  |  | Remaining Allowance | 14823037 | [6 empty] | Remaining Allowance | 14823037 | -14823037 |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8007 | 8007.1 | 8007.15 | Remaining Allowance | Survey, Tests, Investigations | Remaining Allowance
[21 empty] | 0 | [7 empty] | 0
0
| 80.08 | Start-up |  |  |  | 22524792 | Total reflects allowance for all S-U | 80.08 | Start-up |  |  | 26098436.79 |  | 3573644.79 |  | 80.08 | Start Up |  |  |  |  | 8400328.79 |  |  | 29920 |  |  |  |  | 0
[21 empty] | 0 | [7 empty] | 0 |  | 0 | 0
|  |  | SFMTA | [5 empty] | SFMTA | 6992179.59 |  |  | 6992179.59 |  |  |  | SFMTA | 6992179.59 | 0 |  | 6992179.59 |  |  | 29920 |  |  |  |  | 0 |  | 29920 | 6992179.59 |  |  |  | 8008 | 8008.1 | 8008.11 | SFMTA | Start-up | SFMTA
|  |  | DPT | [5 empty] | DPT | 49727.2 |  |  | 49727.2 |  |  |  | DPT | 49727.2 | 0 |  | 49727.2 |  |  | 0 |  |  |  |  | 0 |  | 0 | 49727.2 |  |  |  | 8008 | 8008.1 | 8008.12 | DPT | Start-up | DPT
|  |  | PMCM | 0 |  |  |  |  | PMCM | 0 |  |  | 0 |  |  |  | PMCM | 0 |  |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8008 | 8008.1 | 8008.13 | PMCM | Start-up | PMCM
[9 empty] | Contingency | [7 empty] | Contingency |  | 1358422 |  | 1358422 |  |  | 0 |  |  |  |  | 0 |  | 0 | 1358422 |  |  |  | 8008 | 8008.1 | 8008.14 | Contingency | Start-up | Contingency
[9 empty] | Escalcation on Base | 413286 | [6 empty] | Escalcation on Base |  |  |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8008 | 8008.1 | 8008.15 | Escalcation on Base | Start-up | Escalcation on Base
[9 empty] | Remaining Allowance | 18643244 | [6 empty] | Remaining Allowance |  |  |  | 0 | [7 empty] | 0 |  | 0 | 0 |  |  |  | 8008 | 8008.1 | 8008.16 | Remaining Allowance | Start-up | Remaining Allowance
[6 empty] | 384911494 | [5 empty] | 390089808.8263 | 5178314.8263 | [8 empty] | 363809592.1029 |  |  | 159009005.0793 |  |  |  |  | 143968130
[19 empty] | -2268297.9696 | [15 empty] | Total 80 current CCE
[9 empty] | Subtotals - Labor Only: | [15 empty] | 112788891.0793 |  |  |  |  | 97748016
[9 empty] | SFMTA |  | 38886007.2138 | [10 empty] | -2356718 | [12 empty] | Advance credit ODC for near completion of FD
[9 empty] | SFMTA - Real Estate SCC 60 |  | 1044785.218 | [10 empty] | 366166310.1029
[9 empty] | DPT |  | 1006207.2 | [10 empty] | 361568360
[9 empty] | DPW - FD |  | 3600712.8873 | [10 empty] | -4597950.1029
[9 empty] | DPW - CM |  | 6954400
Note on U34: Clifford, Alex J: changed from 'Dept of tech' to 'SFPUC' as per cost report code
Note on AQ34: Clifford, Alex J: changed from 'Dept of tech' to 'SFPUC' as per cost report code
Note on X50: Clifford, Alex; 10/19/12 transferred $737,727k of the CCE labor total to 8004.811

## SFMTA without PMCM duplicates
| M544.1 | Central Subway | [27 empty] | Approvals: | PM
| PM | Funghi, John O | [28 empty] | PE/RE
| PE | Hoe, Albert | [28 empty] | S/MGR
| RE | [29 empty] | MGR
[7 empty] | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 |  | Totals
| 2111.1 | Project Management
|  | MPM | R | 5508 | Funghi, John O | 2371.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144
|  | MPM | A | 5502 | Ames, Lewis T | 1513.326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144
|  | MPM | Q | 5211 | Nguyen, Roger Q | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40
|  | MPM | A | 5207 | Ng, Elisa | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32
|  | MPM | A | 5203 | Ancheta, Bernardino | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28
|  | MPM | B | 5201 | Chin, Tiffany | 997.688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72
|  | MPM | A | 1824 | Gallardo, Mario | 1324.238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
|  | MCE | S | 1844 | Haddad, Leila | 1034.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32
|  | MCE | S | 1842 | Katz, Jessie | 902.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
|  | MCE | R | 1426 | Nacion, Joery R | 692.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144
[5 empty] | Man Days Task | 2111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 668
PM |  |  |  |  | Dollars Task | 2111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113993.318 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 943521.752
[5 empty] | Man Days Div | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 668
[5 empty] | Dollars Div | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113993.318 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 943521.752
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 4; 2012-11-01: 4.2; 2012-12-01: 4.2; 2013-01-01: 4.2; 2013-02-01: 4.2; 2013-03-01: 4.2; 2013-04-01: 4.2; 2013-05-01: 4.2
| 2121.1 | Coordination
|  | MCE | R | 5241 | Hoe, Albert | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 102
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 19 | 19 | 25 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 197
PM |  |  |  |  | Dollars Task | 2121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55453.788 | 30524.028 | 30524.028 | 39014.328 | 39014.328 | 39014.328 | 39014.328 | 39014.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 311573.484
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 1.7; 2012-11-01: 0.95; 2012-12-01: 0.95; 2013-01-01: 1.25; 2013-02-01: 1.25; 2013-03-01: 1.25; 2013-04-01: 1.25; 2013-05-01: 1.25
| 2121.1 | Engineering Services - IRP
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
PM |  |  |  |  | Dollars Task | 2121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28124.352
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0.1; 2012-11-01: 0.1; 2012-12-01: 0.1; 2013-01-01: 0.1; 2013-02-01: 0.1; 2013-03-01: 0.1; 2013-04-01: 0.1; 2013-05-01: 0.1
| 2126.3 | Engineering Support - Overhead
|  | MCE | G | 5241 | Phang, Tee S | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
|  | MCE | G | 5241 | Leung, So-Man | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
|  | MCE | G | 5203 | David, Chris R | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2126.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19
PM |  |  |  |  | Dollars Task | 2126.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25332.194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25332.194
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0.95; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2126.5 | Engineering Services - Mechanical
|  | MCE | M | 5211 | Eng, Foo O | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
|  | MCE | M | 5241 | Huey, Lang A | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
|  | MCE | M | 5203 | Lee, Timothy C | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
|  | MCE | M | 5201 | Becker, John | 997.688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2126.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19
PM |  |  |  |  | Dollars Task | 2126.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23713.128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23713.128
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0.95; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2126.6 | Engineering Services - Electrical
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22
|  | MCE | N | 5241 | Leung, Frank W | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
|  | MCE | R | 5207 | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22
|  | MCE | N | 5207 | Green, Meghan V | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
PM |  |  |  |  | Dollars Task | 2126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65092.3 | 5660.2 | 5660.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76412.7
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 2.3; 2012-11-01: 0.2; 2012-12-01: 0.2; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2127 | Final Design Cost Estimate
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
FD |  |  |  |  | Dollars Task | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2128 | Specifications & Calculations
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
FD |  |  |  |  | Dollars Task | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2129 | Bid and Award
|  | MCE | R | 5241 | Hoe, Albert | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 42
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63
|  | MCE | R | 5207 | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63
|  | MCE | G | 5241 | Leung, So-Man | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 49
|  | MCE | M | 5241 | Huey, Lang A | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 49
|  | MCE | M | 5203 | Lee, Timothy C | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 343
CM |  |  |  |  | Dollars Task | 2129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72466.732 | 72466.732 | 72466.732 | 72466.732 | 72466.732 | 72466.732 | 72466.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 507267.124
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0; 2012-11-01: 2.45; 2012-12-01: 2.45; 2013-01-01: 2.45; 2013-02-01: 2.45; 2013-03-01: 2.45; 2013-04-01: 2.45; 2013-05-01: 2.45
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 3131 | Construction Management (68A065)
|  | MCE | R | 5211 | Wong, Arthur G | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
|  | MCE | R | 6318 | Volberding, Ben | 1138.571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
|  | MPM | B | 5380 | Ciardi, Vincenzo | 588.412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 162
CM |  |  |  |  | Dollars Task | 3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62725.59 | 62725.59 | 62725.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 188176.77
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 2.7; 2012-11-01: 2.7; 2012-12-01: 2.7; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 3111.1 | Project Management
|  | MPM | R | 5508 | Funghi, John O | 2371.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MPM | A | 5502 | Ames, Lewis T | 1513.326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MPM | Q | 5211 | Nguyen, Roger Q | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 65
|  | MPM | A | 5207 | Ng, Elisa | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 52
|  | MPM | A | 5203 | Ancheta, Bernardino | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MPM | B | 5201 | Chin, Tiffany | 997.688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 117
|  | MPM | A | 1824 | Gallardo, Mario | 1324.238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
|  | MCE | S | 1844 | Haddad, Leila | 1034.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28
|  | MCE | S | 1842 | Katz, Jessie | 902.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 26
|  | MCE | R | 1426 | Nacion, Joery R | 692.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MCE | R | 5241 | Hoe, albert | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 156
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 65
|  | MPM | S | 5504 | PM II MPMS | 1751.241 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0
|  | MPM | S | 5504 | PM II MPMS | 1751.241 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MPM | S | 5506 | PM III MPMS | 2126.618 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0
[5 empty] | Man Days Task | 3111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 91 | 91 | 91 | 91 | 91 | 91 |  | 1225
PM |  |  |  |  | Dollars Task | 3111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141001.802 | 141001.802 | 141001.802 | 141001.802 | 141001.802 | 141001.802 | 141001.802 | 134214.538 | 134214.538 | 134214.538 | 134214.538 | 134214.538 | 134214.538 |  | 1792299.842
[5 empty] | FTE's = (man days x 8)/160 |  | 2013-06-01: 4.85; 2013-07-01: 4.85; 2013-08-01: 4.85; 2013-09-01: 4.85; 2013-10-01: 4.85; 2013-11-01: 4.85; 2013-12-01: 4.85; 2014-01-01: 4.55; 2014-02-01: 4.55; 2014-03-01: 4.55; 2014-04-01: 4.55; 2014-05-01: 4.55; 2014-06-01: 4.55
| 3121 | Design Support to Construction
|  | MCE | R | 5241 | Hoe, Albert | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | 78
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 156
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
CM |  |  |  |  | Dollars Task | 3121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 |  | 392639.988
[5 empty] | FTE's = (man days x 8)/160 |  | 2013-06-01: 0.9; 2013-07-01: 0.9; 2013-08-01: 0.9; 2013-09-01: 0.9; 2013-10-01: 0.9; 2013-11-01: 0.9; 2013-12-01: 0.9; 2014-01-01: 0.9; 2014-02-01: 0.9; 2014-03-01: 0.9; 2014-04-01: 0.9; 2014-05-01: 0.9; 2014-06-01: 0.9
| 3121.2 | Design Support to Construction - Mechanical
|  | MCE | M | 5211 | Eng, Foo O | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 |  | 7
|  | MCE | M | 5241 | Huey, Lang A | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 97
|  | MCE | M | 5203 | Lee, Timothy C | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 4 | 4 | 4 | 4 | 4 | 4 |  | 34
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3121.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 11 | 11 | 11 | 13 | 14 | 13 | 14 | 13 | 14 |  | 138
CM |  |  |  |  | Dollars Task | 3121.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8132.65 | 7502.564 | 8132.65 | 7502.564 | 14691.64 | 14061.554 | 14691.64 | 16316.926 | 18074.698 | 16316.926 | 18074.698 | 16316.926 | 18074.698 |  | 177890.134
[5 empty] | FTE's = (man days x 8)/160 |  | 2013-06-01: 0.3; 2013-07-01: 0.3; 2013-08-01: 0.3; 2013-09-01: 0.3; 2013-10-01: 0.55; 2013-11-01: 0.55; 2013-12-01: 0.55; 2014-01-01: 0.65; 2014-02-01: 0.7; 2014-03-01: 0.65; 2014-04-01: 0.7; 2014-05-01: 0.65; 2014-06-01: 0.7
| 3121.3 | Design Support to Construction - Electrical
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 3 | 3 | 3 | 3 | 3 | 3 |  | 81
|  | MCE | N | 5241 | Leung, Frank W | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MCE | R | 5207 | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 3 | 3 | 3 | 3 | 3 | 3 |  | 81
|  | MCE | N | 5207 | Green, Meghan V | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 26
|  | MCE | N | 5207 | Associate Engineer MCEN | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 |  | 36
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MCE | N | 5241 | Engineer MCEN | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 |  | 36
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3121.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 260
CM |  |  |  |  | Dollars Task | 3121.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 |  | 365228.448
FTE's = (man days x 8)/160 | bar: 2013-06-01 to 2014-06-01
| 3121.4 | Design Support to Construction - Overhead
|  | MCE | G | 5241 | Phang, Tee S | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 |  | 31
|  | MCE | G | 5241 | Leung, So-Man | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MCE | G | 5203 | David, Chris R | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 8 | 8 | 8 | 8 | 8 | 8 |  | 57
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3121.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 10 | 9 | 10 | 9 | 10 | 9 |  | 88
CM |  |  |  |  | Dollars Task | 3121.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2645.988 | 4164.29 | 2645.988 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 12058.092 | 10539.79 | 12058.092 | 10539.79 | 12058.092 | 10539.79 |  | 111345.464
[5 empty] | FTE's = (man days x 8)/160 | [9 empty] | 0.1 | 0.15 | 0.1 | 0.15 | 0.05 | 0.15 | 0.05 | 0.15 | 0.05 | 0.15 | 0.05 | 0.15 | 0.05 | 0.15 | 0.05 | 0.5 | 0.45 | 0.5 | 0.45 | 0.5 | 0.45
| 3126 | Contract Closeout
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 3126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | FTE's = (man days x 8)/160 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3128 | Construction Support for Project Closeout
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | FTE's = (man days x 8)/160 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3131 | Construction
| 3131 | Construction Management
|  | MCE | R | 5211 | Wong, Arthur G | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 324
|  | MCE | R | 6318 | Volberding, Ben | 1138.571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 324
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 |  | 72
|  | MCE | R | 5207 | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 12 | 12 | 12 | 12 | 12 | 12 |  | 93 | man days
|  | MCE | D | 5211 | Senior Engineer MCED | 1757.772 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0 | 18
|  | MCE | D | 5207 | Associate Engineer MCED | 1311.798 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0 | 18
|  | MCE | D | 5211 | Senior Engineer MCED | 1757.772 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0 | 18
|  | MCE | D | 5207 | Associate Engineer MCED | 1311.798 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0 | 18
|  | MCE | D | 5211 | Senior Engineer MCED | 1757.772 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0 | 18
|  | MCE | D | 5207 | Associate Engineer MCED | 1311.798 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0 | 18
|  | MCE | D | 5241 | Engineer MCED | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 18
|  | MCE | D | 5207 | Associate Engineer MCED | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 18
|  |  |  | 6318 | Construct Inspector | 1138.571 | 2006-09-01: 0; 2006-10-01: 0; 2006-11-01: 0; 2006-12-01: 0; 2007-01-01: 0; 2007-02-01: 0; 2007-03-01: 0; 2007-04-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0 |  | 0 | 36 / 54
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 60 | 60 | 60 | 60 | 60 | 60 |  | 813
CM |  |  |  |  | Dollars Task | 3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52134.174 | 52134.174 | 52134.174 | 52134.174 | 52134.174 | 56069.568 | 56069.568 | 56069.568 | 56069.568 | 56069.568 | 56069.568 | 56069.568 | 86095.374 | 86095.374 | 86095.374 | 86095.374 | 86095.374 | 86095.374 |  | 1169730.09
[5 empty] | FTE's = (man days x 8)/160 | [9 empty] | 0 | 0 | 0 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 3 | 3 | 3 | 3 | 3 | 3
| 1121.19 | Task
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 1121.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 1121.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 1121.2 | Task
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 1121.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 1121.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Div | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 131 | 130 | 115 | 113 | 115 | 113 | 115 | 181 | 183 | 181 | 183 | 186 | 188 | 186 | 212 | 212 | 212 | 212 | 212 | 212 |  | 3568
[5 empty] | Dollars Div | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238478.532 | 179056.384 | 177538.082 | 171295.068 | 168649.08 | 171295.068 | 168649.08 | 171295.068 | 265019.894 | 267035.796 | 265019.894 | 267035.796 | 271578.884 | 273594.786 | 271578.884 | 306982.502 | 307221.972 | 306982.502 | 307221.972 | 306982.502 | 307221.972 |  | 5169733.718
| 1131 | Task
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Div | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Div | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Phase | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 215 | 214 | 199 | 197 | 199 | 197 | 199 | 181 | 183 | 181 | 183 | 186 | 188 | 186 | 212 | 212 | 212 | 212 | 212 | 212 |  | 4236
[5 empty] | Dollars Phase | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352471.85 | 297560.446 | 296042.144 | 289799.13 | 287153.142 | 289799.13 | 287153.142 | 289799.13 | 265019.894 | 267035.796 | 265019.894 | 267035.796 | 271578.884 | 273594.786 | 271578.884 | 306982.502 | 307221.972 | 306982.502 | 307221.972 | 306982.502 | 307221.972 |  | 6113255.47
[6 empty] | Total $ (all of the above) | [8 empty] | 352471.85 | 297560.446 | 296042.144 | 289799.13 | 287153.142 | 289799.13 | 287153.142 | 289799.13 | 265019.894 | 267035.796 | 265019.894 | 267035.796 | 271578.884 | 273594.786 | 271578.884 | 306982.502 | 307221.972 | 306982.502 | 307221.972 | 306982.502 | 307221.972 |  | 6113255.47
[22 empty] | Average $298,722 from October 2012 - May 2013 | Average $627,461 per month from June 2013 to June 2014
[5 empty] | SFMTA - remaining cost to complete | estimate June '12 to Sept '12, $298,722 x 4 months | [8 empty] | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above |  | estimate Q3, Q4, 2014 | estimate Q1, Q2, 2015 | estimate Q3, Q4, 2015 | estimate Q1, Q2, 2016 | estimate Q3, Q4, 2016 | estimate Q1, Q2, 2017 | estimate Q3, Q4, 2017 | estimate Q1, Q2, 2018 | estimate Q3, Q4, 2018 | estimate Q1, Q2, 2019 | estimate Q3, Q4, 2019
[5 empty] | Original Staff plan SFMTA Total FTE's | [9 empty] | 10.82 | 10.82 | 10.82 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 |  | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 7.05 | 0
[5 empty] | Original Staff plan SFMTA Peak FTE's | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75806 | 0
[5 empty] | October 2012, SFMTA update Total FTE's | [9 empty] | 12.8 | 10.75 | 10.7 | 9.95 | 9.85 | 9.95 | 9.85 | 9.95 | 9.05 | 9.15 | 9.05 | 9.15 | 9.3 | 9.4 | 9.3 | 10.6 | 10.6 | 10.6 | 10.6 | 10.6 | 10.6
[5 empty] | October update % relative to original plan | [9 empty] | 118.3% | 99.35% | 98.89% | 92.13% | 91.2% | 92.13% | 91.2% | 92.13% | 83.8% | 84.72% | 83.8% | 84.72% | 86.11% | 87.04% | 86.11% | 114% | 114% | 114% | 114% | 114% | 114%
| SFMTA to complete (excludes start up, safety & security) |  |  |  | 25848466.0506 | 1194888 | [8 empty] | 352471.85 | 297560.446 | 296042.144 | 289799.13 | 287153.142 | 289799.13 | 287153.142 | 289799.13 | 265019.894 | 267035.796 | 265019.894 | 267035.796 | 271578.884 | 273594.786 | 271578.884 | 306982.502 | 307221.972 | 306982.502 | 307221.972 | 306982.502 | 307221.972 |  | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1440322.5806 | 0
ALBERT HOE TO ADVISE/CONFIRM EXPECTED PEAK FTE'S AT 23, OR INCLUDE CONTINGENCY FOR ADDITIONAL DURING CONSTRUCTION
[5 empty] | ORIGINAL STAFF PLAN SFMTA PEAKS AT 35 FTE's | [30 empty] | average expenditure for 6 months, 408,546 x 6 = | 1900000
$16m spend to date
[37 empty] | allocate | 43.7% | of total to PM |  | allocate | 56.3% | to CM
|  |  |  | PM | SFMTA PM - 8003 | 382364.16 | [8 empty] | 287100.272 | 158203.834 | 158203.834 | 161033.934 | 161033.934 | 161033.934 | 161033.934 | 161033.934 | 141001.802 | 141001.802 | 141001.802 | 141001.802 | 141001.802 | 141001.802 | 141001.802 | 134214.538 | 134214.538 | 134214.538 | 134214.538 | 134214.538 | 134214.538 |  | 830367.3182 | 830367.3182 | 830367.3182 | 830367.3182 | 830367.3182 | 830367.3182 | 830367.3182 | 830367.3182 | 830367.3182 | 629471.9993 | 0
|  |  |  | CM | SFMTA CM - 8004 | 812523.84 | [8 empty] | 65371.578 | 139356.612 | 137838.31 | 128765.196 | 126119.208 | 128765.196 | 126119.208 | 128765.196 | 124018.092 | 126033.994 | 124018.092 | 126033.994 | 130577.082 | 132592.984 | 130577.082 | 172767.964 | 173007.434 | 172767.964 | 173007.434 | 172767.964 | 173007.434 |  | 1069632.6818 | 1069632.6818 | 1069632.6818 | 1069632.6818 | 1069632.6818 | 1069632.6818 | 1069632.6818 | 1069632.6818 | 1069632.6818 | 810850.5813 | 0
[6 empty] | 1194888 | [8 empty] | 352471.85 | 297560.446 | 296042.144 | 289799.13 | 287153.142 | 289799.13 | 287153.142 | 289799.13 | 265019.894 | 267035.796 | 265019.894 | 267035.796 | 271578.884 | 273594.786 | 271578.884 | 306982.502 | 307221.972 | 306982.502 | 307221.972 | 306982.502 | 307221.972 |  | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1440322.5806 | 0
[5 empty] | Check | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | % of total to PM | 32% | [8 empty] | 81.45% | 53.17% | 53.44% | 55.57% | 56.08% | 55.57% | 56.08% | 55.57% | 53.2% | 52.8% | 53.2% | 52.8% | 51.92% | 51.54% | 51.92% | 43.72% | 43.69% | 43.72% | 43.69% | 43.72% | 43.69%
[6 empty] | ESTIMATE | 2013-07-01: SFMTA FORECAST |  | PROJECTED COST TO COMPLETE - BASED ON AVERAGE FORECAST DURING CONSTRUCTION PEAK
% to PM
68%
ESTIMATE
to CM
| SFMTA to complete - PM |  |  |  | 11686119.4755
| SFMTA to complete - CM |  |  |  | 14162346.5751
(excludes start up, safety & security)
| SFMTA to complete (excludes start up, safety & security) |  |  |  | 25848466.0506
Note on C10: JChin: MCE or MPM
Note on D10: JChin: Unit
Note on E10: JChin: Classification
Note on G10: JChin: Burdened daily rate
Note on C29: JChin: MCE or MPM
Note on D29: JChin: Unit
Note on E29: JChin: Classification
Note on G29: JChin: Burdened daily rate
Note on C56: JChin: MCE or MPM
Note on D56: JChin: Unit
Note on E56: JChin: Classification
Note on G56: JChin: Burdened daily rate
Note on C82: JChin: MCE or MPM
Note on D82: JChin: Unit
Note on E82: JChin: Classification
Note on G82: JChin: Burdened daily rate
Note on C108: JChin: MCE or MPM
Note on D108: JChin: Unit
Note on E108: JChin: Classification
Note on G108: JChin: Burdened daily rate
Note on C134: JChin: MCE or MPM
Note on D134: JChin: Unit
Note on E134: JChin: Classification
Note on G134: JChin: Burdened daily rate
Note on C160: JChin: MCE or MPM
Note on D160: JChin: Unit
Note on E160: JChin: Classification
Note on G160: JChin: Burdened daily rate
Note on C186: JChin: MCE or MPM
Note on D186: JChin: Unit
Note on E186: JChin: Classification
Note on G186: JChin: Burdened daily rate
Note on C212: JChin: MCE or MPM
Note on D212: JChin: Unit
Note on E212: JChin: Classification
Note on G212: JChin: Burdened daily rate
Note on C238: JChin: MCE or MPM
Note on D238: JChin: Unit
Note on E238: JChin: Classification
Note on G238: JChin: Burdened daily rate
Note on C264: JChin: MCE or MPM
Note on D264: JChin: Unit
Note on E264: JChin: Classification
Note on G264: JChin: Burdened daily rate
Note on C290: JChin: MCE or MPM
Note on D290: JChin: Unit
Note on E290: JChin: Classification
Note on G290: JChin: Burdened daily rate
Note on C316: JChin: MCE or MPM
Note on D316: JChin: Unit
Note on E316: JChin: Classification
Note on G316: JChin: Burdened daily rate
Note on C342: JChin: MCE or MPM
Note on D342: JChin: Unit
Note on E342: JChin: Classification
Note on G342: JChin: Burdened daily rate
Note on C368: JChin: MCE or MPM
Note on D368: JChin: Unit
Note on E368: JChin: Classification
Note on G368: JChin: Burdened daily rate
Note on C394: JChin: MCE or MPM
Note on D394: JChin: Unit
Note on E394: JChin: Classification
Note on G394: JChin: Burdened daily rate
Note on C420: JChin: MCE or MPM
Note on D420: JChin: Unit
Note on E420: JChin: Classification
Note on G420: JChin: Burdened daily rate
Note on C446: JChin: MCE or MPM
Note on D446: JChin: Unit
Note on E446: JChin: Classification
Note on G446: JChin: Burdened daily rate
Note on C472: JChin: MCE or MPM
Note on D472: JChin: Unit
Note on E472: JChin: Classification
Note on G472: JChin: Burdened daily rate
Note on C498: JChin: MCE or MPM
Note on D498: JChin: Unit
Note on E498: JChin: Classification
Note on G498: JChin: Burdened daily rate
Note on C524: JChin: MCE or MPM
Note on D524: JChin: Unit
Note on E524: JChin: Classification
Note on G524: JChin: Burdened daily rate
Note on C553: JChin: MCE or MPM
Note on D553: JChin: Unit
Note on E553: JChin: Classification
Note on G553: JChin: Burdened daily rate

## SFMTA
| M544.1 | Central Subway | [27 empty] | Approvals: | PM
| PM | Funghi, John O | [28 empty] | PE/RE
| PE | Hoe, Albert | [28 empty] | S/MGR
| RE | [29 empty] | MGR
[7 empty] | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 |  | Totals
| 2111.1 | Project Management
|  | MPM | R | 5508 | Funghi, John O | 2371.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144
|  | MPM | A | 5502 | Ames, Lewis T | 1513.326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144
|  | MPM | Q | 5211 | Nguyen, Roger Q | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40
|  | MPM | A | 5207 | Ng, Elisa | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32
|  | MPM | A | 5203 | Ancheta, Bernardino | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28
|  | MPM | B | 5201 | Chin, Tiffany | 997.688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72
|  | MPM | A | 1824 | Gallardo, Mario | 1324.238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
|  | MCE | S | 1844 | Haddad, Leila | 1034.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32
|  | MCE | S | 1842 | Katz, Jessie | 902.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
|  | MCE | R | 1426 | Nacion, Joery R | 692.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144
[5 empty] | Man Days Task | 2111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 668
PM |  |  |  |  | Dollars Task | 2111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113993.318 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 943521.752
[5 empty] | Man Days Div | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 668
[5 empty] | Dollars Div | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113993.318 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 943521.752
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 4; 2012-11-01: 4.2; 2012-12-01: 4.2; 2013-01-01: 4.2; 2013-02-01: 4.2; 2013-03-01: 4.2; 2013-04-01: 4.2; 2013-05-01: 4.2
| 2121.1 | Coordination
|  | MCE | R | 5241 | Hoe, Albert | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 102
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 19 | 19 | 25 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 197
CM |  |  |  |  | Dollars Task | 2121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55453.788 | 30524.028 | 30524.028 | 39014.328 | 39014.328 | 39014.328 | 39014.328 | 39014.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 311573.484
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 1.7; 2012-11-01: 0.95; 2012-12-01: 0.95; 2013-01-01: 1.25; 2013-02-01: 1.25; 2013-03-01: 1.25; 2013-04-01: 1.25; 2013-05-01: 1.25
| 2121.1 | Engineering Services - IRP
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
CM |  |  |  |  | Dollars Task | 2121.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 3515.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28124.352
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0.1; 2012-11-01: 0.1; 2012-12-01: 0.1; 2013-01-01: 0.1; 2013-02-01: 0.1; 2013-03-01: 0.1; 2013-04-01: 0.1; 2013-05-01: 0.1
| 2126.3 | Engineering Support - Overhead
|  | MCE | G | 5241 | Phang, Tee S | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
|  | MCE | G | 5241 | Leung, So-Man | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
|  | MCE | G | 5203 | David, Chris R | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2126.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19
CM |  |  |  |  | Dollars Task | 2126.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25332.194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25332.194
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0.95; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2126.5 | Engineering Services - Mechanical
|  | MCE | M | 5211 | Eng, Foo O | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
|  | MCE | M | 5241 | Huey, Lang A | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
|  | MCE | M | 5203 | Lee, Timothy C | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
|  | MCE | M | 5201 | Becker, John | 997.688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2126.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19
CM |  |  |  |  | Dollars Task | 2126.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23713.128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23713.128
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0.95; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2126.6 | Engineering Services - Electrical
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22
|  | MCE | N | 5241 | Leung, Frank W | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
|  | MCE | R | 5207 | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22
|  | MCE | N | 5207 | Green, Meghan V | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
CM |  |  |  |  | Dollars Task | 2126.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65092.3 | 5660.2 | 5660.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76412.7
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 2.3; 2012-11-01: 0.2; 2012-12-01: 0.2; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2127 | Final Design Cost Estimate
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
CM |  |  |  |  | Dollars Task | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2128 | Specifications & Calculations
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
CM |  |  |  |  | Dollars Task | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 2129 | Bid and Award
|  | MCE | R | 5241 | Hoe, Albert | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 42
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63
|  | MCE | R | 5207 | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63
|  | MCE | G | 5241 | Leung, So-Man | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 49
|  | MCE | M | 5241 | Huey, Lang A | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 49
|  | MCE | M | 5203 | Lee, Timothy C | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 2129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 343
CM |  |  |  |  | Dollars Task | 2129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72466.732 | 72466.732 | 72466.732 | 72466.732 | 72466.732 | 72466.732 | 72466.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 507267.124
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 0; 2012-11-01: 2.45; 2012-12-01: 2.45; 2013-01-01: 2.45; 2013-02-01: 2.45; 2013-03-01: 2.45; 2013-04-01: 2.45; 2013-05-01: 2.45
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 3131 | Construction Management (68A065)
|  | MCE | R | 5211 | Wong, Arthur G | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
|  | MCE | R | 6318 | Volberding, Ben | 1138.571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
|  | MPM | B | 5380 | Ciardi, Vincenzo | 588.412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 162
CM |  |  |  |  | Dollars Task | 3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62725.59 | 62725.59 | 62725.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 188176.77
[5 empty] | FTE's = (man days x 8)/160 |  | 2012-10-01: 2.7; 2012-11-01: 2.7; 2012-12-01: 2.7; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0
| 3111.1 | Project Management
|  | MPM | R | 5508 | Funghi, John O | 2371.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MPM | A | 5502 | Ames, Lewis T | 1513.326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MPM | Q | 5211 | Nguyen, Roger Q | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 65
|  | MPM | A | 5207 | Ng, Elisa | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 52
|  | MPM | A | 5203 | Ancheta, Bernardino | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MPM | B | 5201 | Chin, Tiffany | 997.688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 117
|  | MPM | A | 1824 | Gallardo, Mario | 1324.238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
|  | MCE | S | 1844 | Haddad, Leila | 1034.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28
|  | MCE | S | 1842 | Katz, Jessie | 902.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 26
|  | MCE | R | 1426 | Nacion, Joery R | 692.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MCE | R | 5241 | Hoe, albert | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 156
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 65
|  | MPM | S | 5504 | PM II MPMS | 1751.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MPM | S | 5504 | PM II MPMS | 1751.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MPM | S | 5506 | PM III MPMS | 2126.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
[5 empty] | Man Days Task | 3111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 151 | 151 | 151 | 151 | 151 | 151 | 145 | 145 | 145 | 145 | 145 | 145 |  | 1927
PM |  |  |  |  | Dollars Task | 3111.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242325.602 | 242325.602 | 242325.602 | 242325.602 | 242325.602 | 242325.602 | 242325.602 | 235538.338 | 235538.338 | 235538.338 | 235538.338 | 235538.338 | 235538.338 |  | 3109509.242
[5 empty] | FTE's = (man days x 8)/160 |  | 2013-06-01: 7.55; 2013-07-01: 7.55; 2013-08-01: 7.55; 2013-09-01: 7.55; 2013-10-01: 7.55; 2013-11-01: 7.55; 2013-12-01: 7.55; 2014-01-01: 7.25; 2014-02-01: 7.25; 2014-03-01: 7.25; 2014-04-01: 7.25; 2014-05-01: 7.25; 2014-06-01: 7.25
| 3121 | Design Support to Construction
|  | MCE | R | 5241 | Hoe, Albert | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | 78
|  | MCE | R | 5211 | Wang, Jane M | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 156
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
CM |  |  |  |  | Dollars Task | 3121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 | 30203.076 |  | 392639.988
[5 empty] | FTE's = (man days x 8)/160 |  | 2013-06-01: 0.9; 2013-07-01: 0.9; 2013-08-01: 0.9; 2013-09-01: 0.9; 2013-10-01: 0.9; 2013-11-01: 0.9; 2013-12-01: 0.9; 2014-01-01: 0.9; 2014-02-01: 0.9; 2014-03-01: 0.9; 2014-04-01: 0.9; 2014-05-01: 0.9; 2014-06-01: 0.9
| 3121.2 | Design Support to Construction - Mechanical
|  | MCE | M | 5211 | Eng, Foo O | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 |  | 7
|  | MCE | M | 5241 | Huey, Lang A | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 97
|  | MCE | M | 5203 | Lee, Timothy C | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 4 | 4 | 4 | 4 | 4 | 4 |  | 34
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3121.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 11 | 11 | 11 | 13 | 14 | 13 | 14 | 13 | 14 |  | 138
CM |  |  |  |  | Dollars Task | 3121.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8132.65 | 7502.564 | 8132.65 | 7502.564 | 14691.64 | 14061.554 | 14691.64 | 16316.926 | 18074.698 | 16316.926 | 18074.698 | 16316.926 | 18074.698 |  | 177890.134
[5 empty] | FTE's = (man days x 8)/160 |  | 2013-06-01: 0.3; 2013-07-01: 0.3; 2013-08-01: 0.3; 2013-09-01: 0.3; 2013-10-01: 0.55; 2013-11-01: 0.55; 2013-12-01: 0.55; 2014-01-01: 0.65; 2014-02-01: 0.7; 2014-03-01: 0.65; 2014-04-01: 0.7; 2014-05-01: 0.65; 2014-06-01: 0.7
| 3121.3 | Design Support to Construction - Electrical
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 3 | 3 | 3 | 3 | 3 | 3 |  | 81
|  | MCE | N | 5241 | Leung, Frank W | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MCE | R | 5207 | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 3 | 3 | 3 | 3 | 3 | 3 |  | 81
|  | MCE | N | 5207 | Green, Meghan V | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 26
|  | MCE | N | 5207 | Associate Engineer MCEN | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 |  | 36
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MCE | N | 5241 | Engineer MCEN | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 |  | 36
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3121.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 260
CM |  |  |  |  | Dollars Task | 3121.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 | 28094.496 |  | 365228.448
FTE's = (man days x 8)/160 | bar: 2013-06-01 to 2014-06-01
| 3121.4 | Design Support to Construction - Overhead
|  | MCE | G | 5241 | Phang, Tee S | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 |  | 31
|  | MCE | G | 5241 | Leung, So-Man | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | MCE | G | 5203 | David, Chris R | 1127.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 8 | 8 | 8 | 8 | 8 | 8 |  | 57
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3121.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 10 | 9 | 10 | 9 | 10 | 9 |  | 88
CM |  |  |  |  | Dollars Task | 3121.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2645.988 | 4164.29 | 2645.988 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 4164.29 | 1518.302 | 12058.092 | 10539.79 | 12058.092 | 10539.79 | 12058.092 | 10539.79 |  | 111345.464
[5 empty] | FTE's = (man days x 8)/160 | [9 empty] | 0.1 | 0.15 | 0.1 | 0.15 | 0.05 | 0.15 | 0.05 | 0.15 | 0.05 | 0.15 | 0.05 | 0.15 | 0.05 | 0.15 | 0.05 | 0.5 | 0.45 | 0.5 | 0.45 | 0.5 | 0.45
| 3126 | Contract Closeout
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 3126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | FTE's = (man days x 8)/160 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3128 | Construction Support for Project Closeout
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | FTE's = (man days x 8)/160 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3131 | Construction
| 3131 | Construction Management
|  | MCE | R | 5211 | Wong, Arthur G | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 324
|  | MCE | R | 6318 | Volberding, Ben | 1138.571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 324
|  | MCE | R | 5241 | Pong, Sanford C | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 |  | 72
|  | MCE | R | 5207 | Seng, Wuthea | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 12 | 12 | 12 | 12 | 12 | 12 |  | 93
|  | MCE | D | 5211 | Senior Engineer MCED | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MCE | D | 5207 | Associate Engineer MCED | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MCE | D | 5211 | Senior Engineer MCED | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MCE | D | 5207 | Associate Engineer MCED | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MCE | D | 5211 | Senior Engineer MCED | 1757.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MCE | D | 5207 | Associate Engineer MCED | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | 234
|  | MCE | D | 5241 | Engineer MCED | 1518.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 |  | 108
|  | MCE | D | 5207 | Associate Engineer MCED | 1311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | 18 | 18 | 18 |  | 108
|  |  |  | 6318 | Construct Inspector | 1138.571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 54 | 54 | 54 | 54 | 54 | 54 |  | 576
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 36 | 36 | 36 | 183 | 183 | 183 | 183 | 183 | 183 | 183 | 258 | 258 | 258 | 258 | 258 | 258 |  | 3009
CM |  |  |  |  | Dollars Task | 3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52134.174 | 52134.174 | 52134.174 | 52134.174 | 52134.174 | 262814.904 | 262814.904 | 262814.904 | 262814.904 | 262814.904 | 262814.904 | 262814.904 | 364276.788 | 364276.788 | 364276.788 | 364276.788 | 364276.788 | 364276.788 |  | 4286035.926
[5 empty] | FTE's = (man days x 8)/160 | [9 empty] | 0 | 0 | 0 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 9.15 | 9.15 | 9.15 | 9.15 | 9.15 | 9.15 | 9.15 | 12.9 | 12.9 | 12.9 | 12.9 | 12.9 | 12.9
| 1121.19 | Task
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 1121.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 1121.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 1121.2 | Task
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 1121.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 1121.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Div | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 131 | 130 | 115 | 113 | 115 | 113 | 115 | 379 | 381 | 379 | 381 | 384 | 386 | 384 | 464 | 464 | 464 | 464 | 464 | 464 |  | 6466
[5 empty] | Dollars Div | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238478.532 | 179056.384 | 177538.082 | 171295.068 | 168649.08 | 171295.068 | 168649.08 | 171295.068 | 573089.03 | 575104.932 | 573089.03 | 575104.932 | 579648.02 | 581663.922 | 579648.02 | 686487.716 | 686727.186 | 686487.716 | 686727.186 | 686487.716 | 686727.186 |  | 9603248.954
| 1131 | Task
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Task | 1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Task | 1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Div | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Dollars Div | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | Man Days Phase | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 215 | 214 | 199 | 197 | 199 | 197 | 199 | 379 | 381 | 379 | 381 | 384 | 386 | 384 | 464 | 464 | 464 | 464 | 464 | 464 |  | 7134
[5 empty] | Dollars Phase | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352471.85 | 297560.446 | 296042.144 | 289799.13 | 287153.142 | 289799.13 | 287153.142 | 289799.13 | 573089.03 | 575104.932 | 573089.03 | 575104.932 | 579648.02 | 581663.922 | 579648.02 | 686487.716 | 686727.186 | 686487.716 | 686727.186 | 686487.716 | 686727.186 |  | 10546770.706
[6 empty] | Total $ (all of the above) | [8 empty] | 352471.85 | 297560.446 | 296042.144 | 289799.13 | 287153.142 | 289799.13 | 287153.142 | 289799.13 | 573089.03 | 575104.932 | 573089.03 | 575104.932 | 579648.02 | 581663.922 | 579648.02 | 686487.716 | 686727.186 | 686487.716 | 686727.186 | 686487.716 | 686727.186 |  | 10546770.706
[22 empty] | Average $298,722 from October 2012 - May 2013 | Average $627,461 per month from June 2013 to June 2014
[5 empty] | SFMTA - remaining cost to complete | estimate June '12 to Sept '12, $298,722 x 4 months | [8 empty] | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above | as above |  | estimate Q3, Q4, 2014 | estimate Q1, Q2, 2015 | estimate Q3, Q4, 2015 | estimate Q1, Q2, 2016 | estimate Q3, Q4, 2016 | estimate Q1, Q2, 2017 | estimate Q3, Q4, 2017 | estimate Q1, Q2, 2018 | estimate Q3, Q4, 2018 | estimate Q1, Q2, 2019 | estimate Q3, Q4, 2019
[5 empty] | Original Staff plan SFMTA Total FTE's | [9 empty] | 10.82 | 10.82 | 10.82 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 10.8 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 |  | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 7.05 | 0
[5 empty] | Original Staff plan SFMTA Peak FTE's | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75806 | 0
[5 empty] | October 2012, SFMTA update Total FTE's | [9 empty] | 12.8 | 10.75 | 10.7 | 9.95 | 9.85 | 9.95 | 9.85 | 9.95 | 18.95 | 19.05 | 18.95 | 19.05 | 19.2 | 19.3 | 19.2 | 23.2 | 23.2 | 23.2 | 23.2 | 23.2 | 23.2
[5 empty] | October update % relative to original plan | [9 empty] | 118.3% | 99.35% | 98.89% | 92.13% | 91.2% | 92.13% | 91.2% | 92.13% | 175.5% | 176.4% | 175.5% | 176.4% | 177.8% | 178.7% | 177.8% | 249.5% | 249.5% | 249.5% | 249.5% | 249.5% | 249.5%
| SFMTA to complete (excludes start up, safety & security) |  |  |  | 51948416.9318 | 1194888 | [8 empty] | 352471.85 | 297560.446 | 296042.144 | 289799.13 | 287153.142 | 289799.13 | 287153.142 | 289799.13 | 573089.03 | 575104.932 | 573089.03 | 575104.932 | 579648.02 | 581663.922 | 579648.02 | 686487.716 | 686727.186 | 686487.716 | 686727.186 | 686487.716 | 686727.186 |  | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 3123500.2258 | 0
ALBERT HOE TO ADVISE/CONFIRM EXPECTED PEAK FTE'S AT 23, OR INCLUDE CONTINGENCY FOR ADDITIONAL DURING CONSTRUCTION
[5 empty] | ORIGINAL STAFF PLAN SFMTA PEAKS AT 35 FTE's | [30 empty] | average expenditure for 6 months, 686,727 x 6 = | 4120362
$16m spend to date
[37 empty] | allocate | 34.3% | of total to PM |  | allocate | 65.7% | to CM
|  |  |  | PM | SFMTA PM - 8003 | 382364.16 | [8 empty] | 113993.318 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 118504.062 | 242325.602 | 242325.602 | 242325.602 | 242325.602 | 242325.602 | 242325.602 | 242325.602 | 235538.338 | 235538.338 | 235538.338 | 235538.338 | 235538.338 | 235538.338 |  | 1413476.1362 | 1413476.1362 | 1413476.1362 | 1413476.1362 | 1413476.1362 | 1413476.1362 | 1413476.1362 | 1413476.1362 | 1413476.1362 | 1071506.1033 | 0
|  |  |  | CM | SFMTA CM - 8004 | 812523.84 | [8 empty] | 238478.532 | 179056.384 | 177538.082 | 171295.068 | 168649.08 | 171295.068 | 168649.08 | 171295.068 | 330763.428 | 332779.33 | 330763.428 | 332779.33 | 337322.418 | 339338.32 | 337322.418 | 450949.378 | 451188.848 | 450949.378 | 451188.848 | 450949.378 | 451188.848 |  | 2706885.8638 | 2706885.8638 | 2706885.8638 | 2706885.8638 | 2706885.8638 | 2706885.8638 | 2706885.8638 | 2706885.8638 | 2706885.8638 | 2051994.1225 | 0
[6 empty] | 1194888 | [8 empty] | 352471.85 | 297560.446 | 296042.144 | 289799.13 | 287153.142 | 289799.13 | 287153.142 | 289799.13 | 573089.03 | 575104.932 | 573089.03 | 575104.932 | 579648.02 | 581663.922 | 579648.02 | 686487.716 | 686727.186 | 686487.716 | 686727.186 | 686487.716 | 686727.186 |  | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 4120362 | 3123500.2258 | 0
[5 empty] | Check | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | % of total to PM | 32% | [8 empty] | 32.34% | 39.83% | 40.03% | 40.89% | 41.27% | 40.89% | 41.27% | 40.89% | 42.28% | 42.14% | 42.28% | 42.14% | 41.81% | 41.66% | 41.81% | 34.31% | 34.3% | 34.31% | 34.3% | 34.31% | 34.3%
[6 empty] | ESTIMATE | 2013-07-01: SFMTA FORECAST |  | PROJECTED COST TO COMPLETE - BASED ON AVERAGE FORECAST DURING CONSTRUCTION PEAK
% to PM
68%
ESTIMATE
to CM
| SFMTA to complete - PM |  |  |  | 18228186.4834
| SFMTA to complete - CM |  |  |  | 33720230.4484
(excludes start up, safety & security)
| SFMTA to complete (excludes start up, safety & security) |  |  |  | 51948416.9318
Note on C10: JChin: MCE or MPM
Note on D10: JChin: Unit
Note on E10: JChin: Classification
Note on G10: JChin: Burdened daily rate
Note on C29: JChin: MCE or MPM
Note on D29: JChin: Unit
Note on E29: JChin: Classification
Note on G29: JChin: Burdened daily rate
Note on C56: JChin: MCE or MPM
Note on D56: JChin: Unit
Note on E56: JChin: Classification
Note on G56: JChin: Burdened daily rate
Note on C82: JChin: MCE or MPM
Note on D82: JChin: Unit
Note on E82: JChin: Classification
Note on G82: JChin: Burdened daily rate
Note on C108: JChin: MCE or MPM
Note on D108: JChin: Unit
Note on E108: JChin: Classification
Note on G108: JChin: Burdened daily rate
Note on C134: JChin: MCE or MPM
Note on D134: JChin: Unit
Note on E134: JChin: Classification
Note on G134: JChin: Burdened daily rate
Note on C160: JChin: MCE or MPM
Note on D160: JChin: Unit
Note on E160: JChin: Classification
Note on G160: JChin: Burdened daily rate
Note on C186: JChin: MCE or MPM
Note on D186: JChin: Unit
Note on E186: JChin: Classification
Note on G186: JChin: Burdened daily rate
Note on C212: JChin: MCE or MPM
Note on D212: JChin: Unit
Note on E212: JChin: Classification
Note on G212: JChin: Burdened daily rate
Note on C238: JChin: MCE or MPM
Note on D238: JChin: Unit
Note on E238: JChin: Classification
Note on G238: JChin: Burdened daily rate
Note on C264: JChin: MCE or MPM
Note on D264: JChin: Unit
Note on E264: JChin: Classification
Note on G264: JChin: Burdened daily rate
Note on C290: JChin: MCE or MPM
Note on D290: JChin: Unit
Note on E290: JChin: Classification
Note on G290: JChin: Burdened daily rate
Note on C316: JChin: MCE or MPM
Note on D316: JChin: Unit
Note on E316: JChin: Classification
Note on G316: JChin: Burdened daily rate
Note on C342: JChin: MCE or MPM
Note on D342: JChin: Unit
Note on E342: JChin: Classification
Note on G342: JChin: Burdened daily rate
Note on C368: JChin: MCE or MPM
Note on D368: JChin: Unit
Note on E368: JChin: Classification
Note on G368: JChin: Burdened daily rate
Note on C394: JChin: MCE or MPM
Note on D394: JChin: Unit
Note on E394: JChin: Classification
Note on G394: JChin: Burdened daily rate
Note on C420: JChin: MCE or MPM
Note on D420: JChin: Unit
Note on E420: JChin: Classification
Note on G420: JChin: Burdened daily rate
Note on C446: JChin: MCE or MPM
Note on D446: JChin: Unit
Note on E446: JChin: Classification
Note on G446: JChin: Burdened daily rate
Note on C472: JChin: MCE or MPM
Note on D472: JChin: Unit
Note on E472: JChin: Classification
Note on G472: JChin: Burdened daily rate
Note on C498: JChin: MCE or MPM
Note on D498: JChin: Unit
Note on E498: JChin: Classification
Note on G498: JChin: Burdened daily rate
Note on C524: JChin: MCE or MPM
Note on D524: JChin: Unit
Note on E524: JChin: Classification
Note on G524: JChin: Burdened daily rate
Note on C553: JChin: MCE or MPM
Note on D553: JChin: Unit
Note on E553: JChin: Classification
Note on G553: JChin: Burdened daily rate

## Summary FTEs
160
|  | Project Group |  |  |  |  | 2010 | [11 empty] | Totals | 2011 | [11 empty] | Totals | 2012 | [11 empty] | Totals | 2013 | [11 empty] | Totals | 2014 | [11 empty] | Totals | 2015 | [11 empty] | Totals | 2016 | [11 empty] | Totals | 2017 | [11 empty] | Totals | 2018 | [11 empty] | Totals | 2019 | [11 empty] | Totals | Grand
| Position Number |  | Cross Walk# | Unit | Individual | Org | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2010 | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2011 | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2012 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2013 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2014 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2015 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2016 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2017 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2018 | 1Q19 | 2Q19 | 3Q19 | 4Q19 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2019 | Totals
|  | SFMTA - Management |  |  |  |  | 6.8 | 6.8 | 7.7 | 7.7 | 7.7 | 7.7 | 6.8 | 6.8 | 6.8 | 7.7 | 7.7 | 7.7 | 87.9 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 91.2 | 7.12 | 7.12 | 7.12 | 7.12 | 7.12 | 7.22 | 7.22 | 7.22 | 7.22 | 7.22 | 7.22 | 7.22 | 86.14 | 21.6 | 21.6 | 21.6 | 21.6 | [8 empty] | 86.4 | 18.6 | 18.6 | 18.6 | 18.6 | [8 empty] | 74.4 | 18.6 | 18.6 | 18.6 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.4 | 18.6 | 18.6 | 18.6 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.4 | 18.6 | 18.6 | 18.6 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.4 | 18.6 | 18.6 | 18.6 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.4 | 17.25 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.75 | 751.39
|  | SFMTA - Engineering |  |  |  |  | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 85.2 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 2.7 | 64.1 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 38.7 | 10.8 | 10.8 | 10.8 | 10.8 | [8 empty] | 43.2 | 9.3 | 9.3 | 9.3 | 9.3 | [8 empty] | 37.2 | 9.3 | 9.3 | 9.3 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2 | 9.3 | 9.3 | 9.3 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2 | 9.3 | 9.3 | 9.3 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2 | 9.3 | 9.3 | 9.3 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2 | 3.9 | 1.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 422.45
|  | SFMTA - Start-Up; Safety & Security; Other |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 10.5 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 18.6 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 23.4 | 3.35 | 3.35 | 3.35 | 3.35 | [8 empty] | 13.4 | 3.35 | 3.35 | 3.35 | 3.35 | [8 empty] | 13.4 | 2.85 | 2.85 | 2.85 | 2.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4 | 2.85 | 2.85 | 4.35 | 4.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4 | 8.65 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.15 | 72.9 | 82.9 | 82.9 | 82.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321.6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 478.85
|  | Subtotals - SFMTA |  |  |  |  | 13.9 | 13.9 | 14.8 | 14.8 | 14.8 | 16.3 | 15.4 | 15.4 | 15.4 | 16.3 | 16.3 | 16.3 | 183.6 | 17.35 | 17.35 | 17.35 | 17.35 | 17.35 | 12.55 | 12.55 | 12.55 | 12.55 | 12.55 | 12.55 | 11.85 | 173.9 | 11.77 | 11.77 | 11.77 | 11.77 | 11.77 | 12.77 | 12.77 | 12.77 | 12.77 | 12.77 | 12.77 | 12.77 | 148.24 | 35.75 | 35.75 | 35.75 | 35.75 | [8 empty] | 143 | 31.25 | 31.25 | 31.25 | 31.25 | [8 empty] | 125 | 30.75 | 30.75 | 30.75 | 30.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 30.75 | 30.75 | 32.25 | 32.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 36.55 | 40.4 | 40.4 | 40.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.75 | 100.8 | 110.8 | 110.8 | 110.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433.2 | 24.15 | 14.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1652.69
Group: Central Subway Partnership - Program Management/Construction Management
1 | O200.1 | Program Manager | 150 | 200 | Various | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | [11 empty] | 3 | [12 empty] | 0 | [12 empty] | 0 | 87
3 | O320.37b | Project Controls Manager | 150 | 320 | J Burns | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 12
4 | O431.35e | Risk/Configuration Manager | 305 | 431 | Various | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | [11 empty] | 3 | [12 empty] | 0 | [12 empty] | 0 | 87
5 | O432.40 | Outreach Manager | 305 | 432 | B Norris | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | [11 empty] | 3 | [12 empty] | 0 | [12 empty] | 0 | 87
6 | O420.25 | Q/A Manager |  |  | M Latch | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | [11 empty] | 3 | [12 empty] | 0 | [12 empty] | 0 | 87
|  | Design Oversight Managers |  |  | Various | PM/CM | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 24.6 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 24.6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 49.2
|  | Regulatory/Interagency Manager |  |  | G Hollins | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 48
|  | Document Control Manager |  |  | S MacKenzie | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | [11 empty] | 3 | [12 empty] | 0 | [12 empty] | 0 | 87
|  | Program Management Staff |  |  | Various | PM/CM | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 181.44 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 201.444 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 201.444 | 50.361 | 50.361 | 50.361 | 50.361 | [8 empty] | 201.444 | 39.3 | 39.3 | 39.3 | 39.3 | [8 empty] | 157.2 | 39.3 | 39.3 | 39.3 | 39.3 | [8 empty] | 157.2 | 39.3 | 39.3 | 39.3 | 39.3 | [8 empty] | 157.2 | 39.3 | [11 empty] | 39.3 | [12 empty] | 0 | [12 empty] | 0 | 1296.672 | 1840.872 | 1135 | 705.872
[19 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Construction Manager |  |  | TBD | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | [11 empty] | 3 | [12 empty] | 0 | [12 empty] | 0 | 87
|  | Safety |  |  | TBD | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | [11 empty] | 3 | [12 empty] | 0 | [12 empty] | 0 | 87
|  | CM Staff |  |  | Various | PM/CM | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 13.404 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 30.684 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 30.684 | 7.671 | 7.671 | 7.671 | 7.671 | [8 empty] | 30.684 | 6.77 | 6.77 | 6.77 | 6.77 | [8 empty] | 27.08 | 6.77 | 6.77 | 6.77 | 6.77 | [8 empty] | 27.08 | 6.77 | 6.77 | 6.77 | 6.77 | [8 empty] | 27.08 | 6.77 | [11 empty] | 6.77 | [12 empty] | 0 | [12 empty] | 0 | 193.466
|  | Mat'l Testing |  |  | Various | PM/CM | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 25.32 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 25.32 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 25.32 | 6.33 | 6.33 | 6.33 | 6.33 | [8 empty] | 25.32 | 4.05 | 4.05 | 4.05 | 4.05 | [8 empty] | 16.2 | 4.05 | 4.05 | 4.05 | 4.05 | [8 empty] | 16.2 | 4.05 | 4.05 | 4.05 | 4.05 | [8 empty] | 16.2 | 4.05 | [11 empty] | 4.05 | [12 empty] | 0 | [12 empty] | 0 | 153.93
|  | Utility CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 12
|  | Utility Staff |  |  | Various | PM/CM | [12 empty] | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 6
|  | Tunnel CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [6 empty] | 1 | 1 | 1 | 2 | 2 | 2 | 9 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 3 | [10 empty] | 9 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 66
|  | Tunnel Staff |  |  | Various | PM/CM | [12 empty] | 0 | [9 empty] | 6.39 | 6.39 | 6.39 | 19.17 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 76.68 | 19.17 | 19.17 | 19.17 | 19.17 | [8 empty] | 76.68 | 19.17 | 19.17 | [10 empty] | 38.34 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 210.87
|  | UMS CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [9 empty] | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | [9 empty] | 18 | [12 empty] | 0 | [12 empty] | 0 | 120
|  | UMS Staff |  |  | Various | PM/CM | [12 empty] | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | [9 empty] | 3.36 | 3.36 | 3.36 | 10.08 | 10.08 | 10.08 | 10.08 | 10.08 | [8 empty] | 40.32 | 10.08 | 10.08 | 10.08 | 10.08 | [8 empty] | 40.32 | 10.08 | 10.1 | 10.1 | 10.1 | [8 empty] | 40.38 | 10.1 | 10.1 | 10.1 | 10.1 | [8 empty] | 40.4 | 10.1 | 10.1 | 10.1 | [9 empty] | 30.3 | [12 empty] | 0 | [12 empty] | 0 | 207.8
|  | CTS CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [9 empty] | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | [9 empty] | 18 | [12 empty] | 0 | [12 empty] | 0 | 120
7 | O420.26 | CTS Staff |  |  | Various | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [9 empty] | 3.96 | 3.96 | 3.96 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | [8 empty] | 47.52 | 11.88 | 11.88 | 11.88 | 11.88 | [8 empty] | 47.52 | 11.88 | 10.1 | 10.1 | 10.1 | [8 empty] | 42.18 | 10.1 | 10.1 | 10.1 | 10.1 | [8 empty] | 40.4 | 10.1 | 10.1 | 10.1 | [9 empty] | 30.3 | [12 empty] | 0 | [12 empty] | 0 | 219.8
8 | O420.27c | MOS CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [9 empty] | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | [9 empty] | 18 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 96
9 | O320.36d | MOS Staff |  |  | Various | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [9 empty] | 3.56 | 3.56 | 3.56 | 10.68 | 10.68 | 10.68 | 10.68 | 10.68 | [8 empty] | 42.72 | 10.68 | 10.68 | 10.68 | 10.68 | [8 empty] | 42.72 | 10.68 | 11.88 | 11.88 | 11.88 | [8 empty] | 46.32 | 11.88 | 11.88 | 11.88 | [9 empty] | 35.64 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 178.08
|  | STS CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | [12 empty] | 0 | [12 empty] | 0 | 60
|  | STS Staff |  |  | Various | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 9.2 | 9.2 | [8 empty] | 24.4 | 9.2 | 9.2 | 9.2 | 9.2 | [8 empty] | 36.8 | 9.2 | 9.2 | 9.2 | 9.2 | [8 empty] | 36.8 | [12 empty] | 0 | [12 empty] | 0 | 122
|  | Start-Up, Testing and Commissioning |  |  | Various | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 8.2 | 8.2 | [8 empty] | 16.4 | 9 | 9 | 13.75 | [9 empty] | 31.75 | [12 empty] | 0 | 48.15 | 1988.096 | 1170 | 818.096
[19 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
10 | O320.37a | [17 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Central Subway Partnership - Program Management/Construction Management (PMCM) Consultant |  |  |  |  | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 352.764 | 33.504 | 33.504 | 33.504 | 33.504 | 33.504 | 33.504 | 34.504 | 34.504 | 34.504 | 41.894 | 41.894 | 41.894 | 430.218 | 37.844 | 37.844 | 37.844 | 37.844 | 37.844 | 38.537 | 38.537 | 38.537 | 38.537 | 38.537 | 39.147 | 39.147 | 460.199 | 115.441 | 178.081 | 184.081 | 184.081 | [8 empty] | 661.684 | 168.99 | 168.99 | 150.99 | 150.99 | [8 empty] | 639.96 | 149.49 | 145.93 | 146.13 | 143.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584.68 | 134.13 | 131.13 | 82.83 | 82.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430.92 | 82.83 | 72.9 | 72.1 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292.83 | 49.7 | 40.5 | 33.25 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3993.205
|  | Hill International - Program Controls Consultant (PCC) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.31 | 5.31 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 180.36 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 146.76 | 34.08 | 34.08 | 34.08 | 34.08 | 368.69 | [7 empty] | 136.32 | 34.21 | 34.21 | 34.21 | 34.21 | 273.16 | [7 empty] | 136.84 | 34.21 | 34.21 | 34.21 | 34.21 | 273.68 | [7 empty] | 136.84 | 34.21 | 34.21 | 34.21 | 34.21 | 273.68 | [7 empty] | 136.84 | 34.21 | 34.21 | 34.21 | 34.21 | 273.68 | [7 empty] | 136.84 | 12.78 | 12.78 | 12.78 | 12.78 | 187.96 | [7 empty] | 51.12 | 0 | 0 | 0 | 0 | 51.12 | [7 empty] | 0 | 1067.23
Group: PB Telamon - Final Design for Utility Relocations and Tunnel (DP1)
1 | O200.1 | Project Managers | 150 | 200 | Various | DP1 | 0.0285 | 0.0285 | 0.057 | 0.057 | 0.114 | 0.171 | 0.171 | 0.171 | 0.171 | 0.171 | 0.171 | 0.171 | 1.482 | 0.171 | 0.171 | 0.171 | 0.1425 | 0.1425 | 0.1425 | 0.1425 | 0.1425 | 0.1425 | 0.057 | 0.057 | 0.057 | 1.539 | 0.049875 | 0.049875 | 0.035625 | 0.0285 | 0.0285 | 0.0285 | 0.0285 | 0.0285 | 0.0285 | 0.0285 | 0.0285 | 0.0285 | 0.39187 | 0.021375 | 0.021375 | 0.021375 | 0.021375 | [8 empty] | 0.0855 | 0.021375 | 0.021375 | 0.021375 | 0 | [8 empty] | 0.064125 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 3.5625
2 | O320.37a | Project Controls and Admin | 150 | 320 | Various | DP1 | 0.1413 | 0.1413 | 0.2826 | 0.2826 | 0.5652 | 0.8478 | 0.8478 | 0.8478 | 0.8478 | 0.8478 | 0.8478 | 0.8478 | 7.3476 | 0.8478 | 0.8478 | 0.8478 | 0.7065 | 0.7065 | 0.7065 | 0.7065 | 0.7065 | 0.7065 | 0.2826 | 0.2826 | 0.2826 | 7.6302 | 0.24728 | 0.24728 | 0.17663 | 0.1413 | 0.1413 | 0.1413 | 0.1413 | 0.1413 | 0.1413 | 0.1413 | 0.1413 | 0.1413 | 1.9429 | 0.10598 | 0.10598 | 0.10598 | 0.10598 | [8 empty] | 0.4239 | 0.10598 | 0.10598 | 0.10598 | 0 | [8 empty] | 0.31793 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 17.6625
3 | O320.37b | Geo-Engineers | 150 | 320 | Various | DP1 | 0.0015 | 0.0015 | 0.003 | 0.003 | 0.006 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.078 | 0.009 | 0.009 | 0.009 | 0.0075 | 0.0075 | 0.0075 | 0.0075 | 0.0075 | 0.0075 | 0.003 | 0.003 | 0.003 | 0.081 | 0.002625 | 0.002625 | 0.001875 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.0015 | 0.020625 | 0.001125 | 0.001125 | 0.001125 | 0.001125 | [8 empty] | 0.0045 | 0.001125 | 0.001125 | 0.001125 | 0 | [8 empty] | 0.003375 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0.1875
4 | O431.35e | Civil Engineers | 305 | 431 | Various | DP1 | 0.0125 | 0.0125 | 0.025 | 0.025 | 0.05 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.65 | 0.075 | 0.075 | 0.075 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.0625 | 0.025 | 0.025 | 0.025 | 0.675 | 0.021875 | 0.021875 | 0.015625 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.0125 | 0.17188 | 0.009375 | 0.009375 | 0.009375 | 0.009375 | [8 empty] | 0.0375 | 0.009375 | 0.009375 | 0.009375 | 0 | [8 empty] | 0.028125 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1.5625
5 | O432.40 | Structural Engineers | 305 | 432 | Various | DP1 | 0.0005 | 0.0005 | 0.001 | 0.001 | 0.002 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.026 | 0.003 | 0.003 | 0.003 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.001 | 0.001 | 0.001 | 0.027 | 0.000875 | 0.000875 | 0.000625 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.0005 | 0.006875 | 0.000375 | 0.000375 | 0.000375 | 0.000375 | [8 empty] | 0.0015 | 0.000375 | 0.000375 | 0.000375 | 0 | [8 empty] | 0.001125 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0.0625
6 | O420.25 |  |  |  |  | DP1 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 1.8 | 1.8 | 1.8 | [8 empty] | 5.4 | 4 | 6 | 8 | 10 | [8 empty] | 28 | 10 | 10 | 5 | [9 empty] | 25 | 58.4
7 | O420.26 |  |  |  |  | DP1 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 1.8 | 1.8 | 1.8 | [8 empty] | 5.4 | 4 | 6 | 8 | 10 | [8 empty] | 28 | 10 | 10 | 5 | [9 empty] | 25 | 58.4
8 | O420.27c |  |  |  |  | DP1 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 2 | 0.5 | 0.5 | 0.75 | 0.75 | [8 empty] | 2.5 | 0.75 | 0.5 | 0.25 | [9 empty] | 1.5 | 6
9 | O320.36d |  |  |  |  | DP1 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0.25 | 0.25 | 0.25 | [8 empty] | 0.75 | 0.5 | 0.5 | 0.75 | 0.75 | [8 empty] | 2.5 | 0.75 | 0.75 | 0.5 | 0.5 | [8 empty] | 2.5 | 5.75
10 | O320.37a |  |  |  |  | DP1 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 1 | 1 | 1 | 1 | [8 empty] | 4 | 1 | 1 | [10 empty] | 2 | 6
|  | PB Telamon - Final Design for Utility Relocations and Tunnel (DP1) |  |  |  |  | 5.6493 | 6.9324 | 10.5211 | 12.1218 | 14.3491 | 13.7782 | 12.3663 | 14.9526 | 15.849 | 14.0429 | 11.9291 | 11.2279 | 143.7199 | 8.1016 | 3.6164 | 3.0364 | 2.7813 | 7.2015 | 3.0343 | 2.649 | 2.5303 | 2.7296 | 2.0485 | 1.985 | 1.152 | 40.8659 | 1.3472 | 1.3355 | 1.2569 | 2.1771 | 3.5154 | 1.6824 | 1.9534 | 1.7564 | 1.7271 | 1.7271 | 1.7229 | 1.774 | 21.9754 | 3.9132 | 3.58 | 3.3712 | 3.3712 | [8 empty] | 14.2357 | 1.1988 | 1.1988 | 1.1988 | 0 | [8 empty] | 3.5963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224.3931
Group: CSDG - Final Design for Stations (DP2)
1 | O200.1 | Principal in Charge | 150 | 200 | R Hornbuckle | DP2 |  |  |  | 0.06 | 0.126 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 3
2 | O320.37a | Project Manager | 150 | 320 | N Munfah | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 14.0507
3 | O320.37b | Deputy Project Manager | 150 | 320 | A Read | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 14.0507
4 | O431.35e | Package Manager - UMS | 305 | 431 |  | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 14.0507
5 | O432.40 | Package Manager - CTS | 305 | 432 |  | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 14.0507
6 | O420.25 | Package Manager - MOS |  |  |  | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 14.0507
|  | Manager/Sr Specialist |  |  | Various | DP2 |  |  |  | 1.5838 | 3.3259 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 0 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 79.1853
|  | Senior Technical |  |  | Various | DP2 |  |  |  | 7.6935 | 16.1564 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 0 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 384.6747
|  | Staff Technical |  |  | Various | DP2 |  |  |  | 5.8188 | 12.2194 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 0 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 290.9374
|  | Technician |  |  | Various | DP2 |  |  |  | 4.492 | 9.4332 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 0 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 224.6
|  | Support Staff |  |  | Various | DP2 |  |  |  | 0.4595 | 0.965 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 0 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 22.9747
|  | Trainee |  |  | Various | DP2 |  |  |  | 2.31 | 4.851 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 0 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 115.5
7 | O420.26 | Support During Construction |  |  | Various | DP2 | [12 empty] | 0 | [10 empty] | 1.125 | 1.125 | 0 | 1.125 | 1.125 | 1.125 | 1.125 | 7.7813 | 7.7813 | 7.7813 | 7.7813 | 6.6563 | 6.6563 | 11.0938 | 11.0938 | 0 | 25.8856 | 22.187 | 19.9689 | 19.9689 | [8 empty] | 0 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | [8 empty] | 0 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | [8 empty] | 0 | 19.9689 | 19.9689 | 19.9689 | [9 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 381.0437
8 | O420.27c | [17 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
9 | O320.36d | [17 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
10 | O320.37a | [17 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Central Subway Design Group (CSDG) - Final Design for Stations (DP2) |  |  |  |  | 0 | 0 | 0 | 23.8226 | 50.0274 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 632.4878 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 0 | 0 | 0 | 1.125 | 1.125 | 560.8878 | 1.125 | 1.125 | 1.125 | 1.125 | 7.7813 | 7.7813 | 7.7813 | 7.7813 | 6.6563 | 6.6563 | 11.0938 | 11.0938 | 71.1254 | 25.8856 | 22.187 | 21 | 21 | [8 empty] | 90.0726 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | [8 empty] | 79.8756 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.8756 | 19.9689 | 19.9689 | 19.9689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.9067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Group: HNTB-B&C Transit - Final Design for Surface, Trackway & Systems (DP3)
1 | O200.1 | Project Managers | 150 | 200 | Various | DP3 |  |  |  |  | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 1.1995 | 1.1995 | 1.1995 | 0 | 1.1995 | 1.1995 | 1.1995 | 1.1995 | 1.1995 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | [8 empty] | 0 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | [8 empty] | 0 | 1.129 | 1.129 | 1.129 | 1.129 | [8 empty] | 0 | 1.129 | 1.129 | 1.129 | 1.129 | [8 empty] | 0 | 1.129 | 1.129 | 1.129 | 1.129 | [8 empty] | 0 | 0.6175 | 0.6175 | 0.6175 | 0.6175 | [8 empty] | 0 | [12 empty] | 0 | 44.8068
2 | O320.37a | Integration Coord & Quality Control | 150 | 320 | Various | DP3 |  |  |  |  | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 2.2409 | 2.2409 | 2.2409 | 0 | 2.2409 | 2.2409 | 2.2409 | 2.2409 | 2.2409 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 0 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 0 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [8 empty] | 0 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [8 empty] | 0 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [8 empty] | 0 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [8 empty] | 0 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 67.2276
3 | O320.37b | Project Controls & Admin | 150 | 320 | Various | DP3 |  |  |  |  | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 2.4049 | 2.4049 | 2.4049 | 0 | 2.4049 | 2.4049 | 2.4049 | 2.4049 | 2.4049 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 0 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 0 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | [8 empty] | 0 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | [8 empty] | 0 | 2.1101 | 2.1101 | 2.1101 | 2.1101 | [8 empty] | 0 | 2.1101 | 2.1101 | 2.1101 | 2.1101 | [8 empty] | 0 | 2.1101 | 2.1101 | 2.1101 | 2.1101 | [8 empty] | 0 | 1.0589 | 1.0589 | 1.0589 | 1.0589 | [8 empty] | 0 | [12 empty] | 0 | 87.2754
4 | O431.35e | Civil/Track & Utilities | 305 | 431 | Various | DP3 |  |  |  |  | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 1.6241 | 1.6241 | 1.6241 | 0 | 1.6241 | 1.6241 | 1.6241 | 1.6241 | 1.6241 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [8 empty] | 0 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [8 empty] | 0 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [8 empty] | 0 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [8 empty] | 0 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 48.7226
5 | O432.40 | Structural | 305 | 432 | Various | DP3 |  |  |  |  | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.22238 | 0.22238 | 0.22238 | 0 | 0.22238 | 0.22238 | 0.22238 | 0.22238 | 0.22238 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [8 empty] | 0 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [8 empty] | 0 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [8 empty] | 0 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [8 empty] | 0 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 6.6714
6 | O420.25 | Environmental and Sustainability | 275 | 420 | Various | DP3 |  |  |  |  | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.24754 | 0.24754 | 0.24754 | 0 | 0.24754 | 0.24754 | 0.24754 | 0.24754 | 0.24754 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [8 empty] | 0 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [8 empty] | 0 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [8 empty] | 0 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [8 empty] | 0 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 7.4261
7 | O420.26 | Controls & Comms | 275 | 420 | Various | DP3 |  |  |  |  | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.95694 | 0.95694 | 0.95694 | 0 | 0.95694 | 0.95694 | 0.95694 | 0.95694 | 0.95694 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [8 empty] | 0 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [8 empty] | 0 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [8 empty] | 0 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [8 empty] | 0 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 28.7083
8 | O420.27c | Train Control |  |  | Various | DP3 |  |  |  |  | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.96902 | 0.96902 | 0.96902 | 0 | 0.96902 | 0.96902 | 0.96902 | 0.96902 | 0.96902 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [8 empty] | 0 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [8 empty] | 0 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [8 empty] | 0 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [8 empty] | 0 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 29.0706
9 | O320.36d | OCS |  |  | Various | DP3 |  |  |  |  | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.69129 | 0.69129 | 0.69129 | 0 | 0.69129 | 0.69129 | 0.69129 | 0.69129 | 0.69129 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [8 empty] | 0 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [8 empty] | 0 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [8 empty] | 0 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [8 empty] | 0 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 20.7388
10 | O320.37a | Corrosion Control |  |  | Various | DP3 |  |  |  |  | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.065406 | 0.065406 | 0.065406 | 0 | 0.065406 | 0.065406 | 0.065406 | 0.065406 | 0.065406 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [8 empty] | 0 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [8 empty] | 0 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [8 empty] | 0 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [8 empty] | 0 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 1.9622
11 | O320.37b | Fare Collection | 150 | 320 | Various | DP3 |  |  |  |  | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.04025 | 0.04025 | 0.04025 | 0 | 0.04025 | 0.04025 | 0.04025 | 0.04025 | 0.04025 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [8 empty] | 0 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [8 empty] | 0 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [8 empty] | 0 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [8 empty] | 0 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 1.2075
12 | O431.35e | Systems Safety | 305 | 431 | Various | DP3 |  |  |  |  | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.36024 | 0.36024 | 0.36024 | 0 | 0.36024 | 0.36024 | 0.36024 | 0.36024 | 0.36024 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [8 empty] | 0 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [8 empty] | 0 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [8 empty] | 0 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [8 empty] | 0 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 10.8071
13 | O432.40 | Elect/Mech | 305 | 432 | Various | DP3 |  |  |  |  | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.69934 | 0.69934 | 0.69934 | 0 | 0.69934 | 0.69934 | 0.69934 | 0.69934 | 0.69934 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [8 empty] | 0 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [8 empty] | 0 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [8 empty] | 0 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [8 empty] | 0 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 20.9803
14 | O420.25 | CADD | 275 | 420 | Various | DP3 |  |  |  |  | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 1.1139 | 1.1139 | 1.1139 | 0 | 1.1139 | 1.1139 | 1.1139 | 1.1139 | 1.1139 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [8 empty] | 0 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [8 empty] | 0 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [8 empty] | 0 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [8 empty] | 0 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 33.4172
15 | O420.26 | Architectural | 275 | 420 | Various | DP3 |  |  |  |  | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.028175 | 0.028175 | 0.028175 | 0 | 0.028175 | 0.028175 | 0.028175 | 0.028175 | 0.028175 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [8 empty] | 0 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [8 empty] | 0 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [8 empty] | 0 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [8 empty] | 0 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 0.84525
16 | O420.27c | Traffic |  |  | Various | DP3 |  |  |  |  | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.020125 | 0.020125 | 0.020125 | 0 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [8 empty] | 0 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [8 empty] | 0 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [8 empty] | 0 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [8 empty] | 0 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 0.60375
|  | HNTB-B&C Transit - Final Design for Surface, Trackway & Systems (DP3) |  |  |  |  | 0 | 0 | 0 | 0 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 17.1358 | 17.1358 | 17.1358 | 94.247 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 145.6545 | 8.5679 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 79.4303 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | [8 empty] | 45.8673 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | [8 empty] | 45.8673 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.0982 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.0982 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.0982 | 2.984 | 2.984 | 2.984 | 2.984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591.2971
Group: Department of Public Works (DPW)
|  | BOE Coordination |  |  | Lesley Wong | EHY | 0.53 | 0.56 | 0.56 | 1.11 | 1.15 | 1.23 | 1.3 | 1.22 | 1.01 | 0.98 | 0.98 | 0.77 | 11.4 | 0.68 | 0.67 | 0.77 | 0.77 | 0.77 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 9.75 | 0.55 | 0.36 | 0.36 | 0.22 | 0.47 | 0.35 | 0.35 | 0.49 | 0.49 | 0.56 | 0.56 | 0.56 | 5.32 | 0.5544 | 0.5544 | 0.5544 | 0.5214 | [8 empty] | 2.1846 | 0.5214 | 0.5148 | 0.4554 | 0.4554 | [8 empty] | 1.947 | 0.4554 | 0.4554 | 0.4554 | 0.4554 | [8 empty] | 1.8216 | 0.4554 | 0.4554 | 0.1881 | 0.0693 | [8 empty] | 1.1682 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 33.5914
|  | Sewer Design & Hydraulic Studies |  |  | Yuan Wu | EHY | 0.28 | 0.2 | 0.1 | 0.25 | 0.18 | 0.38 | 0.3 | 0.22 | 0.22 | 0.2 | 0.2 | 0.2 | 2.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 2.73
|  | Sewer Design |  |  | Kevin Day | EHY | 0.93 | 0.91 | 0.83 | 1.06 | 1.08 | 1.24 | 1.19 | 1.2 | 0.57 | 0.52 | 0.57 | 0.32 | 10.42 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 7.27 | 0.38 | 0.25 | 0.25 | 0.21 | 0.23 | 0.23 | 0.03 | 0.04 | 0.04 | 0.06 | 0.06 | 0.06 | 1.84 | 0.0594 | 0.0594 | 0.0594 | 0.0594 | [8 empty] | 0.2376 | 0.0594 | 0.0528 | 0.0495 | 0.0495 | [8 empty] | 0.2112 | 0.0495 | 0.0495 | 0.0495 | 0.0495 | [8 empty] | 0.198 | 0.0495 | 0.0429 | 0.0297 | 0.0198 | [8 empty] | 0.1419 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 20.3187
|  | Sewer Design |  |  | Cheung/Fong/Helmuth/Others | EHY | 0.33 | 0.33 | 0.51 | 0.7 | 0.67 | 0.66 | 0.82 | 0.89 | 0.46 | 0.52 | 0.48 | 0.24 | 6.61 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 4.08 | 0.18 | 0.18 | 0.18 | 0.16 | 0.16 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1.02 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 11.71
|  | AWSS Design |  |  | Mike Smith | EME | 0.32 | 0.26 | 0.26 | 0.59 | 0.59 | 0.67 | 0.59 | 0.65 | 0.39 | 0.39 | 0.39 | 0.34 | 5.44 | 0.34 | 0.35 | 0.35 | 0.35 | 0.35 | 0.36 | 0.35 | 0.35 | 0.36 | 0.35 | 0.35 | 0.35 | 4.21 | 0.22 | 0.15 | 0.15 | 0.08 | 0.11 | 0.04 | 0.04 | 0.06 | 0.06 | 0.08 | 0.08 | 0.09 | 1.16 | 0.0792 | 0.0792 | 0.0792 | 0.0792 | [8 empty] | 0.3168 | 0.0792 | 0.0792 | 0.0693 | 0.0693 | [8 empty] | 0.297 | 0.0693 | 0.0693 | 0.0693 | 0.0693 | [8 empty] | 0.2772 | 0.0693 | 0.0693 | 0.0396 | 0.0198 | [8 empty] | 0.198 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 11.899
|  | AWSS Design |  |  | Lee/Wong/Others | EME | 0.09 | 0.09 | 0.09 | 0.23 | 0.17 | 0.23 | 0.31 | 0.39 | 0.27 | 0.6 | 0.4 | 0.2 | 3.07 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 2.52 | 0.12 | 0.12 | 0.12 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 6.05
|  | Roadway Renovation Design |  |  | Steve O'Sullivan | ESH | 1.25 | 1.25 | 1.15 | 1.61 | 1.51 | 1.71 | 1.7 | 1.7 | 1.33 | 1.3 | 1.3 | 0.8 | 16.61 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 | 10.78 | 0.75 | 0.55 | 0.55 | 0.35 | 0.43 | 0.18 | 0.18 | 0.24 | 0.24 | 0.31 | 0.31 | 0.31 | 4.4 | 0.3069 | 0.3069 | 0.3069 | 0.3069 | [8 empty] | 1.2276 | 0.3069 | 0.2904 | 0.2079 | 0.2079 | [8 empty] | 1.0131 | 0.2079 | 0.2079 | 0.2079 | 0.2079 | [8 empty] | 0.8316 | 0.2079 | 0.2079 | 0.0891 | 0.0693 | [8 empty] | 0.5742 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 35.4365
|  | Roadway Renovation Design |  |  | Yu/Hernandez/Others | ESH | 0.23 | 0.15 | 0.55 | 0.62 | 0.62 | 0.82 | 1.01 | 0.96 | 0.71 | 0.71 | 0.71 | 0.46 | 7.55 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 5.52 | 0.31 | 0.31 | 0.31 | 0.23 | 0.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 14.46
|  | Structural Sewer Design |  |  | Joseph Elek | EST | 0.08 | 0 | 0 | 0.08 | 0 | 0.32 | 0.25 | 0.25 | 0.2 | 0.23 | 0.25 | 0.25 | 1.91 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 2.04 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.88 | 0.0099 | 0.0099 | 0.0099 | 0.0099 | [8 empty] | 0.0396 | 0.0099 | 0.0099 | 0.0099 | 0.0099 | [8 empty] | 0.0396 | 0.0099 | 0.0099 | 0.0099 | 0.0099 | [8 empty] | 0.0396 | 0.0099 | 0.0099 | 0.0099 | 0.0099 | [8 empty] | 0.0396 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 4.9884
|  | Structural Sewer Design |  |  | Others | EST | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 0.07 | 0.15 | 0.15 | 0.15 | 0.15 | 0.74 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 1.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 3.29
|  | Specs/Site Ass'm't & Remediation |  |  | Carmen Ynami | BCM/ | 0.35 | 0.37 | 0.37 | 0.51 | 0.5 | 0.55 | 0.55 | 0.58 | 0.53 | 0.53 | 0.53 | 0.43 | 5.8 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 1.34 | 1.34 | 1.34 | 1.35 | 1.35 | 1.35 | 1.35 | 13.02 | 1.25 | 0.7 | 0.7 | 0.66 | 1.62 | 1.58 | 1.58 | 2.12 | 2.12 | 2.27 | 2.27 | 2.27 | 19.14 | 2.1714 | 2.1714 | 2.1714 | 2.1714 | [8 empty] | 8.6856 | 2.1714 | 2.1714 | 1.6335 | 1.6335 | [8 empty] | 7.6098 | 1.6335 | 1.6335 | 1.6335 | 1.6335 | [8 empty] | 6.534 | 1.6335 | 1.6335 | 0.6633 | 0.1485 | [8 empty] | 4.0788 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 64.8682
|  | Specs/Site Ass'm't & Remediation |  |  | Others | BCM | 0.12 | 0.12 | 0.12 | 0.2 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.11 | 1.51 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 1.67
|  | Force Main Design |  |  | Elliot Szkup | EME | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.35 | 0.35 | 0.35 | 0.35 | 0.44 | 0.05 | 2.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.67 | 0.06 | 0.06 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.02 | 0.01 | 0.01 | 0.02 | 0.3 | 0.0066 | 0 | 0 | 0 | [8 empty] | 0.0066 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 3.0166
|  | PUC Sewer Operations (TV Tape) |  |  | Others | PUC | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.4 | 0.3 | 0.4 | 0.5 |  | 2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | [10 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 2
|  | AWSS Cistern Design |  |  | Frank Piruzmand | EST |  |  |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.99 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 1.32 |  |  |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 | 0.0099 | 0.0099 | 0.0099 | 0.0099 | [8 empty] | 0.0396 | 0.0099 | 0.0099 | 0.0099 | 0.0099 | [8 empty] | 0.0396 | 0.0099 | 0.0099 | 0.0099 | 0.0099 | [8 empty] | 0.0396 | 0.0099 | 0.0099 | 0.0099 | 0 | [8 empty] | 0.0297 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 2.5385
[45 empty] | 0 | [64 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Resident Engineer (1250) |  |  | Mike Acosta | BCM | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 15
|  | Inspector (1250) |  |  | Gabriel Fernandez | BCM | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 15
|  | Inspector (1250) |  |  | Terrance Huey | BCM | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 13
|  | Office Engineer Engineer (1250) |  |  | Peter Chin | BCM | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 15
[58 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Resident Engineer (1251) |  |  | TBD | BCM | [12 empty] | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 29
|  | Inspector (1251) |  |  | TBD | BCM | [12 empty] | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 29
|  | Inspector (1251) |  |  | TBD | BCM | [12 empty] | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 27
|  | Office Engineer Engineer (1251) |  |  | TBD | BCM | [12 empty] | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 29
|  | Department Of Public Works (DPW) |  |  |  |  | 4.51 | 7.24 | 7.54 | 11.12 | 10.75 | 12.29 | 12.87 | 13.11 | 10.72 | 11.11 | 11.13 | 8.43 | 120.82 | 12.75 | 12.67 | 12.77 | 12.77 | 8.77 | 9.62 | 9.61 | 9.61 | 9.63 | 9.62 | 9.62 | 9.62 | 127.06 | 8.22 | 10 | 10 | 10.29 | 11.64 | 10.56 | 6.2 | 6.98 | 6.98 | 7.31 | 7.31 | 7.33 | 102.82 | 12 | 12 | 12 | 12 | [8 empty] | 48 | 15 | 15 | 15 | 15 | [8 empty] | 60 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 12 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614.7
Group: City and County of San Francisco
|  | Arts Commission |  |  | Various | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | City Attorney's Office |  |  | Various | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | SFFD |  |  | Corbett/Stephenson/Fields | CCSF | [12 empty] | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | [10 empty] | 0.2 | 5
|  | SFPD |  |  | Michael Connolly | CCSF | [12 empty] | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [8 empty] | 0.4 | 0.1 | 0.1 | [10 empty] | 0.2 | 5
|  | Real Estate |  |  | TBD | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Dept of Public Health |  |  | TBD | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | SFPUC |  |  | TBD | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | SFCTA |  |  | TBD | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [38 empty] | 0 | [64 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [51 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | City and County of San Francisco |  |  |  |  | Allowances | [12 empty] | Allowances | [12 empty] | Allowances | [12 empty] | Allowances | [12 empty] | Allowances | [12 empty] | Allowances | [12 empty] | Allowances | [12 empty] | Allowances | [12 empty] | Allowances | [12 empty] | Allowances | [12 empty] | TBD
|  | GRAND TOTALS |  |  |  |  | 53.4563 | 57.4694 | 62.2581 | 91.2614 | 127.8914 | 160.1385 | 158.4066 | 161.2329 | 159.7393 | 167.7911 | 165.6973 | 162.2962 | 1527.6387 | 168.6468 | 164.0816 | 163.6017 | 163.3465 | 163.7667 | 147.0816 | 147.6864 | 67.7623 | 67.9815 | 74.6804 | 75.7419 | 74.2089 | 1478.5862 | 68.8741 | 68.5166 | 68.4379 | 69.6481 | 78.9927 | 77.7727 | 73.6837 | 74.2667 | 73.1124 | 73.4424 | 78.4858 | 78.5568 | 883.7901 | 204.4566 | 263.0648 | 267.6691 | 267.6691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1002.8596 | 247.8745 | 247.8745 | 229.8745 | 228.6757 | [8 empty] | 954.2992 | 229.2335 | 225.6735 | 225.8735 | 222.8735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903.6538 | 213.8735 | 210.8735 | 164.0735 | 144.1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732.9249 | 145.4046 | 139.3246 | 132.5246 | 125.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6782 | 153.484 | 154.284 | 147.034 | 130.284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585.0861 | #VALUE! | 14.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
[7 empty] | #VALUE! | 7.24 | 7.54 | 11.12 | 10.75 | 12.29 | 12.87 | 13.11 | 10.72 | 11.11 | 11.13 | 8.43 | 120.82 | #VALUE! | 12.67 | 12.77 | 12.77 | 8.77 | 9.62 | 9.61 | 9.61 | 9.63 | 9.62 | 9.62 | 9.62 | 127.06 | #VALUE! | 10 | 10 | 10.29 | 11.64 | 10.56 | 6.2 | 6.98 | 6.98 | 7.31 | 7.31 | 7.33 | 102.82 | #VALUE! | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | #VALUE! | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | #VALUE! | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | #VALUE! | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | #VALUE! | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
[7 empty] | 64.4889 | 68.7592 | 73.3674 | 102.6916 | 137.6423 | 169.7749 | 167.7599 | 166.1047 | 165.7908 | 169.4547 | 166.9229 | 163.3954 |  | 171.9693 | 169.5049 | 168.9086 | 168.6023 | 199.1003 | 148.6141 | 148.6416 | 68.6937 | 68.9528 | 75.5152 | 76.564 | 71.314 |  | 64.8683 | 63.6343 | 63.5399 | 63.4346 | 73.7775 | 70.267 | 65.9823 | 66.5258 | 65.3657 | 82.5757 | 87.0082 | 87.0894 |  | 219.1451 | 215.4399 | 212.4711 | 212.4381 | 193.7881 | 190.7584 | 167.8954 | 166.4563 | 167.0433 | 166.4833 | 172.6833 | 172.6833 |  | 193.7881 | 190.7584 | 167.8954 | 166.4563 | 167.0433 | 166.4833 | 172.6833 | 172.6833 | 173.7833 | 173.7767 | 173.1275 | 134.5856 |  | 167.0433 | 166.4833 | 172.6833 | 172.6833 | 35.7764 | 39.7764 | 49.0264 | 39.2764 | 37.35 | 36.85 | 19.05 | 7.3 |  | 173.7833 | 173.7767 | 173.1275 | 134.5856 | [9 empty] | 136.349 | 69.079 | 77.279 | 45.079
[7 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 36 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 56.4 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 56.4 | 3.7 | 3.7 | 3.7 | 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.8 | 3.25 | 3.25 | 3.25 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 3.25 | 3.25 | 3.25 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 3.25 | 3.25 | 3.25 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 204.6
[9 empty] | FTEs by Months | [12 empty] | FTEs by Months | [12 empty] | FTEs by Months | [12 empty] | FTEs by Quarters | [12 empty] | FTEs by Quarters | [12 empty] | FTEs by Quarters | [12 empty] | FTEs by Quarters | [12 empty] | FTEs by Quarters | [12 empty] | FTEs by Quarters | [12 empty] | FTEs by Quarters

## Schedule Basis 1p
CENTRALSUBWAY PROJECT
Staffing Plan
Schedule Basis
Schedule Basis | 2010 |  |  |  | 2011 |  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019
| 1Q10 | 2Q10 | 3Q10 | 4Q10 | 1Q11 | 2Q11 | 3Q11 | 4Q11 | 1Q12 | 2Q12 | 3Q12 | 4Q12 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | 1Q19 | 2Q19 | 3Q19 | 4Q19
CS155-1: Tunnel and Utilities Final Design
CS155-2: Stations Final Design
CS155-3: Surface, Trackway and Systems Final Design
CP 1250: Utility Relocation #1 (Portal and MOS)
CP 1251: Utility Relocation #2 (UMS)
CP 1252: Guideway Tunnels
CP 1253: Union Square/Market St Sta (UMS)
CP 1254: Chinatown Station (CTS)
CP 1255: Moscone Station (MOS)
CP 1256: Surface, Trackwork and Systems (STS)
Project Start-up, Close-out, Change/Claims Resolution
Final Design =
Design support during construction =
Construction =
Contract close-out =
Project start-up/close-out =

## Schedule Basis 3pp
Schedule Basis | 2010 | [11 empty] | 2011 | [12 empty] | 2012 | [12 empty] | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019
| Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Oct | Nov | Dec | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | 1Q19 | 2Q19 | 3Q19 | 4Q19
CS155-1: Tunnel and Utilities Final Design
CS155-2: Stations Final Design
CS155-3: Surface, Trackway and Systems Final Design
CP 1250: Utility Relocation #1 (Portal and MOS)
CP 1251: Utility Relocation #2 (UMS)
CP 1252: Guideway Tunnels
CP 1300: WP 1253 Union Square/Market St Sta (UMS)
CP 1300: WP 1254 Chinatown Station (CTS)
CP 1300: WP 1255 Moscone Station (MOS)
CP 1300: WP 1256 Surface, Trackwork and Systems (STS)
Project Start-up, Close-out, Change/Claims Resolution
|  | By Month | [11 empty] | By Month | [12 empty] | By Month | [12 empty] | By Quarter |  |  |  | By Quarter |  |  |  | By Quarter |  |  |  | By Quarter |  |  |  | By Quarter |  |  |  | By Quarter |  |  |  | By Quarter
Final Design =
Design support during construction =
Construction =
Contract close-out =
Project start-up/close-out =
160
#REF!

## PLANNED FTEs
DP1
[6 empty] | 0.833 | 1.33 | 1.78
[6 empty] | 160 | [43 empty] | 3
| SCC Code | [5 empty] | 2010 | [11 empty] | Totals | 2011 | [11 empty] | Totals | 2012 |  |  |  |  | 2012 | [10 empty] | Totals | 2013 | [11 empty] | Totals | 2014 | [11 empty] | Totals | 2015 | [11 empty] | Totals | 2016 | [11 empty] | Totals | 2017 | [11 empty] | Totals | 2018 | [11 empty] | Totals | 2019 | [11 empty] | Totals | ETC |  | Grand Totals |  | 1652.69
|  | Position | Cross Walk# | Unit | Individual | Org | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2010 | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2011 | Jan | Feb | Mar | April | May | SCC Code | Position | Individual | Org | June | July | Aug | Sept | Oct | Nov | Dec | 2012 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2013 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2014 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2015 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2016 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2017 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2018 | 1Q19 | 2Q19 | 3Q19 | 4Q19 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2019 | June 2012 - May 2019 | [6 empty] | PE | FD | PM | CM | Non-Constr | Legal, Rev | Test | S-U |  | Real Estate
|  | Group: SFMTA - Program Management | [138 empty] | FTEs | $Labor | FTEs | $Labor |  |  |  | 80.01 | 80.02 | 80.03 | 80.04 | 80.05 | 80.06 | 80.07 | 80.08 | 80 | 60
1 | 80.03 | Sr Program Manager | 150 | 200 | John Funghi | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 | Sr Program Manager | John Funghi | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 1.35 | [10 empty] | 4.05 | 75.15 | 3372061.662 | 101.25 | 4543196.85 | 80.03 |  |  | 80.03: 4543196.85
2 | 80.03 | Sr Clerk Typist | 150 | 320 | Joery Nacion | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 | Sr Clerk Typist | Joery Nacion | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 1.35 | [10 empty] | 4.05 | 75.15 | 927854.505 | 101.25 | 1250103.375 | 80.03 |  |  | 80.03: 1250103.375
[141 empty] | 0 | 0
[141 empty] | 0 | 0
3 | 80.03 | Secretary II MPMS | 150 | 320 | Various | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 | Secretary II MPMS |  | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | [11 empty] | 2.7 | 73.8 | 1004370.768 | 99.9 | 1359575.064 | 80.03 |  |  | 80.03: 1359575.064
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
4 | [5 empty] | SFMTA | [34 empty] | SFMTA | [7 empty] | 0 | [91 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
5 | [5 empty] | SFMTA | [34 empty] | SFMTA | [7 empty] | 0 | [91 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
6 | [5 empty] | SFMTA | [34 empty] | SFMTA | [7 empty] | 0 | [91 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
7 | [5 empty] | SFMTA | [34 empty] | SFMTA | [7 empty] | 0 | [91 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
8 | 80.03 | Program Manager Project Services | 275 | 439 | Bill Neilson | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | [6 empty] | 5.4 | [12 empty] | 0 | [5 empty] | 80.03 |  |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 5.4 | 224636.544 | 80.03 |  |  | 80.03: 224636.544
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
9 | 80.04 | Construction Manager | 150 | 320 | Arthur Wong | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.04 | Construction Manager | Arthur Wong | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 1.35 | [10 empty] | 4.05 | 75.15 | 2504038.581 | 101.25 | 3373704.675 |  | 80.04 |  | 80.04: 3373704.675
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
10 | 80.03 | Quality Assurance Manager | 150 | 320 | Roger Nguyen | SFMTA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 80.03 | Quality Assurance Manager | Roger Nguyen | SFMTA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | [10 empty] | 3 | 42.5 | 1416122.95 | 57 | 1899270.78 | 80.03 |  |  | 80.03: 1899270.78
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
11 | 80.03 | QA Support | 275 | 420 | Elisa Ng | SFMTA | [12 empty] | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 80.03 | QA Support | Elisa Ng | SFMTA | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | [10 empty] | 0.6 | 8.5 | 211374.26 | 10.2 | 253649.112 | 80.03 |  |  | 80.03: 253649.112
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
12 | 80.03 | Environmental Manager | 305 | 431 | David Greenaway | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 |  |  | SFMTA | [7 empty] | 4.5 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 26.1 | 747260.226 | 80.03 |  |  | 80.03: 747260.226
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
13 | 80.03 | Finance/Grants Manager | 305 | 432 | Lewis Ames | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 | Finance/Grants Manager | Lewis Ames | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 1.35 | 1.35 | [10 empty] | 2.7 | 73.8 | 2112942.708 | 99.9 | 2860202.934 | 80.03 |  |  | 80.03: 2860202.934
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
14 | [5 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
15 | 80.03 | Finance Director |  |  | Sonali Bose | SFMTA | [12 empty] | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 80.03 | Finance Director | Sonali Bose | SFMTA | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | [10 empty] | 0.6 | 8.5 | 367975.2 | 10.2 | 441570.24 | 80.03 |  |  | 80.03: 441570.24
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
15 | 80.03 | Contracts Manager |  |  | Various | SFMTA | [12 empty] | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 2.4 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 80.03 | Contracts Manager | Various | SFMTA | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 1.44 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | 0.3 | 0.3 | [8 empty] | 1.2 | 0.3 | 0.3 | [10 empty] | 0.6 | 8.64 | 216897.8688 | 11.64 | 292209.6288 | 80.03 |  |  | 80.03: 292209.6288
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
16 | [5 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
18 | 80.04 | Construction Inspectors |  |  | TBD | SFMTA | [9 empty] | 0.9 | 0.9 | 0.9 | 2.7 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.04 | Construction Inspectors | B. Volberding | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | [10 empty] | 5.4 | 76.5 | 1664640 | 94.5 | 2056320 |  | 80.04 |  | 80.04: 2056320
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
17 | [5 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
18 | [5 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
19 | [5 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
22 | 60 | Real Estate Manager | 305 | 432 | Kerstin Magary | SFMTA |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 2.4 | [5 empty] | 60 | Real Estate Manager | Kerstin Magary | SFMTA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.5 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 9.5 | 362753.51 | 15.9 | 607134.822 | 60 |  |  | 80: 607134.822
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
23 | 60 | Real Estate | 275 | 420 | Jason Gallegos | SFMTA |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 2.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | [5 empty] | 60 | Real Estate | Jason Gallegos | SFMTA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.5 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 9.5 | 238487.24 | 13.2 | 331371.744 | 60 |  |  | 80: 331371.744
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
24 | 60 | Real Estate | 275 | 420 | Charles Lewis | SFMTA | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 60 |  |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 60
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
25 | 60 | Real Estate | 275 | 439 | Ken Yee | SFMTA |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 2.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.2 | [5 empty] | 60 |  |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 3.7 | 106278.652 | 60 |  |  | 80: 106278.652
[7 empty] | 0.17188 | 0.2 | 0.19687 | 0.14688 | 0.15 | 0.29063 | 0.25 | 0.38906 | 0.13906 | 0.28906 |  |  | 2.2234 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 2.2234
[7 empty] | 0.17188 | 0.2 | 0.19687 | 0.14688 | 0.15 | 0.29063 | 0.25 | 0.38906 | 0.13906 | 0.28906 |  |  | 2.2234 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 2.2234
|  | Subotals - Group: SFMTA - Management |  |  |  |  | 6.8 | 6.8 | 7.7 | 7.7 | 7.7 | 7.7 | 6.8 | 6.8 | 6.8 | 7.7 | 7.7 | 7.7 | 87.9 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 91.2 | 7.12 | 7.12 | 7.12 | 7.12 | 7.12 |  | Subotals - Group: SFMTA - Management |  |  | 7.22 | 7.22 | 7.22 | 7.22 | 7.22 | 7.22 | 7.22 | 86.14 | 21.6 | 21.6 | 21.6 | 21.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.4 | 18.6 | 18.6 | 18.6 | 18.6 | [8 empty] | 74.4 | 18.6 | 18.6 | 18.6 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.4 | 18.6 | 18.6 | 18.6 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.4 | 18.6 | 18.6 | 18.6 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.4 | 18.6 | 18.6 | 18.6 | 18.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.4 | 17.25 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.75 | 536.69 | 14399519.2528 | 751.39 | 20346484.6468 |  |  | 169.2404 |  | 0 | 13871674.7538 | 5430024.675 | 0 | 0 | 0 | 0 | 1044785.218
[5 empty] | Budget |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
[5 empty] | Actual |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
[5 empty] | Forecast |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
Group: SFMTA - Engineering
1 | 80.02 | Deputy Program Manager | 150 | 200 | Hoe, Albert | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 | Deputy Program Manager | Hoe, Albert | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 1.35 | [10 empty] | 4.05 | 75.15 | 2162812.491 | 101.25 | 2913968.925 | 80.02 |  |  | 80.02: 2913968.925
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
2 | 80.02 | Associate Engineer (5207) | 275 | 420 | Pong, Sanford | SFMTA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 | Associate Engineer (5207) | Pong, Sanford | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 1.2 | 1.2 | 1.2 | 1.2 | [8 empty] | 4.8 | 1.2 | 1.2 | 1.2 | 1.2 | [8 empty] | 4.8 | 1.2 | 1.2 | 1.2 | 1.2 | [8 empty] | 4.8 | 1.2 | 1.2 | 1.2 | 1.2 | [8 empty] | 4.8 | 1.2 | 1.2 | 1.2 | 1.2 | [8 empty] | 4.8 | 1.2 | [11 empty] | 1.2 | 42.3 | 1051897.788 | 69.6 | 1730782.176 | 80.02 |  |  | 80.02: 1730782.176
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
3 | 80.02 | Associate Engineer (5207) | 150 | 320 | Wilson, Prester | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | [12 empty] | 0 | [5 empty] | 80.02 | Associate Engineer (5207) |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 10.8 | 268569.648 | 80.02 |  |  | 80.02: 268569.648
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
4 | 80.02 | Associate Engr MCEG (5207) - Sr Engr | 305 | 431 | Jane Wang (5211) | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 | Associate Engr MCEG (5207) - Sr Engr | Jane Wang (5211) | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | [12 empty] | 0 | 71.1 | 1768083.516 | 86.4 | 2148557.184 | 80.02 |  |  | 80.02: 2148557.184
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
7 | 80.02 | Assistant Engineer (5203) |  |  | Seng, Wuthea | SFMTA | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 12.6 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | [7 empty] | 6.5 | [5 empty] | 80.02 | Assistant Engineer (5203) | Seng, Wuthea | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 6.3 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | [12 empty] | 0 | 71.1 | 1519543.512 | 90.2 | 1927747.184 | 80.02 |  |  | 80.02: 1927747.184
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
8 | 80.02 | Assistant Engineer (5203) |  |  | Various | SFMTA | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 7.2 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | [7 empty] | 4.25 | [5 empty] | 80.02 | Assistant Engineer (5203) |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 11.45 | 128231.52 | 80.02 |  |  | 80.02: 128231.52
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
9 | 80.02 | Assistant Engineer (5203) |  |  | Various | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | [7 empty] | 2.25 | [5 empty] | 80.02 | Assistant Engineer (5203) |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 13.05 | 192347.28 | 80.02 |  |  | 80.02: 192347.28
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0 | bar: 80.01
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
17 | 80.02 | Engineer (5241) |  |  | Huey, Lang | SFMTA | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 7.2 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 5.95 | [5 empty] | 80.02 | Engineer (5241) |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 13.15 | 378456.211 | 80.02 |  |  | 80.02: 378456.211
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
19 | 80.02 | Engineer (5241) |  |  | Phang, Tee | SFMTA | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 7.2 | 1.35 | 1.35 | 1.35 | 1.35 | 1.35 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 8.25 | [5 empty] | 80.02 | Engineer (5241) |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 15.45 | 444650.073 | 80.02 |  |  | 80.02: 444650.073
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
[6 empty] | SFMTA | [34 empty] | SFMTA | [99 empty] | 0 | 0
22 | 80.02 | Sr Engineer MCEQ (5211) |  |  | Bhatti, Jaswant | SFMTA | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 6.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 4.5 | [5 empty] | 80.02 | Sr Engineer MCEQ (5211) |  | SFMTA | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 11.1 | 369857.994 | 80.02 |  |  | 80.02: 369857.994
| 80.02 |  |  |  | Bhatti, Jaswant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.95 | 0.875 |  |  | 2.325 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 2.325
| 80.02 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.95 | 0.875 |  |  | 2.325 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 2.325
[141 empty] | 0 | 0 | bar: 80.01
| 80.02 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
| 80.02 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[5 empty] | Simmons, Edson |  | 0.075 | 0.14375 | 0.125 | 0.05625 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.4 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0.4
[7 empty] | 0.075 | 0.14375 | 0.125 | 0.05625 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.4 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0.4
|  | Subtotals - Group: SFMTA - Engineering |  |  |  |  | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 7.1 | 85.2 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 2.7 | 64.1 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7 |  | Subtotals - Group: SFMTA - Engineering |  |  | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 38.7 | 10.8 | 10.8 | 10.8 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.2 | 9.3 | 9.3 | 9.3 | 9.3 | [8 empty] | 37.2 | 9.3 | 9.3 | 9.3 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2 | 9.3 | 9.3 | 9.3 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2 | 9.3 | 9.3 | 9.3 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2 | 9.3 | 9.3 | 9.3 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2 | 3.9 | 1.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 259.65 | 6502337.307 | 422.45 | 10503168.195 |  |  | 155.3907 |  | 10503168.195 | 0 | 0 | 0 | 0 | 0 | 0
Group: SFMTA - Start-Up; Safety & Security; Other
1 | 80.08 | Start-Up Manager | 150 | 200 | TBD | Ops | [12 empty] | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.6 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 80.08 | Start-Up Manager | TBD | Ops | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.6 | 0.15 | 0.15 | 0.15 | 0.15 | [8 empty] | 0.6 | 0.15 | 0.15 | 0.15 | 0.15 | [8 empty] | 0.6 | 0.15 | 0.15 | 0.15 | 0.15 | [8 empty] | 0.6 | 0.15 | 0.15 | 0.15 | 0.15 | [8 empty] | 0.6 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | [10 empty] | 5.4 | 29.75 | 1047200 | 30.6 | 1077120 | 80.08 |  |  | 80.08: 1077120
[141 empty] | 0 | 0
[141 empty] | 0 | 0
2 | 80.08 | Senior Operations Manager | 150 | 320 | TBD | Ops | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Senior Operations Manager | TBD | Ops | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.75 | 0.75 | 0.75 | 0.75 | [8 empty] | 3 | 0.75 | 0.75 | 0.75 | 0.75 | [8 empty] | 3 | 0.3 | 0.3 | [10 empty] | 0.6 | 6.6 | 222718.32 | 6.6 | 222718.32 | 80.08 |  |  | 80.08: 222718.32
[141 empty] | 0 | 0 |  | 0
[141 empty] | 0 | 0 |  | 0
3 | 80.08 | Senior Operations Manager | 150 | 320 | TBD | Ops | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Senior Operations Manager | TBD | Ops | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0.5 | 0.5 | [8 empty] | 1 | 0.6 | 0.6 | 0.6 | 0.6 | [8 empty] | 2.4 | 0.75 | 0.75 | 0.75 | 0.75 | [8 empty] | 3 | [12 empty] | 0 | 6.4 | 215969.28 | 6.4 | 215969.28 | 80.08 |  |  | 80.08: 215969.28
[141 empty] | 0 | 0 |  | 0
[141 empty] | 0 | 0 |  | 0
4 | 80.08 | Transit Manager II | 305 | 431 | TBD | Ops | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Transit Manager II | TBD | Ops | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0.5 | 0.5 | [8 empty] | 1 | 0.9 | 0.9 | 0.9 | 0.9 | [8 empty] | 3.6 | 6 | 6 | 6 | 6 | [8 empty] | 24 | [12 empty] | 0 | 28.6 | 787512.44 | 28.6 | 787512.44 | 80.08 |  |  | 80.08: 787512.44
[141 empty] | 0 | 0 |  | 0
[141 empty] | 0 | 0 |  | 0
5 | 80.08 | Transit Manager I | 305 | 432 | TBD | Ops | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Transit Manager I | TBD | Ops | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 2 | 6 | 6 | 6 | 6 | [8 empty] | 24 | [12 empty] | 0 | 26 | 634082.8 | 26 | 634082.8 | 80.08 |  |  | 80.08: 634082.8
[141 empty] | 0 | 0 |  | 0
[141 empty] | 0 | 0 |  | 0
6 | 80.08 | Transit Operator | 275 | 420 | TBD | Ops | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Transit Operator | TBD | Ops | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 1.8 | 1.8 | 1.8 | [8 empty] | 5.4 | 25 | 30 | 30 | 30 | [8 empty] | 115 | [12 empty] | 0 | 120.4 | 1640738.96 | 120.4 | 1640738.96 | 80.08 |  |  | 80.08: 1640738.96
[141 empty] | 0 | 0 |  | 0
[141 empty] | 0 | 0 |  | 0
7 | 80.08 | Station Agent | 275 | 420 | TBD | Ops | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Station Agent | TBD | Ops | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 1.8 | 1.8 | 1.8 | [8 empty] | 5.4 | 25 | 30 | 30 | 30 | [8 empty] | 115 | [12 empty] | 0 | 120.4 | 2060838.64 | 120.4 | 2060838.64 | 80.08 |  |  | 80.08: 2060838.64
[141 empty] | 0 | 0 |  | 0
[141 empty] | 0 | 0 |  | 0
8 | 80.08 | Senior Stationary Engineer |  |  | TBD | Ops | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Senior Stationary Engineer | TBD | Ops | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0.5 | 0.5 | [8 empty] | 1 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 2 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | [12 empty] | 0 | 9 | 180017.1 | 9 | 180017.1 | 80.08 |  |  | 80.08: 180017.1
[141 empty] | 0 | 0 |  | 0
[141 empty] | 0 | 0 |  | 0
9 | 80.08 | Electronic Maint Tech Asst Sup |  |  | TBD | Ops | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Electronic Maint Tech Asst Sup | TBD | Ops | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0.25 | 0.25 | 0.25 | [8 empty] | 0.75 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | [12 empty] | 0 | 6.75 | 173182.05 | 6.75 | 173182.05 | 80.08 |  |  | 80.08: 173182.05
[141 empty] | 0 | 0 |  | 0
[141 empty] | 0 | 0 |  | 0
10 | 80.08 | Parking Control Officer |  |  | TBD | DPT | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Parking Control Officer | TBD | DPT | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [12 empty] | 0 | 4 | 49727.2 | 4 | 49727.2 | 80.08 |  |  | 80.08: 49727.2
[19 empty] | 0 | [12 empty] | 0 | [29 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 80.08 |  |  | 80.08: 0
[19 empty] | 0 | [12 empty] | 0 | [29 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 80.08 |  |  | 80.08: 0
11 | 80.03 | Safety Representative |  |  | B Woo/Kartik Shah | SFMTA | [12 empty] | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 80.03 | Safety Representative | B Woo/Kartik Shah | SFMTA | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | 10.8 | [12 empty] | 0 | 71.1 | 1820160 | 81.6 | 2088960 | 80.03 |  |  | 80.03: 2088960
| 80.03 | [36 empty] | 80.03 | [102 empty] | 0 | 0 |  | 0 | 80.03
| 80.03 | [36 empty] | 80.03 | [102 empty] | 0 | 0 |  | 0 | 80.03
12 | 80.03 | Traffic Engineer |  |  | Al Herce/Albert Wong | DPT | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 80.03 | Traffic Engineer | Al Herce/Albert Wong | DPT | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 0.25 | 0.25 | 0.25 | 0.25 | [8 empty] | 1 | 0.25 | 0.25 | 0.25 | 0.25 | [8 empty] | 1 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 5.5 | 140800 | 17.5 | 448000 | 80.02 |  |  | 80.02: 448000
| 80.03 | [36 empty] | 80.03 | [102 empty] | 0 | 0 |  | 0 | 80.02 |  |  | 80.02: 0; 80.03: 0
| 80.03 | [36 empty] | 80.03 | [102 empty] | 0 | 0 |  | 0 | 80.02 |  |  | 80.02: 0; 80.03: 0
13 | 80.03 | Traffic Asst Engineer |  |  | S Broady/L Slingsby | DPT | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.5 | [12 empty] | 0 | [5 empty] | 80.03 | Traffic Asst Engineer | S Broady/L Slingsby | DPT | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 3.5 | 74480 | 80.02 |  |  | 80.02: 74480
| 80.03 | [36 empty] | 80.03 | [102 empty] | 0 | 0 |  | 0 | 80.02 |  |  | 80.02: 0; 80.03: 0
| 80.03 | [36 empty] | 80.03 | [102 empty] | 0 | 0 |  | 0 | 80.02 |  |  | 80.02: 0; 80.03: 0
14 | 80.03 | Traffic Assoc Engineer I |  |  | Alex Wong | DPT | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 80.03 | Traffic Assoc Engineer I | Alex Wong | DPT | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 0.25 | 0.25 | 0.25 | 0.25 | [8 empty] | 1 | 0.25 | 0.25 | 0.25 | 0.25 | [8 empty] | 1 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 5.5 | 136400 | 17.5 | 434000 | 80.02 |  |  | 80.02: 434000
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | #REF! |  | 80.08
[19 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 |  | 80.08
[141 empty] | 0 | 0
[19 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
[19 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
|  | Subtotals - Group: SFMTA - Start-Up; Safety & Security; Other |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 10.5 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 1.55 | 18.6 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 |  | Subtotals - Group: SFMTA - Start-Up; Safety & Security; Other |  |  | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 23.4 | 3.35 | 3.35 | 3.35 | 3.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4 | 3.35 | 3.35 | 3.35 | 3.35 | [8 empty] | 13.4 | 2.85 | 2.85 | 2.85 | 2.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4 | 2.85 | 2.85 | 4.35 | 4.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4 | 8.65 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.15 | 72.9 | 82.9 | 82.9 | 82.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321.6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 440 | 9109346.79 | 478.85 | 10087346.79 |  |  | 131.6611 |  | 956480 | 2088960 | 0 | 0 | 0 | 0 | 7041906.79
Group: Central Subway Partnership - Program Management/Construction Management
1 | 80.03 | Program Manager | 150 | 200 | Various | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.03 | Program Manager | R.Edwards/R. Redmond | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | [12 empty] | 0 | 79 | 2209289.3221 | 108 | 3020294.2631 | 80.03 |  |  | 80.03: 3020294.2631
3 | 80.03 | Project Controls Manager | 150 | 320 | J Burns | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | [12 empty] | 0 | [5 empty] | 80.03 |  |  | PM/CM | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 12 | 335588.2515 | 80.03 |  |  | 80.03: 335588.2515
4 | 80.03 | Risk/Configuration Manager | 305 | 431 | Various | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.03 | Program Manager Project Services | E. Stassevitch | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | [12 empty] | 0 | 79 | 2209289.3221 | 108 | 3020294.2631 | 80.03 |  |  | 80.03: 3020294.2631
5 | 80.03 | Outreach Manager | 305 | 432 | B Norris | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.03 | Outreach Manager | C.Goodyear | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | [12 empty] | 0 | 61 | 1705906.9449 | 90 | 2516911.8859 | 80.03 |  |  | 80.03: 2516911.8859
6 | 80.03 | Q/A Manager |  |  | M Latch | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.03 | Q/A Manager | M. Latch | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | [12 empty] | 0 | 79 | 2209289.3221 | 108 | 3020294.2631 | 80.03 |  |  | 80.03: 3020294.2631
| 80.03 | Design Oversight Managers |  |  | Various | PM/CM | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 24.6 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 24.6 | [5 empty] | 80.03 | Design Oversight Managers | H.Q Chin | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | [10 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 49 | 1370318.6934 | 98.2 | 2746230.5244 | 80.03 |  |  | 80.03: 2746230.5244
| 80.03 | Regulatory/Interagency Manager |  |  | G Hollins | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.03 | Regulatory/Interagency Manager | G Hollins | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 11 | 307622.5638 | 40 | 1118627.5049 | 80.03 |  |  | 80.03: 1118627.5049
| 80.03 | Document Control Manager |  |  | S MacKenzie | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.03 | Risk/Configuration Manager | Alex Clifford | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 43 | 1202524.5677 | 72 | 2013529.5087 | 80.03 |  |  | 80.03: 2013529.5087
| 80.03 | Program Management Staff |  |  | Various | PM/CM | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 15.12 | 181.44 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 201.444 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 80.03 | Program Management Staff* | Various* (see details below) | PM/CM | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 16.787 | 201.444 | 50.361 | 50.361 | 50.361 | 50.361 | [8 empty] | 201.444 | 39.3 | 39.3 | 39.3 | 39.3 | [8 empty] | 157.2 | 39.3 | 39.3 | 39.3 | 39.3 | [8 empty] | 157.2 | 39.3 | 39.3 | [10 empty] | 78.6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 711.953 | 19910255.1991 | 1178.772 | 32965169.5287 | 80.03 |  |  | 80.03: 32965169.5287
[19 empty] | 0 | [12 empty] | 0 | [29 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 80.03 |  |  | 80.03: 0
| 80.04 | Construction Manager |  |  | TBD | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.04 | Construction Manager | M. Benson | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | [12 empty] | 0 | 79 | 2209289.3221 | 108 | 3020294.2631 | 80.03 |  |  | 80.03: 3020294.2631
| 80.04 | Safety |  |  | TBD | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.04 | Program Safety Manager | D. Matlock | PM/CM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | [12 empty] | 0 | 79 | 2209289.3221 | 108 | 3020294.2631 | 80.03 |  |  | 80.03: 3020294.2631
| 80.04 | CM Staff |  |  | Various | PM/CM | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 1.117 | 13.404 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 30.684 | 2.557 | 2.557 | 2.557 | 2.557 | 2.557 | 80.04 | CM Staff | Various* (see details below) | PM/CM | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 23.285 | 4.5 | 4.5 | 4.5 | 4.5 | [8 empty] | 18 | 4.5 | 4.5 | 4.5 | 4.5 | [8 empty] | 18 | 4.5 | 4.5 | 4.5 | 4.5 | [8 empty] | 18 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 64.5 | 1803786.8516 | 121.373 | 3394279.4037 | 80.03 |  |  | 80.03: 3394279.4037
| 80.04 | Mat'l Testing |  |  | Various | PM/CM | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 25.32 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 25.32 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 80.04 | Mat'l Testing | TBD | PM/CM | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11 | 25.32 | 6.33 | 6.33 | 6.33 | 6.33 | [8 empty] | 25.32 | 4.05 | 4.05 | 4.05 | 4.05 | [8 empty] | 16.2 | 4.05 | 4.05 | 4.05 | 4.05 | [8 empty] | 16.2 | 4.05 | 4.05 | 4.05 | 4.05 | [8 empty] | 16.2 | 4.05 | [11 empty] | 4.05 | [12 empty] | 0 | [12 empty] | 0 | 92.74 | 2593537.87 | 153.93 | 4304758.2955 | 80.03 |  |  | 80.03: 4304758.2955
| 80.04 | Utility CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | [5 empty] | 80.04 | Safety & Security Certification | Wayne Giles | PM/CM | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1.75 | 0.75 | 0.75 | 0.75 | 0.75 | [8 empty] | 3 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 4.75 | 132837.0162 | 16.75 | 468425.2677 | 80.03 |  |  | 80.03: 468425.2677
| 80.04 | Utility Staff |  |  | Various | PM/CM | [12 empty] | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | [5 empty] | 80.04 | CCO | A.Butler/D.Butler | PM/CM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3.5 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | 1.5 | 1.5 | 1.5 | 1.5 | [8 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 15.5 | 433468.1581 | 21.5 | 601262.2839 | 80.03 |  |  | 80.03: 601262.2839
| 80.04 | Tunnel CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [6 empty] | 1 | 1 | 1 | 2 | 2 | 2 | 9 | 2 | 2 | 2 | 2 | 2 | 80.04 | Tunnel RE/ARE | S. Wilson/M.Leong | PM/CM | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 3 | [10 empty] | 9 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 95 | 2656740.324 | 114 | 3188088.3888 | 80.03 |  |  | 80.03: 3188088.3888
| 80.04 | Tunnel Staff |  |  | Various | PM/CM | [12 empty] | 0 | [9 empty] | 6.39 | 6.39 | 6.39 | 19.17 | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 80.04 | Tunnel Staff (OE,IE,Insp) | Various* (see details below) | PM/CM | 6.39 | 6.39 | 6.39 | 6.39 | 6.39 | 7 | 7 | 77.9 | 21 | 27 | 33 | 33 | [8 empty] | 114 | 33 | 33 | 15 | 15 | [8 empty] | 96 | 15 | 12 | 6 | 3 | [8 empty] | 36 | 3 | 3 | [10 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 297.95 | 8332376.6268 | 349.07 | 9761982.578 | 80.03 |  |  | 80.03: 9761982.578
| 80.04 | UMS CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.04 | UMS RE/ARE | TBD | PM/CM | [7 empty] | 0 |  | 6 | 6 | 6 | [8 empty] | 18 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | [12 empty] | 0 | [12 empty] | 0 | 114 | 3188088.3888 | 114 | 3188088.3888 | 80.03 |  |  | 80.03: 3188088.3888
| 80.04 | UMS Staff |  |  | Various | PM/CM | [12 empty] | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | [5 empty] | 80.04 | UMS Staff (OE,IE,Insp) | TBD | PM/CM | [7 empty] | 0 |  | 10.08 | 10.08 | 10.08 | [8 empty] | 30.24 | 10.08 | 10.08 | 10.08 | 10.08 | [8 empty] | 40.32 | 10.08 | 10.1 | 10.1 | 10.1 | [8 empty] | 40.38 | 10.1 | 10.1 | 10.1 | 10.1 | [8 empty] | 40.4 | 10.1 | 10.1 | 10.1 | 6 | [8 empty] | 36.3 | [12 empty] | 0 | [12 empty] | 0 | 187.64 | 5247481.6253 | 193.64 | 5415275.751 | 80.03 |  |  | 80.03: 5415275.751
| 80.04 | CTS CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.04 | CTS RE/ARE | TBD | PM/CM | [7 empty] | 0 |  | 6 | 6 | 6 | [8 empty] | 18 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | [10 empty] | 12 | [12 empty] | 0 | 126 | 3523676.6403 | 126 | 3523676.6403 | 80.03 |  |  | 80.03: 3523676.6403
7 | 80.04 | CTS Staff |  |  | Various | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.04 | CTS Staff (OE,IE,Insp) | TBD | PM/CM | [7 empty] | 0 |  | 11.88 | 11.88 | 11.88 | [8 empty] | 35.64 | 11.88 | 11.88 | 11.88 | 11.88 | [8 empty] | 47.52 | 11.88 | 10.1 | 10.1 | 10.1 | [8 empty] | 42.18 | 10.1 | 10.1 | 10.1 | 10.1 | [8 empty] | 40.4 | 10.1 | 10.1 | 10.1 | 10.1 | [8 empty] | 40.4 | 6 | [11 empty] | 6 | [12 empty] | 0 | 212.14 | 5932640.972 | 212.14 | 5932640.972 | 80.03 |  |  | 80.03: 5932640.972
8 | 80.04 | MOS CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.04 | YB\MOS RE/ARE | TBD | PM/CM | [7 empty] | 0 |  | 6 | 6 | 6 | [8 empty] | 18 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 6 | 6 | [8 empty] | 24 | 6 | 6 | 3 | [9 empty] | 15 | [12 empty] | 0 | [12 empty] | 0 | 105 | 2936397.2002 | 105 | 2936397.2002 | 80.03 |  |  | 80.03: 2936397.2002
9 | 80.04 | MOS Staff |  |  | Various | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.04 | YB\MOS Staff (OE,IE,Insp) | TBD | PM/CM | [7 empty] | 0 |  | 10.68 | 10.68 | 10.68 | [8 empty] | 32.04 | 10.68 | 10.68 | 10.68 | 10.68 | [8 empty] | 42.72 | 10.68 | 11.88 | 11.88 | 11.88 | [8 empty] | 46.32 | 11.88 | 11.88 | 11.88 | 11.88 | [8 empty] | 47.52 | 11.88 | 6 | [10 empty] | 17.88 | [12 empty] | 0 | [12 empty] | 0 | 186.48 | 5215041.4276 | 186.48 | 5215041.4276 | 80.03 |  |  | 80.03: 5215041.4276
| 80.04 | STS CM's/RE's |  |  | TBD | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.04 | STS RE/ARE | TBD | PM/CM | [7 empty] | 0 |  | 3 | 3 | 3 | [8 empty] | 9 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 3 | [9 empty] | 9 | [12 empty] | 0 | 66 | 1845735.383 | 66 | 1845735.383 | 80.03 |  |  | 80.03: 1845735.383
| 80.04 | STS Staff |  |  | Various | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.04 | STS Staff (OE,IE,Insp) | TBD | PM/CM | [7 empty] | 0 |  | 3 | 3 | 3 | [8 empty] | 9 | 3 | 3 | 3 | 3 | [8 empty] | 12 | 3 | 3 | 9.2 | 9.2 | [8 empty] | 24.4 | 9.2 | 9.2 | 9.2 | 9.2 | [8 empty] | 36.8 | 9.2 | 9.2 | 9.2 | 9.2 | [8 empty] | 36.8 | 9.2 | 6 | [10 empty] | 15.2 | [12 empty] | 0 | 134.2 | 3752995.2788 | 134.2 | 3752995.2788 | 80.03 |  |  | 80.03: 3752995.2788
| 80.08 | Start-Up, Testing and Commissioning |  |  | Various | PM/CM | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 80.08 | Start-Up, Testing and Commissioning |  | PM/CM | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 8.2 | 8.2 | [8 empty] | 16.4 | 9 | 9 | 13.75 | [9 empty] | 31.75 | [12 empty] | 0 | 48.15 | 1346547.859 | 48.15 | 1346547.859 | 80.03 |  |  | 80.03: 1346547.859
[19 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
10 | [18 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
|  | Subtotals: Group: Central Subway Partnership - Program Management/Construction Management |  |  |  |  | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 352.764 | 33.504 | 33.504 | 33.504 | 33.504 | 33.504 | 33.504 | 34.504 | 34.504 | 34.504 | 41.894 | 41.894 | 41.894 | 430.218 | 37.844 | 37.844 | 37.844 | 37.844 | 37.844 |  | Subtotals: Group: Central Subway Partnership - Program Management/Construction Management |  |  | 38.537 | 38.537 | 38.537 | 38.537 | 38.537 | 39.147 | 39.147 | 460.199 | 115.441 | 178.081 | 184.081 | 184.081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661.684 | 168.99 | 168.99 | 150.99 | 150.99 | [8 empty] | 639.96 | 149.49 | 145.93 | 146.13 | 143.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584.68 | 134.13 | 131.13 | 82.83 | 82.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430.92 | 82.83 | 72.9 | 72.1 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292.83 | 49.7 | 40.5 | 33.25 | 16.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3021.003 | 84484426.201 | 3993.205 | 111672723.6379 |  |  |  |  | 0 | 111672723.6379 | 0 | 0 | 0 | 0 | 0
Group: PCC
| 80.03 | Estimating | 150 | 200 | Various | PCC | [11 empty] | 1.17 | 1.17 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 4.71 | 56.52 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 80.03 | Estimating | C.J.Dombrowski | PCC | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 24.6 | 3.64 | 3.64 | 3.64 | 3.64 | [8 empty] | 14.56 | 3.78 | 3.78 | 3.78 | 3.78 | [8 empty] | 15.12 | 3.78 | 3.78 | 3.78 | 3.78 | [8 empty] | 15.12 | 3.78 | 3.78 | 3.78 | 3.78 | [8 empty] | 15.12 | 3.78 | 3.78 | 3.78 | 3.78 | [8 empty] | 15.12 | 3.12 | 3.12 | 3.12 | 3.12 | [8 empty] | 12.48 | [12 empty] | 0 | 101.87 | 1639999.1745 | 169.81 | 1412838.7273 | 80.03 |  |  | 80.03: 1412838.7273
| 80.03 | Cost Schedule | 150 | 320 | Various | PCC | [11 empty] | 1.4 | 1.4 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 30.36 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 80.03 | Cost /Schedule | Various* (see detailsbelow) | PCC | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 26.64 | 6.62 | 6.62 | 6.62 | 6.62 | [8 empty] | 26.48 | 6.62 | 6.62 | 6.62 | 6.62 | [8 empty] | 26.48 | 6.62 | 6.62 | 6.62 | 6.62 | [8 empty] | 26.48 | 6.62 | 6.62 | 6.62 | 6.62 | [8 empty] | 26.48 | 6.62 | 6.62 | 6.62 | 6.62 | [8 empty] | 26.48 | 1.44 | 1.44 | 1.44 | 1.44 | [8 empty] | 5.76 | [12 empty] | 0 | 153.7 | 2474407.3144 | 196.56 | 927570.6278 | 80.03 |  |  | 80.03: 927570.6278
| 80.03 | Systems/Project Reporting | 305 | 431 | Various | PCC | [11 empty] | 1.62 | 1.62 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 76.8 | 5.73 | 5.73 | 5.73 | 5.73 | 5.73 | 80.03 | Systems/Project Reporting | Various* (see detailsbelow) | PCC | 5.73 | 5.73 | 5.73 | 5.73 | 5.73 | 5.73 | 5.73 | 68.76 | 17.13 | 17.13 | 17.13 | 17.13 | [8 empty] | 68.52 | 17.13 | 17.13 | 17.13 | 17.13 | [8 empty] | 68.52 | 17.13 | 17.13 | 17.13 | 17.13 | [8 empty] | 68.52 | 17.13 | 17.13 | 17.13 | 17.13 | [8 empty] | 68.52 | 17.13 | 17.13 | 17.13 | 17.13 | [8 empty] | 68.52 | 5.91 | 5.91 | 5.91 | 5.91 | [8 empty] | 23.64 | [12 empty] | 0 | 406.35 | 6541804.8941 | 513.42 | 1445135.4569 | 80.03 |  |  | 80.03: 1445135.4569
| 80.03 | Contract Admin | 305 | 432 | Various | PCC | [11 empty] | 1.12 | 1.12 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 16.68 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 80.03 | Contract Admin | TBD | PCC | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 26.76 | 6.69 | 6.69 | 6.69 | 6.69 | [8 empty] | 26.76 | 6.68 | 6.68 | 6.68 | 6.68 | [8 empty] | 26.72 | 6.68 | 6.68 | 6.68 | 6.68 | [8 empty] | 26.72 | 6.68 | 6.68 | 6.68 | 6.68 | [8 empty] | 26.72 | 6.68 | 6.68 | 6.68 | 6.68 | [8 empty] | 26.72 | 2.31 | 2.31 | 2.31 | 2.31 | [8 empty] | 9.24 | [12 empty] | 0 | 158.49 | 2551521.2444 | 187.44 | 320243.4449 | 80.03 |  |  | 80.03: 320243.4449
[19 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
[19 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
|  | Subtotals: Group: PCC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.31 | 5.31 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 180.36 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 |  | Subtotals: Group: PCC |  |  | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 146.76 | 34.08 | 34.08 | 34.08 | 34.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.32 | 34.21 | 34.21 | 34.21 | 34.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.84 | 34.21 | 34.21 | 34.21 | 34.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.84 | 34.21 | 34.21 | 34.21 | 34.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.84 | 34.21 | 34.21 | 34.21 | 34.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.84 | 12.78 | 12.78 | 12.78 | 12.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820.41 | 13207732.6274 | 1067.23 | 4105788.2569 |  |  |  |  | 0 | 4105788.2569 | 0 | 0 | 0 | 0 | 0
Group: PB Telamon - Final Design for Utility Relocations and Tunnel (DP1)
1 | 80.02 | Project Managers | 150 | 200 | Various | DP1 | 0.72268 | 0.76537 | 0.59804 | 0.62902 | 0.75616 | 0.9731 | 0.8065 | 0.57743 | 0.50714 | 0.40093 | 0.31789 | 0.31789 | 7.3722 | 0.26583 | 0.2398 | 0.2398 | 0.19732 | 0.202 | 0.20669 | 0.20669 | 0.20669 | 0.26968 | 0.13859 | 0.1339 | 0.1339 | 2.4409 | 0.19097 | 0.19097 | 0.17909 | 0.28978 | 0.28978 | 80.03 | Project Managers |  | DP1 | 0.28041 | 0.33872 | 0.32466 | 0.31529 | 0.31529 | 0.31529 | 0.31529 | 3.3455 | 0.60091 | 0.60091 | 0.48429 | 0.48429 | [8 empty] | 2.1704 | 0.25105 | 0.25105 | 0.25105 | 0 | [8 empty] | 0.75314 | [12 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1285 | 125381.1637 | 16.0821 | 393176.4711 | 80.02 |  |  | 80.02: 393176.4711
2 | 80.02 | Project Controls and Admin | 150 | 320 | Various | DP1 | 0.42591 | 0.45507 | 0.6342 | 0.68106 | 0.96436 | 1.2596 | 1.2388 | 1.2709 | 1.8716 | 1.7558 | 1.5449 | 1.42 | 13.5223 | 1.1389 | 1.269 | 1.5059 | 1.3955 | 4.6754 | 0.87486 | 0.61455 | 0.61455 | 0.62522 | 0.26274 | 0.26378 | 0.26378 | 13.5041 | 0.23149 | 0.23149 | 0.1716 | 0.15519 | 0.57377 | 80.03 | Project Controls and Admin |  | DP1 | 0.16144 | 0.16794 | 0.16794 | 0.17836 | 0.17836 | 0.17627 | 0.18148 | 2.5753 | 0.17939 | 0.17939 | 0.16637 | 0.16637 | [8 empty] | 0.69151 | 0.11431 | 0.11431 | 0.11431 | 0 | [8 empty] | 0.34293 | [12 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2462 | 54915.8958 | 30.6362 | 748995.4496 | 80.02 |  |  | 80.02: 748995.4496
3 | 80.02 | Geo-Engineers | 150 | 320 | Various | DP1 | 1.8992 | 2.721 | 4.471 | 5.2087 | 5.4658 | 4.3917 | 4.173 | 2.9492 | 3.147 | 1.5569 | 0.98835 | 1.1133 | 38.0852 | 0.5224 | 0.22304 | 0.19961 | 0.18118 | 0.24053 | 0.24521 | 0.24521 | 0.13588 | 0.25875 | 0.20815 | 0.20346 | 0.20346 | 2.8669 | 0.38068 | 0.38068 | 0.38006 | 0.72544 | 0.72544 | 80.03 | Geo-Engineers |  | DP1 | 0.71607 | 0.88892 | 0.87486 | 0.86549 | 0.86549 | 0.86549 | 0.86549 | 8.5341 | 1.7294 | 1.7294 | 1.3837 | 1.3837 | [8 empty] | 6.2263 | 0.69233 | 0.69233 | 0.69233 | 0 | [8 empty] | 2.077 | [12 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.245 | 348263.4735 | 57.7894 | 1412838.7273 | 80.02 |  |  | 80.02: 1412838.7273
4 | 80.02 | Civil Engineers | 305 | 431 | Various | DP1 | 1.8352 | 2.1288 | 3.7246 | 3.8912 | 5.3614 | 3.219 | 1.9825 | 1.3495 | 1.3843 | 1.0183 | 0.6866 | 0.76115 | 27.3426 | 0.7372 | 0.70597 | 0.59039 | 0.41286 | 0.4696 | 0.52167 | 0.52167 | 0.51229 | 0.5628 | 0.38839 | 0.33632 | 0.33632 | 6.0955 | 0.38891 | 0.38891 | 0.3837 | 0.80385 | 0.69556 | 80.03 | Civil Engineers |  | DP1 | 0.28322 | 0.28634 | 0.13016 | 0.026031 | 0.026031 | 0.026031 | 0.026031 | 3.4648 | 0.45555 | 0.45555 | 0.032799 | 0.032799 | [8 empty] | 0.97669 | 0.020304 | 0.020304 | 0.020304 | 0 | [8 empty] | 0.060913 | [12 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8415 | 45019.9151 | 37.9404 | 927570.6278 | 80.02 |  |  | 80.02: 927570.6278
5 | 80.02 | Structural Engineers | 305 | 432 | Various | DP1 | 0 | 0 | 0 | 0 | 0 | 1.5316 | 1.6164 | 6.4295 | 6.3993 | 7.8428 | 7.5469 | 6.9794 | 38.3459 | 5.2072 | 1.1515 | 0.47366 | 0.56738 | 1.5827 | 1.1505 | 1.0255 | 1.0255 | 0.94337 | 0.99127 | 0.99231 | 0.15931 | 15.2702 | 0.065599 | 0.053937 | 0.052895 | 0.052895 | 1.0809 | 80.03 | Structural Engineers |  | DP1 | 0.099648 | 0.099648 | 0.099439 | 0.19097 | 0.19097 | 0.18888 | 0.2347 | 2.4105 | 0.64599 | 0.31279 | 1.0625 | 1.0625 | [8 empty] | 3.0838 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.188 | 102388.8044 | 59.1104 | 1445135.4569 | 80.02 |  |  | 80.02: 1445135.4569
6 | 80.02 | Environmental & Hydrology |  |  | Various | DP1 | 0.40192 | 0.45086 | 0.58831 | 0.88923 | 0.97877 | 1.2526 | 1.2943 | 1.187 | 1.3547 | 0.93192 | 0.72471 | 0.62058 | 10.6749 | 0.22491 | 0.027072 | 0.027072 | 0.018742 | 0.020825 | 0.022908 | 0.022908 | 0.022908 | 0.043732 | 0.03332 | 0.031237 | 0.031237 | 0.52687 | 0.052062 | 0.052062 | 0.052062 | 0.089547 | 0.089547 | 80.03 | Environmental & Hydrology |  | DP1 | 0.085382 | 0.10412 | 0.097877 | 0.093713 | 0.093713 | 0.093713 | 0.093713 | 0.99752 | 0.18743 | 0.18743 | 0.14994 | 0.14994 | [8 empty] | 0.67473 | 0.07497 | 0.07497 | 0.07497 | 0 | [8 empty] | 0.22491 | [12 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5619 | 38184.8305 | 13.0989 | 320243.4449 | 80.02 |  |  | 80.02: 320243.4449
7 | 80.02 | Architectural & Landscaping |  |  | Various | DP1 | 0.057269 | 0.057269 | 0.057269 | 0.11454 | 0.11454 | 0.17181 | 0.17181 | 0.17181 | 0.17701 | 0.067681 | 0.015619 | 0.015619 | 1.1922 | 0.0052062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0031237 | 0.0031237 | 0.0031237 | 0.0031237 | 0.017701 | 0.0062475 | 0.0062475 | 0.0062475 | 0.012495 | 0.012495 | 80.03 | Architectural & Landscaping |  | DP1 | 0.012495 | 0.015619 | 0.015619 | 0.015619 | 0.015619 | 0.015619 | 0.015619 | 0.14994 | 0.031237 | 0.031237 | 0.02499 | 0.02499 | [8 empty] | 0.11245 | 0.012495 | 0.012495 | 0.012495 | 0 | [8 empty] | 0.037485 | [12 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25615 | 6262.3122 | 1.5098 | 36912.0028 | 80.02 |  |  | 80.02: 36912.0028
8 | 80.02 | CAD |  |  | Various | DP1 | 0.30717 | 0.35402 | 0.44774 | 0.70805 | 0.70805 | 0.97877 | 1.0829 | 1.0173 | 1.0079 | 0.46856 | 0.10412 | 0 | 7.1846 | 0 | 0 | 0 | 0.00833 | 0.010412 | 0.012495 | 0.012495 | 0.012495 | 0.022908 | 0.022908 | 0.020825 | 0.020825 | 0.14369 | 0.031237 | 0.031237 | 0.031237 | 0.047898 | 0.047898 | 80.03 | CAD |  | DP1 | 0.043732 | 0.052062 | 0.045815 | 0.04165 | 0.04165 | 0.04165 | 0.04165 | 0.49772 | 0.0833 | 0.0833 | 0.06664 | 0.06664 | [8 empty] | 0.29988 | 0.03332 | 0.03332 | 0.03332 | 0 | [8 empty] | 0.09996 | [12 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70805 | 17310.4565 | 8.2259 | 201106.7738 | 80.02 |  |  | 80.02: 201106.7738
9 | [5 empty] | DP1 | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
10 | [5 empty] | DP1 | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
|  | Subtotals - Group: PB Telamon - Final Design for Utility Relocations and Tunnel (DP1) |  |  |  |  | 5.6493 | 6.9324 | 10.5211 | 12.1218 | 14.3491 | 13.7782 | 12.3663 | 14.9526 | 15.849 | 14.0429 | 11.9291 | 11.2279 | 143.7199 | 8.1016 | 3.6164 | 3.0364 | 2.7813 | 7.2015 | 3.0343 | 2.649 | 2.5303 | 2.7296 | 2.0485 | 1.985 | 1.152 | 40.8659 | 1.3472 | 1.3355 | 1.2569 | 2.1771 | 3.5154 |  | Subtotals - Group: PB Telamon - Final Design for Utility Relocations and Tunnel (DP1) |  |  | 1.6824 | 1.9534 | 1.7564 | 1.7271 | 1.7271 | 1.7229 | 1.774 | 21.9754 | 3.9132 | 3.58 | 3.3712 | 3.3712 | [8 empty] | 14.2357 | 1.1988 | 1.1988 | 1.1988 | 0 | [8 empty] | 3.5963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.1753 | 737726.8516 | 224.3931 | 5485978.9542 |  |  |  |  | 5485978.9542 | 0 | 0 | 0 | 0 | 0 | 0
Group: CSDG - Final Design for Stations (DP2)
1 | 80.02 | Principal in Charge | 150 | 200 | R Hornbuckle | DP2 |  |  |  | 0.06 | 0.126 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 1.593 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | [5 empty] | 1.407 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 3 | 65082.9104 | 80.02 |  |  | 80.02: 65082.9104
2 | 80.02 | Project Manager | 150 | 320 | N Munfah | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 7.4609 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 6.5898 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 14.0507 | 304820.1498 | 80.02 |  |  | 80.02: 304820.1498
3 | 80.02 | Deputy Project Manager | 150 | 320 | A Read | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 7.4609 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 6.5898 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 14.0507 | 304820.1498 | 80.02 |  |  | 80.02: 304820.1498
4 | 80.02 | Package Manager - UMS | 305 | 431 |  | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 7.4609 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 6.5898 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 14.0507 | 304820.1498 | 80.02 |  |  | 80.02: 304820.1498
5 | 80.02 | Package Manager - CTS | 305 | 432 |  | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 7.4609 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 6.5898 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 14.0507 | 304820.1498 | 80.02 |  |  | 80.02: 304820.1498
6 | 80.02 | Package Manager - MOS |  |  |  | DP2 |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 7.4609 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | [5 empty] | 6.5898 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 14.0507 | 304820.1498 | 80.02 |  |  | 80.02: 304820.1498
| 80.02 | Manager/Sr Specialist |  |  | Various | DP2 |  |  |  | 1.5838 | 3.3259 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 42.0475 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | [5 empty] | 37.1378 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 79.1853 | 1717869.9289 | 80.02 |  |  | 80.02: 1717869.9289
| 80.02 | Senior Technical |  |  | Various | DP2 |  |  |  | 7.6935 | 16.1564 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 204.2623 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | [5 empty] | 180.4124 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 384.6747 | 8345249.6809 | 80.02 |  |  | 80.02: 8345249.6809
| 80.02 | Staff Technical |  |  | Various | DP2 |  |  |  | 5.8188 | 12.2194 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 154.4878 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | [5 empty] | 136.4496 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 290.9374 | 6311684.2478 | 80.02 |  |  | 80.02: 6311684.2478
| 80.02 | Technician |  |  | Various | DP2 |  |  |  | 4.492 | 9.4332 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 119.2626 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | [5 empty] | 105.3374 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 224.6 | 4872540.5605 | 80.02 |  |  | 80.02: 4872540.5605
| 80.02 | Support Staff |  |  | Various | DP2 |  |  |  | 0.4595 | 0.965 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 12.1996 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | [5 empty] | 10.7751 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 22.9747 | 498420.114 | 80.02 |  |  | 80.02: 498420.114
| 80.02 | Trainee |  |  | Various | DP2 |  |  |  | 2.31 | 4.851 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 61.3305 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | [5 empty] | 54.1695 | [5 empty] | 80.02 |  |  | DP2 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 115.5 | 2505692.0513 | 80.02 |  |  | 80.02: 2505692.0513
7 | 80.02 | Support During Construction |  |  | Various | DP2 | [12 empty] | 0 | [10 empty] | 1.125 | 1.125 | 2.25 | 1.125 | 1.125 | 1.125 | 1.125 | 7.7813 | 80.03 | Support During Construction |  | DP2 | 7.7813 | 7.7813 | 7.7813 | 6.6563 | 6.6563 | 11.0938 | 11.0938 | 71.1254 | 25.8856 | 22.187 | 21 | 21 | [8 empty] | 90.0726 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | [8 empty] | 79.8756 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | [8 empty] | 79.8756 | 19.9689 | 19.9689 | 19.9689 | [9 empty] | 59.9067 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 368.5746 | 7995969.2255 | 383.1059 | 8311215.6576 | 80.02 |  |  | 80.02: 8311215.6576
8 | [18 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
9 | [18 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
10 | [18 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
|  | Subtotals - Group: Central Subway Design Group (CSDG) - Final Design for Stations (DP2) |  |  |  |  | 0 | 0 | 0 | 23.8226 | 50.0274 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 632.4878 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 0 | 0 | 0 | 1.125 | 1.125 | 560.8878 | 1.125 | 1.125 | 1.125 | 1.125 | 7.7813 |  | Subtotals - Group: Central Subway Design Group (CSDG) - Final Design for Stations (DP2) |  |  | 7.7813 | 7.7813 | 7.7813 | 6.6563 | 6.6563 | 11.0938 | 11.0938 | 71.1254 | 25.8856 | 22.187 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.0726 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | [8 empty] | 79.8756 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.8756 | 19.9689 | 19.9689 | 19.9689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.9067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.5746 | 7995969.2255 | 1574.2315 | 34151855.9007 |  |  |  |  | 34151855.9007 | 0 | 0 | 0 | 0 | 0 | 0
Group: HNTB-B&C Transit - Final Design for Surface, Trackway & Systems (DP3)
1 | 80.02 | Project Managers | 150 | 200 | Various | DP3 |  |  |  |  | 0.79768 | 0.79768 | 0.79768 | 0.79768 | 0.79768 | 1.5954 | 1.5954 | 1.5954 | 8.7744 | 1.5954 | 1.5954 | 1.5954 | 1.5954 | 1.5954 | 0.79768 | 0.79768 | 0.79768 | 0.79768 | 0.79768 | 0.79768 | 0.79768 | 13.5605 | 0.79768 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 80.03 | Project Managers |  | DP3 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 7.395 | 1.0676 | 1.0676 | 1.0676 | 1.0676 | [8 empty] | 4.2703 | 1.0676 | 1.0676 | 1.0676 | 1.0676 | [8 empty] | 4.2703 | 2.0097 | 2.0097 | 2.0097 | 2.0097 | [8 empty] | 8.0388 | 2.0097 | 2.0097 | 2.0097 | 2.0097 | [8 empty] | 8.0388 | 2.0097 | 2.0097 | 2.0097 | 2.0097 | [8 empty] | 8.0388 | 1.0992 | 1.0992 | 1.0992 | 1.0992 | [8 empty] | 4.3966 | [12 empty] | 0 | 41.2518 | 1038319.5937 | 66.7834 | 1680957.6661 | 80.02 |  |  | 80.02: 1680957.6661
2 | 80.02 | Integration Coord & Quality Control | 150 | 320 | Various | DP3 |  |  |  |  | 1.4902 | 1.4902 | 1.4902 | 1.4902 | 1.4902 | 2.9804 | 2.9804 | 2.9804 | 16.3923 | 2.9804 | 2.9804 | 2.9804 | 2.9804 | 2.9804 | 1.4902 | 1.4902 | 1.4902 | 1.4902 | 1.4902 | 1.4902 | 1.4902 | 25.3336 | 1.4902 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 80.03 | Integration Coord & Quality Control |  | DP3 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 13.8153 | 1.9944 | 1.9944 | 1.9944 | 1.9944 | [8 empty] | 7.9777 | 1.9944 | 1.9944 | 1.9944 | 1.9944 | [8 empty] | 7.9777 | 1.9944 | 1.9944 | 1.9944 | 1.9944 | [8 empty] | 7.9777 | 1.9944 | 1.9944 | 1.9944 | 1.9944 | [8 empty] | 7.9777 | 1.9944 | 1.9944 | 1.9944 | 1.9944 | [8 empty] | 7.9777 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 47.7316 | 1201416.8885 | 95.4295 | 2401987.7088 | 80.02 |  |  | 80.02: 2401987.7088
3 | 80.02 | Project Controls & Admin | 150 | 320 | Various | DP3 |  |  |  |  | 1.5993 | 1.5993 | 1.5993 | 1.5993 | 1.5993 | 3.1986 | 3.1986 | 3.1986 | 17.5921 | 3.1986 | 3.1986 | 3.1986 | 3.1986 | 3.1986 | 1.5993 | 1.5993 | 1.5993 | 1.5993 | 1.5993 | 1.5993 | 1.5993 | 27.1878 | 1.5993 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 80.03 | Project Controls & Admin |  | DP3 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 14.8264 | 2.1404 | 2.1404 | 2.1404 | 2.1404 | [8 empty] | 8.5616 | 2.1404 | 2.1404 | 2.1404 | 2.1404 | [8 empty] | 8.5616 | 3.756 | 3.756 | 3.756 | 3.756 | [8 empty] | 15.024 | 3.756 | 3.756 | 3.756 | 3.756 | [8 empty] | 15.024 | 3.756 | 3.756 | 3.756 | 3.756 | [8 empty] | 15.024 | 1.8849 | 1.8849 | 1.8849 | 1.8849 | [8 empty] | 7.5394 | [12 empty] | 0 | 78.1517 | 1967101.2506 | 129.3408 | 3255545.0138 | 80.02 |  |  | 80.02: 3255545.0138
4 | 80.02 | Civil/Track & Utilities | 305 | 431 | Various | DP3 |  |  |  |  | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 2.16 | 2.16 | 2.16 | 11.8802 | 2.16 | 2.16 | 2.16 | 2.16 | 2.16 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 18.3603 | 1.08 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 80.03 | Civil/Track & Utilities |  | DP3 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 10.0125 | 1.4454 | 1.4454 | 1.4454 | 1.4454 | [8 empty] | 5.7818 | 1.4454 | 1.4454 | 1.4454 | 1.4454 | [8 empty] | 5.7818 | 1.4454 | 1.4454 | 1.4454 | 1.4454 | [8 empty] | 5.7818 | 1.4454 | 1.4454 | 1.4454 | 1.4454 | [8 empty] | 5.7818 | 1.4454 | 1.4454 | 1.4454 | 1.4454 | [8 empty] | 5.7818 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 34.5931 | 870717.0445 | 69.1618 | 1740820.9079 | 80.02 |  |  | 80.02: 1740820.9079
5 | 80.02 | Structural | 305 | 432 | Various | DP3 |  |  |  |  | 0.14788 | 0.14788 | 0.14788 | 0.14788 | 0.14788 | 0.29577 | 0.29577 | 0.29577 | 1.6267 | 0.29577 | 0.29577 | 0.29577 | 0.29577 | 0.29577 | 0.14788 | 0.14788 | 0.14788 | 0.14788 | 0.14788 | 0.14788 | 0.14788 | 2.514 | 0.14788 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 80.03 | Structural |  | DP3 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 1.371 | 0.19792 | 0.19792 | 0.19792 | 0.19792 | [8 empty] | 0.79168 | 0.19792 | 0.19792 | 0.19792 | 0.19792 | [8 empty] | 0.79168 | 0.19792 | 0.19792 | 0.19792 | 0.19792 | [8 empty] | 0.79168 | 0.19792 | 0.19792 | 0.19792 | 0.19792 | [8 empty] | 0.79168 | 0.19792 | 0.19792 | 0.19792 | 0.19792 | [8 empty] | 0.79168 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 4.7367 | 119224.5767 | 9.4701 | 238365.1925 | 80.02 |  |  | 80.02: 238365.1925
6 | 80.02 | Environmental and Sustainability | 275 | 420 | Various | DP3 |  |  |  |  | 0.16461 | 0.16461 | 0.16461 | 0.16461 | 0.16461 | 0.32922 | 0.32922 | 0.32922 | 1.8107 | 0.32922 | 0.32922 | 0.32922 | 0.32922 | 0.32922 | 0.16461 | 0.16461 | 0.16461 | 0.16461 | 0.16461 | 0.16461 | 0.16461 | 2.7984 | 0.16461 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 80.03 | Environmental and Sustainability |  | DP3 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 1.5261 | 0.22031 | 0.22031 | 0.22031 | 0.22031 | [8 empty] | 0.88123 | 0.22031 | 0.22031 | 0.22031 | 0.22031 | [8 empty] | 0.88123 | 0.22031 | 0.22031 | 0.22031 | 0.22031 | [8 empty] | 0.88123 | 0.22031 | 0.22031 | 0.22031 | 0.22031 | [8 empty] | 0.88123 | 0.22031 | 0.22031 | 0.22031 | 0.22031 | [8 empty] | 0.88123 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 5.2725 | 132711.5198 | 10.5414 | 265329.5808 | 80.02 |  |  | 80.02: 265329.5808
7 | 80.02 | Controls & Comms | 275 | 420 | Various | DP3 |  |  |  |  | 0.63637 | 0.63637 | 0.63637 | 0.63637 | 0.63637 | 1.2727 | 1.2727 | 1.2727 | 7 | 1.2727 | 1.2727 | 1.2727 | 1.2727 | 1.2727 | 0.63637 | 0.63637 | 0.63637 | 0.63637 | 0.63637 | 0.63637 | 0.63637 | 10.8182 | 0.63637 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 80.03 | Controls & Comms |  | DP3 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 5.8996 | 0.85168 | 0.85168 | 0.85168 | 0.85168 | [8 empty] | 3.4067 | 0.85168 | 0.85168 | 0.85168 | 0.85168 | [8 empty] | 3.4067 | 0.85168 | 0.85168 | 0.85168 | 0.85168 | [8 empty] | 3.4067 | 0.85168 | 0.85168 | 0.85168 | 0.85168 | [8 empty] | 3.4067 | 0.85168 | 0.85168 | 0.85168 | 0.85168 | [8 empty] | 3.4067 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 20.3829 | 513043.3143 | 40.7514 | 1025725.3305 | 80.02 |  |  | 80.02: 1025725.3305
8 | 80.02 | Train Control |  |  | Various | DP3 |  |  |  |  | 0.6444 | 0.6444 | 0.6444 | 0.6444 | 0.6444 | 1.2888 | 1.2888 | 1.2888 | 7.0884 | 1.2888 | 1.2888 | 1.2888 | 1.2888 | 1.2888 | 0.6444 | 0.6444 | 0.6444 | 0.6444 | 0.6444 | 0.6444 | 0.6444 | 10.9548 | 0.6444 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 80.03 | Train Control |  | DP3 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 5.974 | 0.86243 | 0.86243 | 0.86243 | 0.86243 | [8 empty] | 3.4497 | 0.86243 | 0.86243 | 0.86243 | 0.86243 | [8 empty] | 3.4497 | 0.86243 | 0.86243 | 0.86243 | 0.86243 | [8 empty] | 3.4497 | 0.86243 | 0.86243 | 0.86243 | 0.86243 | [8 empty] | 3.4497 | 0.86243 | 0.86243 | 0.86243 | 0.86243 | [8 empty] | 3.4497 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 20.6401 | 519517.047 | 41.2657 | 1038668.2369 | 80.02 |  |  | 80.02: 1038668.2369
9 | 80.02 | OCS |  |  | Various | DP3 |  |  |  |  | 0.45971 | 0.45971 | 0.45971 | 0.45971 | 0.45971 | 0.91942 | 0.91942 | 0.91942 | 5.0568 | 0.91942 | 0.91942 | 0.91942 | 0.91942 | 0.91942 | 0.45971 | 0.45971 | 0.45971 | 0.45971 | 0.45971 | 0.45971 | 0.45971 | 7.8151 | 0.45971 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 80.03 | OCS |  | DP3 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 4.2618 | 0.61525 | 0.61525 | 0.61525 | 0.61525 | [8 empty] | 2.461 | 0.61525 | 0.61525 | 0.61525 | 0.61525 | [8 empty] | 2.461 | 0.61525 | 0.61525 | 0.61525 | 0.61525 | [8 empty] | 2.461 | 0.61525 | 0.61525 | 0.61525 | 0.61525 | [8 empty] | 2.461 | 0.61525 | 0.61525 | 0.61525 | 0.61525 | [8 empty] | 2.461 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 14.7246 | 370621.1955 | 29.4387 | 740981.3902 | 80.02 |  |  | 80.02: 740981.3902
10 | 80.02 | Corrosion Control |  |  | Various | DP3 |  |  |  |  | 0.043495 | 0.043495 | 0.043495 | 0.043495 | 0.043495 | 0.08699 | 0.08699 | 0.08699 | 0.47845 | 0.08699 | 0.08699 | 0.08699 | 0.08699 | 0.08699 | 0.043495 | 0.043495 | 0.043495 | 0.043495 | 0.043495 | 0.043495 | 0.043495 | 0.73942 | 0.043495 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 80.03 | Corrosion Control |  | DP3 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.40323 | 0.058212 | 0.058212 | 0.058212 | 0.058212 | [8 empty] | 0.23285 | 0.058212 | 0.058212 | 0.058212 | 0.058212 | [8 empty] | 0.23285 | 0.058212 | 0.058212 | 0.058212 | 0.058212 | [8 empty] | 0.23285 | 0.058212 | 0.058212 | 0.058212 | 0.058212 | [8 empty] | 0.23285 | 0.058212 | 0.058212 | 0.058212 | 0.058212 | [8 empty] | 0.23285 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 1.3932 | 35066.052 | 2.7853 | 70107.4096 | 80.02 |  |  | 80.02: 70107.4096
11 | 80.02 | Fare Collection | 150 | 320 | Various | DP3 |  |  |  |  | 0.026766 | 0.026766 | 0.026766 | 0.026766 | 0.026766 | 0.053533 | 0.053533 | 0.053533 | 0.29443 | 0.053533 | 0.053533 | 0.053533 | 0.053533 | 0.053533 | 0.026766 | 0.026766 | 0.026766 | 0.026766 | 0.026766 | 0.026766 | 0.026766 | 0.45503 | 0.026766 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 80.03 | Fare Collection |  | DP3 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.24814 | 0.035823 | 0.035823 | 0.035823 | 0.035823 | [8 empty] | 0.14329 | 0.035823 | 0.035823 | 0.035823 | 0.035823 | [8 empty] | 0.14329 | 0.035823 | 0.035823 | 0.035823 | 0.035823 | [8 empty] | 0.14329 | 0.035823 | 0.035823 | 0.035823 | 0.035823 | [8 empty] | 0.14329 | 0.035823 | 0.035823 | 0.035823 | 0.035823 | [8 empty] | 0.14329 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 0.85733 | 21579.1089 | 1.714 | 43143.0213 | 80.02 |  |  | 80.02: 43143.0213
12 | 80.02 | Systems Safety | 305 | 431 | Various | DP3 |  |  |  |  | 0.23956 | 0.23956 | 0.23956 | 0.23956 | 0.23956 | 0.47912 | 0.47912 | 0.47912 | 2.6351 | 0.47912 | 0.47912 | 0.47912 | 0.47912 | 0.47912 | 0.23956 | 0.23956 | 0.23956 | 0.23956 | 0.23956 | 0.23956 | 0.23956 | 4.0725 | 0.23956 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 80.03 | Systems Safety |  | DP3 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 2.2209 | 0.32061 | 0.32061 | 0.32061 | 0.32061 | [8 empty] | 1.2824 | 0.32061 | 0.32061 | 0.32061 | 0.32061 | [8 empty] | 1.2824 | 0.32061 | 0.32061 | 0.32061 | 0.32061 | [8 empty] | 1.2824 | 0.32061 | 0.32061 | 0.32061 | 0.32061 | [8 empty] | 1.2824 | 0.32061 | 0.32061 | 0.32061 | 0.32061 | [8 empty] | 1.2824 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 7.6731 | 193133.0247 | 15.3407 | 386130.0403 | 80.02 |  |  | 80.02: 386130.0403
13 | 80.02 | Elect/Mech | 305 | 432 | Various | DP3 |  |  |  |  | 0.46506 | 0.46506 | 0.46506 | 0.46506 | 0.46506 | 0.93013 | 0.93013 | 0.93013 | 5.1157 | 0.93013 | 0.93013 | 0.93013 | 0.93013 | 0.93013 | 0.46506 | 0.46506 | 0.46506 | 0.46506 | 0.46506 | 0.46506 | 0.46506 | 7.9061 | 0.46506 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 80.03 | Elect/Mech |  | DP3 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 4.3115 | 0.62242 | 0.62242 | 0.62242 | 0.62242 | [8 empty] | 2.4897 | 0.62242 | 0.62242 | 0.62242 | 0.62242 | [8 empty] | 2.4897 | 0.62242 | 0.62242 | 0.62242 | 0.62242 | [8 empty] | 2.4897 | 0.62242 | 0.62242 | 0.62242 | 0.62242 | [8 empty] | 2.4897 | 0.62242 | 0.62242 | 0.62242 | 0.62242 | [8 empty] | 2.4897 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 14.896 | 374937.0173 | 29.7816 | 749609.9944 | 80.02 |  |  | 80.02: 749609.9944
14 | 80.02 | CADD | 275 | 420 | Various | DP3 |  |  |  |  | 0.74075 | 0.74075 | 0.74075 | 0.74075 | 0.74075 | 1.4815 | 1.4815 | 1.4815 | 8.1482 | 1.4815 | 1.4815 | 1.4815 | 1.4815 | 1.4815 | 0.74075 | 0.74075 | 0.74075 | 0.74075 | 0.74075 | 0.74075 | 0.74075 | 12.5927 | 0.74075 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 80.03 | CADD |  | DP3 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 6.8672 | 0.99138 | 0.99138 | 0.99138 | 0.99138 | [8 empty] | 3.9655 | 0.99138 | 0.99138 | 0.99138 | 0.99138 | [8 empty] | 3.9655 | 0.99138 | 0.99138 | 0.99138 | 0.99138 | [8 empty] | 3.9655 | 0.99138 | 0.99138 | 0.99138 | 0.99138 | [8 empty] | 3.9655 | 0.99138 | 0.99138 | 0.99138 | 0.99138 | [8 empty] | 3.9655 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 23.7262 | 597195.1375 | 47.4357 | 1193969.715 | 80.02 |  |  | 80.02: 1193969.715
15 | 80.02 | Architectural | 275 | 420 | Various | DP3 |  |  |  |  | 0.018736 | 0.018736 | 0.018736 | 0.018736 | 0.018736 | 0.037473 | 0.037473 | 0.037473 | 0.2061 | 0.037473 | 0.037473 | 0.037473 | 0.037473 | 0.037473 | 0.018736 | 0.018736 | 0.018736 | 0.018736 | 0.018736 | 0.018736 | 0.018736 | 0.31852 | 0.018736 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 80.03 | Architectural |  | DP3 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.1737 | 0.025076 | 0.025076 | 0.025076 | 0.025076 | [8 empty] | 0.1003 | 0.025076 | 0.025076 | 0.025076 | 0.025076 | [8 empty] | 0.1003 | 0.025076 | 0.025076 | 0.025076 | 0.025076 | [8 empty] | 0.1003 | 0.025076 | 0.025076 | 0.025076 | 0.025076 | [8 empty] | 0.1003 | 0.025076 | 0.025076 | 0.025076 | 0.025076 | [8 empty] | 0.1003 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 0.60013 | 15105.3762 | 1.1998 | 30200.1149 | 80.02 |  |  | 80.02: 30200.1149
16 | 80.02 | Traffic |  |  | Various | DP3 |  |  |  |  | 0.013383 | 0.013383 | 0.013383 | 0.013383 | 0.013383 | 0.026766 | 0.026766 | 0.026766 | 0.14721 | 0.026766 | 0.026766 | 0.026766 | 0.026766 | 0.026766 | 0.013383 | 0.013383 | 0.013383 | 0.013383 | 0.013383 | 0.013383 | 0.013383 | 0.22751 | 0.013383 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 80.03 | Traffic |  | DP3 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.12407 | 0.017911 | 0.017911 | 0.017911 | 0.017911 | [8 empty] | 0.071645 | 0.017911 | 0.017911 | 0.017911 | 0.017911 | [8 empty] | 0.071645 | 0.017911 | 0.017911 | 0.017911 | 0.017911 | [8 empty] | 0.071645 | 0.017911 | 0.017911 | 0.017911 | 0.017911 | [8 empty] | 0.071645 | 0.017911 | 0.017911 | 0.017911 | 0.017911 | [8 empty] | 0.071645 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [12 empty] | 0 | 0.42866 | 10789.5545 | 0.85702 | 21571.5106 | 80.02 |  |  | 80.02: 21571.5106
|  | Subtotals - Group: HNTB-B&C Transit - Final Design for Surface, Trackway & Systems (DP3) |  |  |  |  | 0 | 0 | 0 | 0 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 17.1358 | 17.1358 | 17.1358 | 94.247 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 145.6545 | 8.5679 | 6.442 | 6.442 | 6.442 | 6.442 |  | Subtotals - Group: HNTB-B&C Transit - Final Design for Surface, Trackway & Systems (DP3) |  |  | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 79.4303 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.8673 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | [8 empty] | 45.8673 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.0982 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.0982 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.0982 | 2.984 | 2.984 | 2.984 | 2.984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.0596 | 7980477.7017 | 591.2971 | 14883112.8334 | 2480420.2561 |  |  |  | 14883112.8334 | 0 | 0 | 0 | 0 | 0 | 0
Group: Department of Public Works (DPW)
| 80.02 | BOE Coordination |  |  | Lesley Wong | EHY | 0.53 | 0.56 | 0.56 | 1.11 | 1.15 | 1.23 | 1.3 | 1.22 | 1.01 | 0.98 | 0.98 | 0.77 | 11.4 | 0.68 | 0.67 | 0.77 | 0.77 | 0.77 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 9.75 | 0.55 | 0.36 | 0.36 | 0.22 | 0.47 | 80.02 | BOE Coordination |  | EHY | 0.35 | 0.35 | 0.49 | 0.49 | 0.56 | 0.56 | 0.56 | 5.32 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 3.36 | 81521.664 | 26.47 | 642225.728 | 80.02 | 756830.24 |  | 80.02: 756830.24
| 80.02 | Sewer Design & Hydraulic Studies |  |  | Yuan Wu | EHY | 0.28 | 0.2 | 0.1 | 0.25 | 0.18 | 0.38 | 0.3 | 0.22 | 0.22 | 0.2 | 0.2 | 0.2 | 2.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.02 | Sewer Design & Hydraulic Studies |  | EHY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 2.73 | 45231.8704 | 80.02 | 78056.16 |  | 80.02: 78056.16
| 80.02 | Sewer Design |  |  | Kevin Day | EHY | 0.93 | 0.91 | 0.83 | 1.06 | 1.08 | 1.24 | 1.19 | 1.2 | 0.57 | 0.52 | 0.57 | 0.32 | 10.42 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 0.61 | 7.27 | 0.38 | 0.25 | 0.25 | 0.21 | 0.23 | 80.02 | Sewer Design |  | EHY | 0.23 | 0.03 | 0.04 | 0.04 | 0.06 | 0.06 | 0.06 | 1.84 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.52 | 9089.1008 | 19.53 | 341365.6512 | 80.02 | 558401.76 |  | 80.02: 558401.76
| 80.02 | Sewer Design |  |  | Cheung/Fong/Helmuth/Others | EHY | 0.33 | 0.33 | 0.51 | 0.7 | 0.67 | 0.66 | 0.82 | 0.89 | 0.46 | 0.52 | 0.48 | 0.24 | 6.61 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 4.08 | 0.18 | 0.18 | 0.18 | 0.16 | 0.16 | 80.02 | Sewer Design |  | EHY | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1.02 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.16 | 3328 | 11.71 | 243568 | 80.02 | 334812.32 |  | 80.02: 334812.32
| 80.02 | AWSS Design |  |  | Mike Smith | EME | 0.32 | 0.26 | 0.26 | 0.59 | 0.59 | 0.67 | 0.59 | 0.65 | 0.39 | 0.39 | 0.39 | 0.34 | 5.44 | 0.34 | 0.35 | 0.35 | 0.35 | 0.35 | 0.36 | 0.35 | 0.35 | 0.36 | 0.35 | 0.35 | 0.35 | 4.21 | 0.22 | 0.15 | 0.15 | 0.08 | 0.11 | 80.02 | AWSS Design |  | EME | 0.04 | 0.04 | 0.06 | 0.06 | 0.08 | 0.08 | 0.09 | 1.16 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.45 | 9130.86 | 10.81 | 219343.548 | 80.02 | 309079.52 |  | 80.02: 309079.52
| 80.02 | AWSS Design |  |  | Lee/Wong/Others | EME | 0.09 | 0.09 | 0.09 | 0.23 | 0.17 | 0.23 | 0.31 | 0.39 | 0.27 | 0.6 | 0.4 | 0.2 | 3.07 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 2.52 | 0.12 | 0.12 | 0.12 | 0.05 | 0.05 | 80.02 | AWSS Design |  | EME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 6.05 | 91960 | 80.02 | 172981.6 |  | 80.02: 172981.6
| 80.02 | Roadway Renovation Design |  |  | Steve O'Sullivan | ESH | 1.25 | 1.25 | 1.15 | 1.61 | 1.51 | 1.71 | 1.7 | 1.7 | 1.33 | 1.3 | 1.3 | 0.8 | 16.61 | 0.84 | 0.84 | 0.84 | 0.84 | 0.84 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 | 10.78 | 0.75 | 0.55 | 0.55 | 0.35 | 0.43 | 80.02 | Roadway Renovation Design |  | ESH | 0.18 | 0.18 | 0.24 | 0.24 | 0.31 | 0.31 | 0.31 | 4.4 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 1.77 | 42382.9594 | 31.79 | 761217.1077 | 80.02 | 908939.68 |  | 80.02: 908939.68
| 80.02 | Roadway Renovation Design |  |  | Yu/Hernandez/Others | ESH | 0.23 | 0.15 | 0.55 | 0.62 | 0.62 | 0.82 | 1.01 | 0.96 | 0.71 | 0.71 | 0.71 | 0.46 | 7.55 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46 | 5.52 | 0.31 | 0.31 | 0.31 | 0.23 | 0.23 | 80.02 | Roadway Renovation Design |  | ESH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 14.46 | 219792 | 80.02 | 413440.32 |  | 80.02: 413440.32
| 80.02 | Structural Sewer Design |  |  | Joseph Elek | EST | 0.08 | 0 | 0 | 0.08 | 0 | 0.32 | 0.25 | 0.25 | 0.2 | 0.23 | 0.25 | 0.25 | 1.91 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 2.04 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 80.02 | Structural Sewer Design |  | EST | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.88 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.03 | 588.774 | 4.83 | 94792.614 | 80.02 | 138099.36 |  | 80.02: 138099.36
| 80.02 | Structural Sewer Design |  |  | Others | EST | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 0.07 | 0.15 | 0.15 | 0.15 | 0.15 | 0.74 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 1.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 80.02 | Structural Sewer Design |  | EST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 3.29 | 50008 | 80.02 | 94067.68 |  | 80.02: 94067.68
| 80.02 | Specs/Site Ass'm't & Remediation |  |  | Carmen Ynami | BCM/ | 0.35 | 0.37 | 0.37 | 0.51 | 0.5 | 0.55 | 0.55 | 0.58 | 0.53 | 0.53 | 0.53 | 0.43 | 5.8 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 1.34 | 1.34 | 1.34 | 1.35 | 1.35 | 1.35 | 1.35 | 13.02 | 1.25 | 0.7 | 0.7 | 0.66 | 1.62 | 80.02 | Specs/Site Ass'm't & Remediation |  | BCM/ | 1.58 | 1.58 | 2.12 | 2.12 | 2.27 | 2.27 | 2.27 | 19.14 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 14.21 | 279806.268 | 37.96 | 747462.768 | 80.02 | 1085352.32 |  | 80.02: 1085352.32
| 80.02 | Specs/Site Ass'm't & Remediation |  |  | Others | BCM | 0.12 | 0.12 | 0.12 | 0.2 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.11 | 1.51 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.08 | 0 | 0 | 0 | 0 | 80.02 | Specs/Site Ass'm't & Remediation |  | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 1.67 | 22712 | 80.02 | 47748.64 |  | 80.02: 47748.64
| 80.02 | Force Main Design |  |  | Elliot Szkup | EME | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.35 | 0.35 | 0.35 | 0.35 | 0.44 | 0.05 | 2.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.67 | 0.06 | 0.06 | 0.06 | 0.01 | 0.01 | 80.02 | Force Main Design |  | EME | 0.01 | 0.01 | 0.02 | 0.02 | 0.01 | 0.01 | 0.02 | 0.3 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.1 | 1408 | 3.01 | 42380.8 | 80.02 | 86061.92 |  | 80.02: 86061.92
| 80.02 | PUC Sewer Operations (TV Tape) |  |  | Others | PUC | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.4 | 0.3 | 0.4 | 0.5 |  | 2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 80.02 | PUC Sewer Operations (TV Tape) |  | PUC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 2 | 32000 | 80.02 | 57184 | 160 | 80.02: 57184
| 80.02 | AWSS Cistern Design |  |  | Frank Piruzmand | EST |  |  |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.99 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 1.32 |  |  |  |  | 0.01 | 80.02 | AWSS Cistern Design |  | EST | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0.07 | 1366.4 | 2.39 | 46652.8 | 80.02 | 68334.88 | 178.7 | 80.02: 68334.88
[114 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0
| 80.04 | Resident Engineer (1250) |  |  | Mike Acosta | BCM | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [5 empty] | 80.04 | Resident Engineer (1250) |  | BCM | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 15 | 276000 | 80.04 | 360000 |  | 80.04: 360000
| 80.04 | Inspector (1250) |  |  | Gabriel Fernandez | BCM | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [5 empty] | 80.04 | Inspector (1250) |  | BCM | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 15 | 240000 | 80.04 | 360000 |  | 80.04: 360000
| 80.04 | Inspector (1250) |  |  | Terrance Huey | BCM | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [5 empty] | 80.04 | Inspector (1250) |  | BCM | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 13 | 176800 | 80.04 | 312000 |  | 80.04: 312000
| 80.04 | Office Engineer Engineer (1250) |  |  | Peter Chin | BCM | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 1 | 1 | 1 | [8 empty] | 4 | [5 empty] | 80.04 | Office Engineer Engineer (1250) |  | BCM | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 15 | 228000 | 80.04 | 360000 |  | 80.04: 360000
| 80.04 | [17 empty] | 0 | [18 empty] | 80.04 | [23 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 80.04: 0
| 80.04 | Resident Engineer (1251) |  |  | TBD | BCM | [12 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.04 | Resident Engineer (1251) |  | BCM | 1 | [6 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 1 | 18400 | 18 | 331200 | 80.04 | 432000 |  | 80.04: 432000
| 80.04 | Inspector (1251) |  |  | TBD | BCM | [12 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.04 | Inspector (1251) |  | BCM | 1 | [6 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 1 | 16000 | 18 | 288000 | 80.04 | 432000 |  | 80.04: 432000
| 80.04 | Inspector (1251) |  |  | TBD | BCM | [12 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.04 | Inspector (1251) |  | BCM | 1 | [6 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 1 | 13600 | 18 | 244800 | 80.04 | 432000 | 160 | 80.04: 432000
| 80.04 | Office Engineer Engineer (1251) |  |  | TBD | BCM | [12 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1 | 1 | 1 | 1 | 1 | 80.04 | Office Engineer Engineer (1251) |  | BCM | 1 | [6 empty] | 6 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 1 | 15200 | 18 | 273600 | 80.04 | 432000 | 150 | 80.04: 432000
| 80.04 | Inspectors (Stations and Systems) |  |  | TBD | BCM | [12 empty] | 0 | [12 empty] | 0 |  | 3 | 3 | 4 | 4 | 80.04 | Inspectors (Stations and Systems) |  | BCM | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 42 | 12 | 12 | 12 | 12 | [8 empty] | 48 | 15 | 15 | 15 | 15 | [8 empty] | 60 | 15 | 15 | 15 | 15 | [8 empty] | 60 | 15 | 15 | 15 | 15 | [8 empty] | 60 | 12 | 12 | 6 | 6 | [8 empty] | 36 | [12 empty] | 0 | [12 empty] | 0 | 292 | 4672000 | 306 | 4896000 | 80.04 | 7344000
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
[141 empty] | 0 | 0
|  | Subtotals - Department Of Public Works (DPW) |  |  |  |  | 4.51 | 7.24 | 7.54 | 11.12 | 10.75 | 12.29 | 12.87 | 13.11 | 10.72 | 11.11 | 11.13 | 8.43 | 120.82 | 12.75 | 12.67 | 12.77 | 12.77 | 8.77 | 9.62 | 9.61 | 9.61 | 9.63 | 9.62 | 9.62 | 9.62 | 127.06 | 8.22 | 10 | 10 | 10.29 | 11.64 |  |  |  |  | 10.56 | 6.2 | 6.98 | 6.98 | 7.31 | 7.31 | 7.33 | 102.82 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 15 | 15 | 15 | 15 | [8 empty] | 60 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 12 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316.67 | 5163822.0262 | 614.7 | 10555112.8873 |  |  |  |  | 5109390.4 | 0 | 3120000 | 0 | 0 | 0 | 0
Group: City and County of San Francisco
| 80.02/ 80.08 | Arts Commission |  |  | Various | CCSF
| 80.02/ 80.08 | City Attorney's Office |  |  | Various | CCSF
|  | SFFD |  |  | Corbett/Stephenson/Fields | CCSF
|  | SFPD |  |  | Michael Connolly | CCSF
| 60 | Real Estate |  |  | TBD | CCSF
|  | Dept of Public Health |  |  | TBD | CCSF
|  | SFPUC |  |  | TBD | CCSF
|  | SFCTA |  |  | TBD | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [42 empty] | 0 | [64 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [55 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 0
|  | Subtotals - Group: City and County of San Francisco |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | 80.02: 0; 80.03: 0
|  | GRAND TOTALS |  |  |  |  | 53.4563 | 57.4694 | 62.2581 | 91.2614 | 127.8914 | 160.1385 | 158.4066 | 161.2329 | 159.7393 | 167.7911 | 165.6973 | 162.2962 | 1527.6387 | 168.6468 | 164.0816 | 163.6017 | 163.3465 | 163.7667 | 147.0816 | 147.6864 | 67.7623 | 67.9815 | 74.6804 | 75.7419 | 74.2089 | 1478.5862 | 68.8741 | 68.5166 | 68.4379 | 69.6481 | 78.9927 |  | GRAND TOTALS |  |  | 77.7727 | 73.6837 | 74.2667 | 73.1124 | 73.4424 | 78.4858 | 78.5568 | 883.7901 | 204.4566 | 263.0648 | 267.6691 | 267.6691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1002.8596 | 247.8745 | 247.8745 | 229.8745 | 228.6757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954.2992 | 229.2335 | 225.6735 | 225.8735 | 222.8735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903.6538 | 213.8735 | 210.8735 | 164.0735 | 144.1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732.9249 | 145.4046 | 139.3246 | 132.5246 | 125.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6782 | 153.484 | 154.284 | 147.034 | 130.284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585.0861 | 24.15 | 14.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 5289.8224 | 149581357.9833 | 9717.7467 | 221791572.1023
|  | Detailed Listing of Names included above on single lines labeled various | [141 empty] | 6954400
|  | CSP - Program Management Staff |  |  | Various
|  | Outreach (2) |  |  | Lam, Catherine
Wu, Cindy
Yeung, Malcolm
Chan, Deland
[5 empty] | Chow, Tan | DP1
|  | Intueor (2) |  |  | Hotha, Pavan |  | 0.86756 | 0.91881 | 0.71794 | 0.75512 | 0.90775 | 1.1682 | 0.96819 | 0.69319 | 0.60881 | 0.48131 | 0.38162 | 0.38162 |  | 0.31912 | 0.28787 | 0.28787 | 0.23688 | 0.2425 | 0.24813 | 0.24813 | 0.24813 | 0.32375 | 0.16638 | 0.16075 | 0.16075 |  | 0.22925 | 0.22925 | 0.215 | 0.34788 | 0.34788 |  |  |  |  | 0.33663 | 0.40663 | 0.38975 | 0.3785 | 0.3785 | 0.3785 | 0.3785 |  | 0.72137 | 0.72137 | 0.58137 | 0.58137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.30138 | 0.30138 | 0.30138 | 0 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Robert Clarke Blair |  | 0.5113 | 0.5463 | 0.76135 | 0.8176 | 1.1577 | 1.5122 | 1.4872 | 1.5257 | 2.2468 | 2.1078 | 1.8547 | 1.7047 |  | 1.3672 | 1.5234 | 1.8078 | 1.6752 | 5.6128 | 1.0503 | 0.73775 | 0.73775 | 0.75056 | 0.31541 | 0.31666 | 0.31666 |  | 0.2779 | 0.2779 | 0.206 | 0.1863 | 0.6888 |  |  |  |  | 0.1938 | 0.20161 | 0.20161 | 0.21411 | 0.21411 | 0.21161 | 0.21786 |  | 0.21535 | 0.21535 | 0.19972 | 0.19972 | 0.35875 | 0.0625 | 0.0625 | 0.05 | 0.05 | 0 | 0 | 0 |  | 0.13722 | 0.13722 | 0.13722 | 0 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CCO (2) |  |  | Chan Jason |  | 2.2799 | 3.2665 | 5.3674 | 6.253 | 6.5616 | 5.2721 | 5.0096 | 3.5404 | 3.7779 | 1.869 | 1.1865 | 1.3365 |  | 0.62713 | 0.26775 | 0.23963 | 0.2175 | 0.28875 | 0.29437 | 0.29437 | 0.16312 | 0.31062 | 0.24987 | 0.24425 | 0.24425 |  | 0.457 | 0.457 | 0.45625 | 0.87087 | 0.87087 |  |  |  |  | 0.85962 | 1.0671 | 1.0503 | 1.039 | 1.039 | 1.039 | 1.039 |  | 2.0761 | 2.0761 | 1.6611 | 1.6611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.83113 | 0.83113 | 0.83113 | 0 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Ng, Raymond |  | 2.2031 | 2.5556 | 4.4713 | 4.6712 | 6.4363 | 3.8644 | 2.38 | 1.62 | 1.6619 | 1.2225 | 0.82425 | 0.91375 |  | 0.885 | 0.8475 | 0.70875 | 0.49562 | 0.56375 | 0.62625 | 0.62625 | 0.615 | 0.67563 | 0.46625 | 0.40375 | 0.40375 |  | 0.46687 | 0.46687 | 0.46063 | 0.965 | 0.835 |  |  |  |  | 0.34 | 0.34375 | 0.15625 | 0.03125 | 0.03125 | 0.03125 | 0.03125 |  | 0.54688 | 0.54688 | 0.039375 | 0.039375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.024375 | 0.024375 | 0.024375 | 0 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Archeology (2) |  |  | Konzak, Michael |  | 0 | 0 | 0 | 0 | 0 | 1.8386 | 1.9405 | 7.7185 | 7.6822 | 9.4151 | 9.0599 | 8.3786 |  | 6.2511 | 1.3824 | 0.56863 | 0.68112 | 1.9 | 1.3811 | 1.2311 | 1.2311 | 1.1325 | 1.19 | 1.1912 | 0.19125 |  | 0.07875 | 0.06475 | 0.0635 | 0.0635 | 1.2976 |  |  |  |  | 0.11962 | 0.11962 | 0.11937 | 0.22925 | 0.22925 | 0.22675 | 0.28175 |  | 0.7755 | 0.3755 | 1.2755 | 1.2755 | 2.7056 | 0.55037 | 0.55037 | 0.44038 | 0.44038 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Meyer, Michael |  | 0.4825 | 0.54125 | 0.70625 | 1.0675 | 1.175 | 1.5037 | 1.5537 | 1.425 | 1.6262 | 1.1187 | 0.87 | 0.745 |  | 0.27 | 0.0325 | 0.0325 | 0.0225 | 0.025 | 0.0275 | 0.0275 | 0.0275 | 0.0525 | 0.04 | 0.0375 | 0.0375 |  | 0.0625 | 0.0625 | 0.0625 | 0.1075 | 0.1075 |  |  |  |  | 0.1025 | 0.125 | 0.1175 | 0.1125 | 0.1125 | 0.1125 | 0.1125 |  | 0.225 | 0.225 | 0.18 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.09 | 0.09 | 0.09 | 0 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Mischke, Bryan |  | 0.06875 | 0.06875 | 0.06875 | 0.1375 | 0.1375 | 0.20625 | 0.20625 | 0.20625 | 0.2125 | 0.08125 | 0.01875 | 0.01875 |  | 0.00625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00375 | 0.00375 | 0.00375 | 0.00375 |  | 0.0075 | 0.0075 | 0.0075 | 0.015 | 0.015 |  |  |  |  | 0.015 | 0.01875 | 0.01875 | 0.01875 | 0.01875 | 0.01875 | 0.01875 |  | 0.0375 | 0.0375 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.015 | 0.015 | 0.015 | 0 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Much, Bryan |  | 0.36875 | 0.425 | 0.5375 | 0.85 | 0.85 | 1.175 | 1.3 | 1.2212 | 1.21 | 0.5625 | 0.125 | 0 |  | 0 | 0 | 0 | 0.01 | 0.0125 | 0.015 | 0.015 | 0.015 | 0.0275 | 0.0275 | 0.025 | 0.025 |  | 0.0375 | 0.0375 | 0.0375 | 0.0575 | 0.0575 |  |  |  |  | 0.0525 | 0.0625 | 0.055 | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.1 | 0.1 | 0.08 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.04 | 0.04 | 0.04 | 0 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Newland, Michael
[5 empty] | Praetzellis, Adrian | DP2
[5 empty] | Praetzellis, Mary |  |  |  |  | 0.06 | 0.126 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 |  | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201 | 0.201
[5 empty] | Ribeiro, Maria |  |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 |  | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414
[5 empty] | Stoyka, Michael |  |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 |  | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414
|  | Outreach (4) |  |  | Chan, Charles |  |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 |  | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414
[5 empty] | Chau, Betty |  |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 |  | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414
[5 empty] | Halasz, Erin |  |  |  |  | 0.281 | 0.5901 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 |  | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414 | 0.9414
[5 empty] | Pierce, Robert |  |  |  |  | 1.5838 | 3.3259 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 |  | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054 | 5.3054
|  | Financial/Admin (3)) |  |  | Vodvarka, Jenny |  |  |  |  | 7.6935 | 16.1564 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 |  | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732 | 25.7732
[5 empty] | Jiang, Jessie |  |  |  |  | 5.8188 | 12.2194 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 |  | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928 | 19.4928
[5 empty] | Moody, Shela |  |  |  |  | 4.492 | 9.4332 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 |  | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482 | 15.0482
[5 empty] | Lau, Elissa |  |  |  |  | 0.4595 | 0.965 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 |  | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393 | 1.5393
[5 empty] | Ward, Beverly |  |  |  |  | 2.31 | 4.851 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 |  | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385 | 7.7385
|  | CSP - CM Staff |  |  | Various | DP3
|  | Environmental Inspector (1) |  |  | TBD | [5 empty] | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 1.1995 | 1.1995 | 1.1995 |  | 1.1995 | 1.1995 | 1.1995 | 1.1995 | 1.1995 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 |  | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 |  |  |  |  | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 | 0.59976 |  | 0.59976 | 0.59976 | 0.59976 | 0.59976 | [9 empty] | 0.59976 | 0.59976 | 0.59976 | 0.59976 | [9 empty] | 1.129 | 1.129 | 1.129 | 1.129 | [9 empty] | 1.129 | 1.129 | 1.129 | 1.129 | [9 empty] | 1.129 | 1.129 | 1.129 | 1.129 | [9 empty] | 0.6175 | 0.6175 | 0.6175 | 0.6175
|  | Specialty Inspection (.5) | [8 empty] | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 2.2409 | 2.2409 | 2.2409 |  | 2.2409 | 2.2409 | 2.2409 | 2.2409 | 2.2409 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 |  | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 |  |  |  |  | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 | 1.1205 |  | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [9 empty] | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [9 empty] | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [9 empty] | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [9 empty] | 1.1205 | 1.1205 | 1.1205 | 1.1205 | [9 empty] | 0 | 0 | 0 | 0
[11 empty] | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 2.4049 | 2.4049 | 2.4049 |  | 2.4049 | 2.4049 | 2.4049 | 2.4049 | 2.4049 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 |  | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 |  |  |  |  | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 | 1.2025 |  | 1.2025 | 1.2025 | 1.2025 | 1.2025 | [9 empty] | 1.2025 | 1.2025 | 1.2025 | 1.2025 | [9 empty] | 2.1101 | 2.1101 | 2.1101 | 2.1101 | [9 empty] | 2.1101 | 2.1101 | 2.1101 | 2.1101 | [9 empty] | 2.1101 | 2.1101 | 2.1101 | 2.1101 | [9 empty] | 1.0589 | 1.0589 | 1.0589 | 1.0589
|  | CSP - Tunnel Staff |  |  | Various | [5 empty] | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 1.6241 | 1.6241 | 1.6241 |  | 1.6241 | 1.6241 | 1.6241 | 1.6241 | 1.6241 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 |  | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 |  |  |  |  | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 | 0.81204 |  | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [9 empty] | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [9 empty] | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [9 empty] | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [9 empty] | 0.81204 | 0.81204 | 0.81204 | 0.81204 | [9 empty] | 0 | 0 | 0 | 0
|  | Inspectors |  |  | Greeley, Jame | [5 empty] | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.22238 | 0.22238 | 0.22238 |  | 0.22238 | 0.22238 | 0.22238 | 0.22238 | 0.22238 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 |  | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 |  |  |  |  | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 | 0.11119 |  | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [9 empty] | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [9 empty] | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [9 empty] | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [9 empty] | 0.11119 | 0.11119 | 0.11119 | 0.11119 | [9 empty] | 0 | 0 | 0 | 0
[5 empty] | Green, Larry | [5 empty] | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.24754 | 0.24754 | 0.24754 |  | 0.24754 | 0.24754 | 0.24754 | 0.24754 | 0.24754 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 |  | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 |  |  |  |  | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 | 0.12377 |  | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [9 empty] | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [9 empty] | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [9 empty] | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [9 empty] | 0.12377 | 0.12377 | 0.12377 | 0.12377 | [9 empty] | 0 | 0 | 0 | 0
[5 empty] | Hawk, William | [5 empty] | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.95694 | 0.95694 | 0.95694 |  | 0.95694 | 0.95694 | 0.95694 | 0.95694 | 0.95694 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 |  | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 |  |  |  |  | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 | 0.47847 |  | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [9 empty] | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [9 empty] | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [9 empty] | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [9 empty] | 0.47847 | 0.47847 | 0.47847 | 0.47847 | [9 empty] | 0 | 0 | 0 | 0
[5 empty] | Reynolds, Audie | [5 empty] | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.96902 | 0.96902 | 0.96902 |  | 0.96902 | 0.96902 | 0.96902 | 0.96902 | 0.96902 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 |  | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 |  |  |  |  | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 | 0.48451 |  | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [9 empty] | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [9 empty] | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [9 empty] | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [9 empty] | 0.48451 | 0.48451 | 0.48451 | 0.48451 | [9 empty] | 0 | 0 | 0 | 0
[5 empty] | TBD | [5 empty] | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.69129 | 0.69129 | 0.69129 |  | 0.69129 | 0.69129 | 0.69129 | 0.69129 | 0.69129 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 |  | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 |  |  |  |  | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 | 0.34565 |  | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [9 empty] | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [9 empty] | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [9 empty] | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [9 empty] | 0.34565 | 0.34565 | 0.34565 | 0.34565 | [9 empty] | 0 | 0 | 0 | 0
[5 empty] | TBD | [5 empty] | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.065406 | 0.065406 | 0.065406 |  | 0.065406 | 0.065406 | 0.065406 | 0.065406 | 0.065406 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 |  | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 |  |  |  |  | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 | 0.032703 |  | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [9 empty] | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [9 empty] | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [9 empty] | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [9 empty] | 0.032703 | 0.032703 | 0.032703 | 0.032703 | [9 empty] | 0 | 0 | 0 | 0
[5 empty] | TBD | [5 empty] | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.04025 | 0.04025 | 0.04025 |  | 0.04025 | 0.04025 | 0.04025 | 0.04025 | 0.04025 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 |  | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 |  |  |  |  | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 |  | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [9 empty] | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [9 empty] | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [9 empty] | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [9 empty] | 0.020125 | 0.020125 | 0.020125 | 0.020125 | [9 empty] | 0 | 0 | 0 | 0
|  | Project Engineer |  |  | Hembd, Mathew | [5 empty] | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.36024 | 0.36024 | 0.36024 |  | 0.36024 | 0.36024 | 0.36024 | 0.36024 | 0.36024 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 |  | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 |  |  |  |  | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 | 0.18012 |  | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [9 empty] | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [9 empty] | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [9 empty] | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [9 empty] | 0.18012 | 0.18012 | 0.18012 | 0.18012 | [9 empty] | 0 | 0 | 0 | 0
|  | Instrumentation |  |  | Wolski, Michael | [5 empty] | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.69934 | 0.69934 | 0.69934 |  | 0.69934 | 0.69934 | 0.69934 | 0.69934 | 0.69934 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 |  | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 |  |  |  |  | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 | 0.34967 |  | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [9 empty] | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [9 empty] | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [9 empty] | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [9 empty] | 0.34967 | 0.34967 | 0.34967 | 0.34967 | [9 empty] | 0 | 0 | 0 | 0
|  | Office Engineer |  |  | Leong, Kristie | [5 empty] | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 1.1139 | 1.1139 | 1.1139 |  | 1.1139 | 1.1139 | 1.1139 | 1.1139 | 1.1139 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 |  | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 |  |  |  |  | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 | 0.55695 |  | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [9 empty] | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [9 empty] | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [9 empty] | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [9 empty] | 0.55695 | 0.55695 | 0.55695 | 0.55695 | [9 empty] | 0 | 0 | 0 | 0
|  | PCC - Cost/Schedule |  |  | Various | [5 empty] | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.028175 | 0.028175 | 0.028175 |  | 0.028175 | 0.028175 | 0.028175 | 0.028175 | 0.028175 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 |  | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 |  |  |  |  | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 | 0.014087 |  | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [9 empty] | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [9 empty] | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [9 empty] | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [9 empty] | 0.014087 | 0.014087 | 0.014087 | 0.014087 | [9 empty] | 0 | 0 | 0 | 0
[5 empty] | A. Ayers | [5 empty] | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.020125 | 0.020125 | 0.020125 |  | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.020125 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 |  | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 |  |  |  |  | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 | 0.010063 |  | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [9 empty] | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [9 empty] | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [9 empty] | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [9 empty] | 0.010063 | 0.010063 | 0.010063 | 0.010063 | [9 empty] | 0 | 0 | 0 | 0
K. Frew-Eckhaus
|  | PCC - System/Project Reporting |  |  | Various
S. Mackensie
M. Washington
C. Rhodes
T. Washington

## PLANNED $Labor
[6 empty] | 160 | [43 empty] | 3
| SCC Code | [5 empty] | 2010 | [11 empty] | Totals | 2011 | [11 empty] | Totals | 2012 | [15 empty] | Totals | 2013 | [11 empty] | Totals | 2014 | [11 empty] | Totals | 2015 | [11 empty] | Totals | 2016 | [11 empty] | Totals | 2017 | [11 empty] | Totals | 2018 | [11 empty] | Totals | 2019 | [11 empty] | Totals |  | Grand | [12 empty] | Jan - May 2012 | June 2012 to completion |  | PLANNED EXPENDITURE - JUNE 2012 TO PROJECT COMPLETION
|  | Position | Cross Walk# | Unit | Individual | Org | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2010 | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | 2011 | Jan | Feb | Mar | April | May | SCC Code | Position | Individual | Org | June | July | Aug | Sept | Oct | Nov | Dec | 2012 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2013 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2014 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2015 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2016 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2017 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2018 | 1Q19 | 2Q19 | 3Q19 | 4Q19 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2019 | ETC Jun 2012 - May 2019 | Totals |  |  | PE | FD | PM | CM | Non-Constr | Legal, Rev | Test | S-U |  | Real Estate |  |  | CODE | PE 80.01 | FD 80.02 | PM 80.03 | CM 80.04 | Non-Constr 80.05 | Legal, Rev 80.06 | Test 80.07 | S-U 80.08
|  | Group: SFMTA - Program Management | [140 empty] | $Labor |  | 80.01 | 80.02 | 80.03 | 80.04 | 80.05 | 80.06 | 80.07 | 80.08 | 80 | 60 |  |  |  | 80.01 | 80.02 | 80.03 | 80.04 | 80.05 | 80.06 | 80.07 | 80.08
1 | 80.03 | Sr Program Manager | 150 | 200 | John Funghi | SFMTA | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 484607.664 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 484607.664 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 80.03 | Sr Program Manager | John Funghi | SFMTA | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 40383.972 | 484607.664 | 121151.916 | 121151.916 | 121151.916 | 121151.916 | [8 empty] | 484607.664 | 121151.916 | 121151.916 | 121151.916 | 121151.916 | [8 empty] | 484607.664 | 121151.916 | 121151.916 | 121151.916 | 121151.916 | [8 empty] | 484607.664 | 121151.916 | 121151.916 | 121151.916 | 121151.916 | [8 empty] | 484607.664 | 121151.916 | 121151.916 | 121151.916 | 121151.916 | [8 empty] | 484607.664 | 121151.916 | 121151.916 | 121151.916 | 121151.916 | [8 empty] | 484607.664 | 121151.916 | 60575.958 | 0 | 0 | [8 empty] | 181727.874 | 3372061.662 | 4543196.85 | 4543196.85 | 80.03 | 80.03: 4543196.85 |  | 201919.86 | 3372061.662 | 80.03 | 0 | 0 | 3372061.662 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0.925 | 0.45 | 1 | 0.95 | 0.3625 | 0.95625 | 0.75625 | 0.7125 | 0.73125 | 0.625 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | #REF! | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0.925 | 0.45 | 1 | 0.95 | 0.3625 | 0.95625 | 0.75625 | 0.7125 | 0.73125 | 0.625 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | #REF! | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 80.03 | Sr Clerk Typist | 150 | 320 | Joery Nacion | SFMTA | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 133344.36 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 133344.36 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 80.03 | Sr Clerk Typist | Joery Nacion | SFMTA | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 11112.03 | 133344.36 | 33336.09 | 33336.09 | 33336.09 | 33336.09 | [8 empty] | 133344.36 | 33336.09 | 33336.09 | 33336.09 | 33336.09 | [8 empty] | 133344.36 | 33336.09 | 33336.09 | 33336.09 | 33336.09 | [8 empty] | 133344.36 | 33336.09 | 33336.09 | 33336.09 | 33336.09 | [8 empty] | 133344.36 | 33336.09 | 33336.09 | 33336.09 | 33336.09 | [8 empty] | 133344.36 | 33336.09 | 33336.09 | 33336.09 | 33336.09 | [8 empty] | 133344.36 | 33336.09 | 16668.045 | 0 | 0 | [8 empty] | 50004.135 | 927854.505 | 1250103.375 | 1250103.375 | 80.03 | 80.03: 1250103.375 |  | 55560.15 | 927854.505 | 80.03 | 0 | 0 | 927854.505 | 0 | 0 | 0 | 0 | 0
| 80.03 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 |  | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 |  | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 80.03 | Secretary II MPMS | 150 | 320 | Yvette Rauls-Torres | SFMTA | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 146981.088 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 146981.088 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 80.03 | Secretary II MPMS | 0 | SFMTA | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 12248.424 | 146981.088 | 36745.272 | 36745.272 | 36745.272 | 36745.272 | [8 empty] | 146981.088 | 36745.272 | 36745.272 | 36745.272 | 36745.272 | [8 empty] | 146981.088 | 36745.272 | 36745.272 | 36745.272 | 36745.272 | [8 empty] | 146981.088 | 36745.272 | 36745.272 | 36745.272 | 36745.272 | [8 empty] | 146981.088 | 36745.272 | 36745.272 | 36745.272 | 36745.272 | [8 empty] | 146981.088 | 36745.272 | 36745.272 | 36745.272 | 36745.272 | [8 empty] | 146981.088 | 36745.272 | 0 | 0 | 0 | [8 empty] | 36745.272 | 1004370.768 | 1359575.064 | 1359575.064 | 80.03 | 80.03: 1359575.064 |  | 61242.12 | 1004370.768 | 80.03 | 0 | 0 | 1004370.768 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Exec Secretary | 305 | 431 | TBD | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Sr Admin/Analyst | 305 | 432 | TBD | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | PM III MPMS | 275 | 420 | TBD | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | PM II MPMS | 275 | 420 | TBD | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 80.03 | Program Manager Project Services | 275 | 439 | Bill Neilson | SFMTA | 37439.424 | 37439.424 | 37439.424 | 37439.424 | 37439.424 | 37439.424 | 0 | 0 | 0 | 0 | 0 | 0 | 224636.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.03 | Program Manager Project Services | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 224636.544 | 224636.544 | 80.03 | 80.03: 224636.544 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 |  | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 |  | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 80.04 | Construction Manager | 150 | 320 | Arthur Wong | SFMTA | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 359861.832 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 359861.832 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 80.04 | Construction Manager | Arthur Wong | SFMTA | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 29988.486 | 359861.832 | 89965.458 | 89965.458 | 89965.458 | 89965.458 | [8 empty] | 359861.832 | 89965.458 | 89965.458 | 89965.458 | 89965.458 | [8 empty] | 359861.832 | 89965.458 | 89965.458 | 89965.458 | 89965.458 | [8 empty] | 359861.832 | 89965.458 | 89965.458 | 89965.458 | 89965.458 | [8 empty] | 359861.832 | 89965.458 | 89965.458 | 89965.458 | 89965.458 | [8 empty] | 359861.832 | 89965.458 | 89965.458 | 89965.458 | 89965.458 | [8 empty] | 359861.832 | 89965.458 | 44982.729 | 0 | 0 | [8 empty] | 134948.187 | 2504038.581 | 3373704.675 | 3373704.675 | 80.04 | 80.04: 3373704.675 |  | 149942.43 | 2504038.581 | 80.04 | 0 | 0 | 0 | 2504038.581 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 |  | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 |  | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 80.03 | Quality Assurance Manager | 150 | 320 | Roger Nguyen | SFMTA | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 199923.24 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 199923.24 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 80.03 | Quality Assurance Manager | Roger Nguyen | SFMTA | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 16660.27 | 199923.24 | 49980.81 | 49980.81 | 49980.81 | 49980.81 | [8 empty] | 199923.24 | 49980.81 | 49980.81 | 49980.81 | 49980.81 | [8 empty] | 199923.24 | 49980.81 | 49980.81 | 49980.81 | 49980.81 | [8 empty] | 199923.24 | 49980.81 | 49980.81 | 49980.81 | 49980.81 | [8 empty] | 199923.24 | 49980.81 | 49980.81 | 49980.81 | 49980.81 | [8 empty] | 199923.24 | 49980.81 | 49980.81 | 49980.81 | 49980.81 | [8 empty] | 199923.24 | 49980.81 | 49980.81 | 0 | 0 | [8 empty] | 99961.62 | 1416122.95 | 1899270.78 | 1899270.78 | 80.03 | 80.03: 1899270.78 |  | 83301.35 | 1416122.95 | 80.03 | 0 | 0 | 1416122.95 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 80.03 | QA Support | 275 | 420 | Elisa Ng | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 29841.072 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 80.03 | QA Support | Elisa Ng | SFMTA | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 2486.756 | 29841.072 | 7460.268 | 7460.268 | 7460.268 | 7460.268 | [8 empty] | 29841.072 | 7460.268 | 7460.268 | 7460.268 | 7460.268 | [8 empty] | 29841.072 | 7460.268 | 7460.268 | 7460.268 | 7460.268 | [8 empty] | 29841.072 | 7460.268 | 7460.268 | 7460.268 | 7460.268 | [8 empty] | 29841.072 | 7460.268 | 7460.268 | 7460.268 | 7460.268 | [8 empty] | 29841.072 | 7460.268 | 7460.268 | 7460.268 | 7460.268 | [8 empty] | 29841.072 | 7460.268 | 7460.268 | 0 | 0 | [8 empty] | 14920.536 | 211374.26 | 253649.112 | 253649.112 | 80.03 | 80.03: 253649.112 |  | 12433.78 | 211374.26 | 80.03 | 0 | 0 | 211374.26 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 80.03 | Environmental Manager | 305 | 431 | David Greenaway | SFMTA | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 309211.128 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 309211.128 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 80.03 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128837.97 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 747260.226 | 747260.226 | 80.03 | 80.03: 747260.226 |  | 128837.97 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 80.03 | Finance/Grants Manager | 305 | 432 | Lewis Ames | SFMTA | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 309211.128 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 309211.128 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 80.03 | Finance/Grants Manager | Lewis Ames | SFMTA | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 25767.594 | 309211.128 | 77302.782 | 77302.782 | 77302.782 | 77302.782 | [8 empty] | 309211.128 | 77302.782 | 77302.782 | 77302.782 | 77302.782 | [8 empty] | 309211.128 | 77302.782 | 77302.782 | 77302.782 | 77302.782 | [8 empty] | 309211.128 | 77302.782 | 77302.782 | 77302.782 | 77302.782 | [8 empty] | 309211.128 | 77302.782 | 77302.782 | 77302.782 | 77302.782 | [8 empty] | 309211.128 | 77302.782 | 77302.782 | 77302.782 | 77302.782 | [8 empty] | 309211.128 | 38651.391 | 38651.391 | 0 | 0 | [8 empty] | 77302.782 | 2112942.708 | 2860202.934 | 2860202.934 | 80.03 | 80.03: 2860202.934 |  | 128837.97 | 2112942.708 | 80.03 | 0 | 0 | 2112942.708 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 80.03 | Finance Support | 305 | 432 | Robert Masys | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 80.03 | Finance Director |  |  | Sonali Bose | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 51949.44 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 80.03 | Finance Director | Sonali Bose | SFMTA | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 4329.12 | 51949.44 | 12987.36 | 12987.36 | 12987.36 | 12987.36 | [8 empty] | 51949.44 | 12987.36 | 12987.36 | 12987.36 | 12987.36 | [8 empty] | 51949.44 | 12987.36 | 12987.36 | 12987.36 | 12987.36 | [8 empty] | 51949.44 | 12987.36 | 12987.36 | 12987.36 | 12987.36 | [8 empty] | 51949.44 | 12987.36 | 12987.36 | 12987.36 | 12987.36 | [8 empty] | 51949.44 | 12987.36 | 12987.36 | 12987.36 | 12987.36 | [8 empty] | 51949.44 | 12987.36 | 12987.36 | 0 | 0 | [8 empty] | 25974.72 | 367975.2 | 441570.24 | 441570.24 | 80.03 | 80.03: 441570.24 |  | 21645.6 | 367975.2 | 80.03 | 0 | 0 | 367975.2 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 80.03 | Contracts Manager |  |  | Mario Gallardo | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 5020.784 | 60249.408 | 3012.4704 | 3012.4704 | 3012.4704 | 3012.4704 | 3012.4704 | 80.03 | Contracts Manager | Various | SFMTA | 3012.4704 | 3012.4704 | 3012.4704 | 3012.4704 | 3012.4704 | 3012.4704 | 3012.4704 | 36149.6448 | 7531.176 | 7531.176 | 7531.176 | 7531.176 | [8 empty] | 30124.704 | 7531.176 | 7531.176 | 7531.176 | 7531.176 | [8 empty] | 30124.704 | 7531.176 | 7531.176 | 7531.176 | 7531.176 | [8 empty] | 30124.704 | 7531.176 | 7531.176 | 7531.176 | 7531.176 | [8 empty] | 30124.704 | 7531.176 | 7531.176 | 7531.176 | 7531.176 | [8 empty] | 30124.704 | 7531.176 | 7531.176 | 7531.176 | 7531.176 | [8 empty] | 30124.704 | 7531.176 | 7531.176 | 0 | 0 | [8 empty] | 15062.352 | 216897.8688 | 292209.6288 | 292209.6288 | 80.03 | 80.03: 292209.6288 |  | 15062.352 | 216897.8688 | 80.03 | 0 | 0 | 216897.8688 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | [5 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 80.04 | Construction Inspectors |  |  | TBD | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19584 | 19584 | 19584 | 58752 | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 235008 | 19584 | 19584 | 19584 | 19584 | 19584 | 80.04 | Construction Inspectors | B. Volberding | SFMTA | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 19584 | 235008 | 58752 | 58752 | 58752 | 58752 | [8 empty] | 235008 | 58752 | 58752 | 58752 | 58752 | [8 empty] | 235008 | 58752 | 58752 | 58752 | 58752 | [8 empty] | 235008 | 58752 | 58752 | 58752 | 58752 | [8 empty] | 235008 | 58752 | 58752 | 58752 | 58752 | [8 empty] | 235008 | 58752 | 58752 | 58752 | 58752 | [8 empty] | 235008 | 58752 | 58752 | 0 | 0 | [8 empty] | 117504 | 1664640 | 2056320 | 2056320 | 80.04 | 80.04: 2056320 |  | 97920 | 1664640 | 80.04 | 0 | 0 | 0 | 1664640 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  | Principal Engineer MCEQ |  |  | TBD | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | Miscellaneous |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Project Controls Manager | 150 | 320 | Drew Howard | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 60 | Real Estate Manager | 305 | 432 | Kerstin Magary | SFMTA | 0 | 0 | 15273.832 | 15273.832 | 15273.832 | 15273.832 | 15273.832 | 15273.832 | 15273.832 | 15273.832 | 15273.832 | 15273.832 | 152738.32 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 7636.916 | 91642.992 | 0 | 0 | 0 | 0 | 0 | 60 | Real Estate Manager | Kerstin Magary | SFMTA | 19092.29 | 19092.29 | 19092.29 | 19092.29 | 19092.29 | 19092.29 | 19092.29 | 133646.03 | 57276.87 | 57276.87 | 57276.87 | 57276.87 | [8 empty] | 229107.48 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 362753.51 | 607134.822 | 607134.822 | 60 | 80: 607134.822 |  | 0 | 362753.51 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | [10 empty] | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | [10 empty] | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 60 | Real Estate | 275 | 420 | Jason Gallegos | SFMTA | 0 | 0 | 6275.98 | 6275.98 | 6275.98 | 6275.98 | 6275.98 | 6275.98 | 6275.98 | 6275.98 | 6275.98 | 6275.98 | 62759.8 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 2510.392 | 30124.704 | 0 | 0 | 0 | 0 | 0 | 60 | Real Estate | Jason Gallegos | SFMTA | 12551.96 | 12551.96 | 12551.96 | 12551.96 | 12551.96 | 12551.96 | 12551.96 | 87863.72 | 37655.88 | 37655.88 | 37655.88 | 37655.88 | [8 empty] | 150623.52 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 238487.24 | 331371.744 | 331371.744 | 60 | 80: 331371.744 |  | 0 | 238487.24 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | [10 empty] | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | [10 empty] | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 60 | Real Estate | 275 | 420 | Charles Lewis | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 60 | [10 empty] | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | [10 empty] | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 |  |  |  |  | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | [10 empty] | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 60 | Real Estate | 275 | 439 | Ken Yee | SFMTA | 0 | 0 | 7180.99 | 7180.99 | 7180.99 | 7180.99 | 7180.99 | 7180.99 | 7180.99 | 7180.99 | 7180.99 | 7180.99 | 71809.9 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 2872.396 | 34468.752 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 106278.652 | 106278.652 | 60 | 80: 106278.652 |  | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0.17188 | 0.2 | 0.19687 | 0.14688 | 0.15 | 0.29063 | 0.25 | 0.38906 | 0.13906 | 0.28906 |  |  | 2.2234 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 2.2234 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0.17188 | 0.2 | 0.19687 | 0.14688 | 0.15 | 0.29063 | 0.25 | 0.38906 | 0.13906 | 0.28906 |  |  | 2.2234 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 2.2234 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subotals - Group: SFMTA - Management |  |  |  |  | 199367.794 | 199367.794 | 228098.596 | 228098.596 | 228098.596 | 228098.596 | 190659.172 | 190659.172 | 190659.172 | 210243.172 | 210243.172 | 210243.172 | 2513837.004 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 206368.734 | 2476424.808 | 191340.7164 | 191340.7164 | 191340.7164 | 191340.7164 | 191340.7164 |  |  |  |  | 197217.3724 | 197217.3724 | 197217.3724 | 197217.3724 | 197217.3724 | 197217.3724 | 197217.3724 | 2337225.1888 | 590145.882 | 590145.882 | 590145.882 | 590145.882 | [8 empty] | 2360583.528 | 495213.132 | 495213.132 | 495213.132 | 495213.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980852.528 | 495213.132 | 495213.132 | 495213.132 | 495213.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980852.528 | 495213.132 | 495213.132 | 495213.132 | 495213.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980852.528 | 495213.132 | 495213.132 | 495213.132 | 495213.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980852.528 | 495213.132 | 495213.132 | 495213.132 | 495213.132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980852.528 | 456561.741 | 297589.737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754151.478 | 14399519.2528 | 20346484.6468 | 20346484.6468 |  |  | 0 | 13871674.7538 | 5430024.675 | 0 | 0 | 0 | 0 | 1044785.218 |  | 956703.582 | 14399519.2528 |  | 0 | 0 | 9629599.9218 | 4168678.581 | 0 | 0 | 0 | 0
[5 empty] | Budget |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [12 empty] | #REF! | #REF!
[5 empty] | Actual |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [12 empty] | #REF! | #REF!
[5 empty] | Forecast |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [12 empty] | #REF! | #REF!
[155 empty] | 0 | 0
|  | Group: SFMTA - Engineering | [29 empty] | 4990261.812 |  |  | 574022.1492 | [119 empty] | 574022.1492 | 0
1 | 80.03 | Deputy Program Manager | 150 | 200 | Hoe, Albert | SFMTA | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 310823.352 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 310823.352 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 80.03 | Deputy Program Manager | Hoe, Albert | SFMTA | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 25901.946 | 310823.352 | 77705.838 | 77705.838 | 77705.838 | 77705.838 | [8 empty] | 310823.352 | 77705.838 | 77705.838 | 77705.838 | 77705.838 | [8 empty] | 310823.352 | 77705.838 | 77705.838 | 77705.838 | 77705.838 | [8 empty] | 310823.352 | 77705.838 | 77705.838 | 77705.838 | 77705.838 | [8 empty] | 310823.352 | 77705.838 | 77705.838 | 77705.838 | 77705.838 | [8 empty] | 310823.352 | 77705.838 | 77705.838 | 77705.838 | 77705.838 | [8 empty] | 310823.352 | 77705.838 | 38852.919 | 0 | 0 | [8 empty] | 116558.757 | 2162812.491 | 2913968.925 | 2913968.925 | 80.03 | 80.03: 2913968.925 |  | 129509.73 | 2162812.491 | 80.03 | 0 | 0 | 2162812.491 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [134 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [134 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 80.02 | Associate Engineer (5207) | 275 | 420 | Pong, Sanford | SFMTA | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 24867.56 | 298410.72 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 268569.648 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 80.03 | Associate Engineer (5207) | Pong, Sanford | SFMTA | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 268569.648 | 67142.412 | 67142.412 | 67142.412 | 67142.412 | [8 empty] | 268569.648 | 29841.072 | 29841.072 | 29841.072 | 29841.072 | [8 empty] | 119364.288 | 29841.072 | 29841.072 | 29841.072 | 29841.072 | [8 empty] | 119364.288 | 29841.072 | 29841.072 | 29841.072 | 29841.072 | [8 empty] | 119364.288 | 29841.072 | 29841.072 | 29841.072 | 29841.072 | [8 empty] | 119364.288 | 29841.072 | 29841.072 | 29841.072 | 29841.072 | [8 empty] | 119364.288 | 29841.072 | 0 | 0 | 0 | [8 empty] | 29841.072 | 1051897.788 | 1730782.176 | 1730782.176 | 80.02 | 80.02: 1730782.176 |  | 111904.02 | 1051897.788 | 80.02 | 0 | 1051897.788 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 80.02 | Associate Engineer (5207) | 150 | 320 | Wilson, Prester | SFMTA | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 268569.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.02 | Associate Engineer (5207) | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 268569.648 | 268569.648 | 80.02 | 80.02: 268569.648 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 80.02 | Associate Engr MCEG (5207) - Sr Engr | 305 | 431 | Jane Wang (5211) | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 268569.648 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 80.03 | Associate Engr MCEG (5207) - Sr Engr | Jane Wang (5211) | SFMTA | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 22380.804 | 268569.648 | 67142.412 | 67142.412 | 67142.412 | 67142.412 | [8 empty] | 268569.648 | 67142.412 | 67142.412 | 67142.412 | 67142.412 | [8 empty] | 268569.648 | 67142.412 | 67142.412 | 67142.412 | 67142.412 | [8 empty] | 268569.648 | 67142.412 | 67142.412 | 67142.412 | 67142.412 | [8 empty] | 268569.648 | 67142.412 | 67142.412 | 67142.412 | 67142.412 | [8 empty] | 268569.648 | 67142.412 | 67142.412 | 67142.412 | 67142.412 | [8 empty] | 268569.648 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1768083.516 | 2148557.184 | 2148557.184 | 80.02 | 80.02: 2148557.184 |  | 111904.02 | 1768083.516 | 80.02 | 0 | 1768083.516 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 80.02 | Assistant Engineer (5203) |  |  | Seng, Wuthea | SFMTA | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 22440.516 | 269286.192 | 27783.496 | 27783.496 | 27783.496 | 27783.496 | 27783.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138917.48 | 0 | 0 | 0 | 0 | 0 | 80.02 | Assistant Engineer (5203) | Seng, Wuthea | SFMTA | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 134643.096 | 57704.184 | 57704.184 | 57704.184 | 57704.184 | [8 empty] | 230816.736 | 57704.184 | 57704.184 | 57704.184 | 57704.184 | [8 empty] | 230816.736 | 57704.184 | 57704.184 | 57704.184 | 57704.184 | [8 empty] | 230816.736 | 57704.184 | 57704.184 | 57704.184 | 57704.184 | [8 empty] | 230816.736 | 57704.184 | 57704.184 | 57704.184 | 57704.184 | [8 empty] | 230816.736 | 57704.184 | 57704.184 | 57704.184 | 57704.184 | [8 empty] | 230816.736 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1519543.512 | 1927747.184 | 1927747.184 | 80.02 | 80.02: 1927747.184 |  | 0 | 1519543.512 | 80.02 | 0 | 1519543.512 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 80.02 | Assistant Engineer (5203) |  |  | Lee, Timothy | SFMTA | 12823.152 | 12823.152 | 12823.152 | 12823.152 | 12823.152 | 12823.152 | 12823.152 | 12823.152 | 12823.152 | 12823.152 | 0 | 0 | 128231.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.02 | Assistant Engineer (5203) | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 128231.52 | 128231.52 | 80.02 | 80.02: 128231.52 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 80.02 | Assistant Engineer (5203) |  |  | David, Chris | SFMTA | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 19234.728 | 0 | 0 | 192347.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.02 | Assistant Engineer (5203) | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 192347.28 | 192347.28 | 80.02 | 80.02: 192347.28 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 80.02 | Engineer (5241) |  |  | Huey, Lang | SFMTA | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 207215.568 | 27340.943 | 27340.943 | 27340.943 | 27340.943 | 27340.943 | 5755.988 | 5755.988 | 5755.988 | 5755.988 | 5755.988 | 5755.988 | 0 | 171240.643 | 0 | 0 | 0 | 0 | 0 | 80.02 | Engineer (5241) | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 378456.211 | 378456.211 | 80.02 | 80.02: 378456.211 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 80.02 | Engineer (5241) |  |  | Phang, Tee | SFMTA | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 17267.964 | 207215.568 | 38852.919 | 38852.919 | 38852.919 | 38852.919 | 38852.919 | 7194.985 | 7194.985 | 7194.985 | 7194.985 | 7194.985 | 7194.985 | 0 | 237434.505 | 0 | 0 | 0 | 0 | 0 | 80.02 | Engineer (5241) | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 444650.073 | 444650.073 | 80.02 | 80.02: 444650.073 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | SFMTA | [31 empty] | 0 |  |  | SFMTA | [99 empty] | 0 |  |  |  | 80.02: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 80.02 | Sr Engineer MCEQ (5211) |  |  | Bhatti, Jaswant | SFMTA | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 18326.297 | 219915.564 | 19992.324 | 19992.324 | 19992.324 | 19992.324 | 19992.324 | 8330.135 | 8330.135 | 8330.135 | 8330.135 | 8330.135 | 8330.135 | 0 | 149942.43 | 0 | 0 | 0 | 0 | 0 | 80.02 | Sr Engineer MCEQ (5211) | 0 | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 369857.994 | 369857.994 | 80.02 | 80.02: 369857.994 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 80.01
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtotals - Group: SFMTA - Engineering |  |  |  |  | 180510.931 | 180510.931 | 180510.931 | 180510.931 | 180510.931 | 180510.931 | 180510.931 | 180510.931 | 180510.931 | 180510.931 | 148453.051 | 148453.051 | 2102015.412 | 184633.236 | 184633.236 | 184633.236 | 184633.236 | 184633.236 | 91944.662 | 91944.662 | 91944.662 | 91944.662 | 91944.662 | 91944.662 | 70663.554 | 1545497.706 | 70663.554 | 70663.554 | 70663.554 | 70663.554 | 70663.554 |  |  |  |  | 89898.282 | 89898.282 | 89898.282 | 89898.282 | 89898.282 | 89898.282 | 89898.282 | 982605.744 | 269694.846 | 269694.846 | 269694.846 | 269694.846 | [8 empty] | 1078779.384 | 232393.506 | 232393.506 | 232393.506 | 232393.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929574.024 | 232393.506 | 232393.506 | 232393.506 | 232393.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929574.024 | 232393.506 | 232393.506 | 232393.506 | 232393.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929574.024 | 232393.506 | 232393.506 | 232393.506 | 232393.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929574.024 | 232393.506 | 232393.506 | 232393.506 | 232393.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929574.024 | 107546.91 | 38852.919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146399.829 | 6502337.307 | 10503168.195 | 10503168.195 |  |  | 7589199.27 | 2913968.925 | 0 | 0 | 0 | 0 | 0 |  |  | 353317.77 | 6502337.307 |  | 0 | 4339524.816 | 2162812.491 | 0 | 0 | 0 | 0 | 0
|  | Group: SFMTA - Start-Up; Safety & Security; Other | [152 empty] | 0 | 0
1 | 80.08 | Start-Up Manager | 150 | 200 | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 21120 | 1760 | 1760 | 1760 | 1760 | 1760 | 80.08 | Start-Up Manager | TBD | Ops | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 1760 | 21120 | 5280 | 5280 | 5280 | 5280 | [8 empty] | 21120 | 5280 | 5280 | 5280 | 5280 | [8 empty] | 21120 | 5280 | 5280 | 5280 | 5280 | [8 empty] | 21120 | 5280 | 5280 | 5280 | 5280 | [8 empty] | 21120 | 95040 | 95040 | 95040 | 95040 | [8 empty] | 380160 | 95040 | 95040 | 95040 | 95040 | [8 empty] | 380160 | 95040 | 95040 | 0 | 0 | [8 empty] | 190080 | 1047200 | 1077120 | 1077120 | 80.08 | 80.08: 1077120 |  | 8800 | 1047200 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1047200
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[141 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 80.08 | Senior Operations Manager | 150 | 320 | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Senior Operations Manager | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 25308.9 | 25308.9 | 25308.9 | 25308.9 | [8 empty] | 101235.6 | 25308.9 | 25308.9 | 25308.9 | 25308.9 | [8 empty] | 101235.6 | 10123.56 | 10123.56 | 0 | 0 | [8 empty] | 20247.12 | 222718.32 | 222718.32 | 222718.32 | 80.08 | 80.08: 222718.32 |  | 0 | 222718.32 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222718.32
[38 empty] | 0 |  |  | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 |  |  | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 80.08 | Senior Operations Manager | 150 | 320 | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Senior Operations Manager | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 16872.6 | 16872.6 | [8 empty] | 33745.2 | 20247.12 | 20247.12 | 20247.12 | 20247.12 | [8 empty] | 80988.48 | 25308.9 | 25308.9 | 25308.9 | 25308.9 | [8 empty] | 101235.6 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 215969.28 | 215969.28 | 215969.28 | 80.08 | 80.08: 215969.28 |  | 0 | 215969.28 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215969.28
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 80.08 | Transit Manager II | 305 | 431 | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Transit Manager II | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 13767.7 | 13767.7 | [8 empty] | 27535.4 | 24781.86 | 24781.86 | 24781.86 | 24781.86 | [8 empty] | 99127.44 | 165212.4 | 165212.4 | 165212.4 | 165212.4 | [8 empty] | 660849.6 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 787512.44 | 787512.44 | 787512.44 | 80.08 | 80.08: 787512.44 |  | 0 | 787512.44 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787512.44
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 80.08 | Transit Manager I | 305 | 432 | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Transit Manager I | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 12193.9 | 12193.9 | 12193.9 | 12193.9 | [8 empty] | 48775.6 | 146326.8 | 146326.8 | 146326.8 | 146326.8 | [8 empty] | 585307.2 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 634082.8 | 634082.8 | 634082.8 | 80.08 | 80.08: 634082.8 |  | 0 | 634082.8 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634082.8
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 80.08 | Transit Operator | 275 | 420 | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Transit Operator | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 24529.32 | 24529.32 | 24529.32 | [8 empty] | 73587.96 | 340685 | 408822 | 408822 | 408822 | [8 empty] | 1567151 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1640738.96 | 1640738.96 | 1640738.96 | 80.08 | 80.08: 1640738.96 |  | 0 | 1640738.96 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1640738.96
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 80.08 | Station Agent | 275 | 420 | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Station Agent | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 30809.88 | 30809.88 | 30809.88 | [8 empty] | 92429.64 | 427915 | 513498 | 513498 | 513498 | [8 empty] | 1968409 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2060838.64 | 2060838.64 | 2060838.64 | 80.08 | 80.08: 2060838.64 |  | 0 | 2060838.64 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060838.64
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 80.08 | Senior Stationary Engineer |  |  | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Senior Stationary Engineer | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 10000.95 | 10000.95 | [8 empty] | 20001.9 | 10000.95 | 10000.95 | 10000.95 | 10000.95 | [8 empty] | 40003.8 | 30002.85 | 30002.85 | 30002.85 | 30002.85 | [8 empty] | 120011.4 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 180017.1 | 180017.1 | 180017.1 | 80.08 | 80.08: 180017.1 |  | 0 | 180017.1 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180017.1
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 80.08 | Electronic Maint Tech Asst Sup |  |  | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Electronic Maint Tech Asst Sup | TBD | Ops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 6414.15 | 6414.15 | 6414.15 | [8 empty] | 19242.45 | 38484.9 | 38484.9 | 38484.9 | 38484.9 | [8 empty] | 153939.6 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 173182.05 | 173182.05 | 173182.05 | 80.08 | 80.08: 173182.05 |  | 0 | 173182.05 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173182.05
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 80.08 | Parking Control Officer |  |  | TBD | DPT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Parking Control Officer | TBD | DPT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 12431.8 | 12431.8 | 12431.8 | 12431.8 | [8 empty] | 49727.2 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 49727.2 | 49727.2 | 49727.2 | 80.08 | 80.08: 49727.2 |  | 0 | 49727.2 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49727.2
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | [99 empty] | 0 |  |  |  | 80.08: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 80.03 | Safety Representative |  |  | B Woo/Kartik Shah | SFMTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 153600 | 23040 | 23040 | 23040 | 23040 | 23040 | 80.03 | Safety Representative | B Woo/Kartik Shah | SFMTA | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 23040 | 276480 | 69120 | 69120 | 69120 | 69120 | [8 empty] | 276480 | 69120 | 69120 | 69120 | 69120 | [8 empty] | 276480 | 69120 | 69120 | 69120 | 69120 | [8 empty] | 276480 | 69120 | 69120 | 69120 | 69120 | [8 empty] | 276480 | 69120 | 69120 | 69120 | 69120 | [8 empty] | 276480 | 69120 | 69120 | 69120 | 69120 | [8 empty] | 276480 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1820160 | 2088960 | 2088960 | 80.03 | 80.03: 2088960 |  | 115200 | 1820160 | 80.03 | 0 | 0 | 1820160 | 0 | 0 | 0 | 0 | 0
| 80.03 | [36 empty] | 80.03 | 0 | 0 | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 | [36 empty] | 80.03 | 0 | 0 | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 80.03 | Traffic Engineer |  |  | Al Herce/Albert Wong | DPT | 0 | 0 | 0 | 0 | 0 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 89600 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 153600 | 12800 | 12800 | 12800 | 12800 | 12800 | 80.03 | Traffic Engineer | Al Herce/Albert Wong | DPT | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 12800 | 153600 | 6400 | 6400 | 6400 | 6400 | [8 empty] | 25600 | 6400 | 6400 | 6400 | 6400 | [8 empty] | 25600 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 140800 | 448000 | 448000 | 80.03 | 80.03: 448000 |  | 64000 | 140800 | 80.03 | 0 | 0 | 140800 | 0 | 0 | 0 | 0 | 0
| 80.03 | [36 empty] | 80.03 | 0 | 0 | 0 | [99 empty] | 0 |  |  | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 | [36 empty] | 80.03 | 0 | 0 | 0 | [99 empty] | 0 |  |  | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 80.03 | Traffic Asst Engineer |  |  | S Broady/L Slingsby | DPT | 0 | 0 | 0 | 0 | 0 | 10640 | 10640 | 10640 | 10640 | 10640 | 10640 | 10640 | 74480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.03 | Traffic Asst Engineer | S Broady/L Slingsby | DPT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 74480 | 74480 | 80.03 | 80.03: 74480 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 | [36 empty] | 80.03 | 0 | 0 | 0 | [99 empty] | 0 |  |  | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 | [36 empty] | 80.03 | 0 | 0 | 0 | [99 empty] | 0 |  |  | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 80.03 | Traffic Assoc Engineer I |  |  | Alex Wong | DPT | 0 | 0 | 0 | 0 | 0 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 86800 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 148800 | 12400 | 12400 | 12400 | 12400 | 12400 | 80.03 | Traffic Assoc Engineer I | Alex Wong | DPT | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 12400 | 148800 | 6200 | 6200 | 6200 | 6200 | [8 empty] | 24800 | 6200 | 6200 | 6200 | 6200 | [8 empty] | 24800 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 136400 | 434000 | 434000 | 80.03 | 80.03: 434000 |  | 62000 | 136400 | 80.03 | 0 | 0 | 136400 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[39 empty] | 0 | 0 | [100 empty] | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtotals - Group: SFMTA - Start-Up; Safety & Security; Other |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 35840 | 35840 | 35840 | 35840 | 35840 | 35840 | 35840 | 250880 | 39760 | 39760 | 39760 | 39760 | 39760 | 39760 | 39760 | 39760 | 39760 | 39760 | 39760 | 39760 | 477120 | 50000 | 50000 | 50000 | 50000 | 50000 |  |  |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000 | 87000 | 87000 | 87000 | 87000 | [8 empty] | 348000 | 87000 | 87000 | 87000 | 87000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348000 | 74400 | 74400 | 74400 | 74400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297600 | 74400 | 74400 | 115041.25 | 115041.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378882.5 | 256692.73 | 318446.08 | 318446.08 | 318446.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212030.97 | 1375836.55 | 1529556.55 | 1529556.55 | 1529556.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5964506.2 | 105163.56 | 105163.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210327.12 | 9109346.79 | 10087346.79 | 10087346.79 |  |  | 0 | 3045440 | 0 | 0 | 0 | 0 | 7041906.79 |  |  | 250000 | 9109346.79 |  | 0 | 0 | 2097360 | 0 | 0 | 0 | 0 | 7011986.79
[155 empty] | 0 | 0
[155 empty] | 0 | 0
[155 empty] | 0 | 0
[155 empty] | 0 | 0
|  | Group: Central Subway Partnership - Program Management/Construction Management | [152 empty] | 0 | 0
1 | 80.03 | Program Manager | 150 | 200 | Various | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 80.03 | Program Manager | R.Edwards/R. Redmond | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2209289.3221 | 3020294.2631 | 3761542.4412 | 80.03 | 80.03: 3020294.2631 |  | 139828.4381 | 2209289.3221 | 80.03 | 0 | 0 | 2209289.3221 | 0 | 0 | 0 | 0 | 0
3 | 80.03 | Project Controls Manager | 150 | 320 | J Burns | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.03 | 0 | 0 | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 335588.2515 | 417949.1601 | 80.03 | 80.03: 335588.2515 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 80.03 | Risk/Configuration Manager | 305 | 431 | Various | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 80.03 | Program Manager Project Services | E. Stassevitch | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2209289.3221 | 3020294.2631 | 3761542.4412 | 80.03 | 80.03: 3020294.2631 |  | 139828.4381 | 2209289.3221 | 80.03 | 0 | 0 | 2209289.3221 | 0 | 0 | 0 | 0 | 0
5 | 80.03 | Outreach Manager | 305 | 432 | B Norris | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 80.03 | Outreach Manager | C.Goodyear | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | [8 empty] | 167794.1257 | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | [8 empty] | 167794.1257 | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | [8 empty] | 167794.1257 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1705906.9449 | 2516911.8859 | 3134618.701 | 80.03 | 80.03: 2516911.8859 |  | 139828.4381 | 1705906.9449 | 80.03 | 0 | 0 | 1705906.9449 | 0 | 0 | 0 | 0 | 0
6 | 80.03 | Q/A Manager |  |  | M Latch | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 80.03 | Q/A Manager | M. Latch | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2209289.3221 | 3020294.2631 | 3761542.4412 | 80.03 | 80.03: 3020294.2631 |  | 139828.4381 | 2209289.3221 | 80.03 | 0 | 0 | 2209289.3221 | 0 | 0 | 0 | 0 | 0
| 80.03 | Design Oversight Managers |  |  | Various | PM/CM | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 687955.9155 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 57329.6596 | 687955.9155 | 0 | 0 | 0 | 0 | 0 | 80.03 | Design Oversight Managers | H.Q Chin | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 195759.8133 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 0 | 0 | [8 empty] | 167794.1257 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1370318.6934 | 2746230.5244 | 3420217.2938 | 80.03 | 80.03: 2746230.5244 |  | 0 | 1370318.6934 | 80.03 | 0 | 0 | 1370318.6934 | 0 | 0 | 0 | 0 | 0
| 80.03 | Regulatory/Interagency Manager |  |  | G Hollins | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 80.03 | Regulatory/Interagency Manager | G Hollins | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | [8 empty] | 111862.7505 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 307622.5638 | 1118627.5049 | 1393163.8671 | 80.03 | 80.03: 1118627.5049 |  | 139828.4381 | 307622.5638 | 80.03 | 0 | 0 | 307622.5638 | 0 | 0 | 0 | 0 | 0
| 80.03 | Document Control Manager |  |  | S MacKenzie | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 80.03 | Risk/Configuration Manager | Alex Clifford | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1202524.5677 | 2013529.5087 | 2507694.9608 | 80.03 | 80.03: 2013529.5087 |  | 139828.4381 | 1202524.5677 | 80.03 | 0 | 0 | 1202524.5677 | 0 | 0 | 0 | 0 | 0
| 80.03 | Program Management Staff |  |  | Various | PM/CM | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 422841.1968 | 5074094.362 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 5633519.9772 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 80.03 | Program Management Staff* | Various* (see details below) | PM/CM | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 469459.9981 | 5633519.9772 | 1408379.9943 | 1408379.9943 | 1408379.9943 | 1408379.9943 | [8 empty] | 5633519.9772 | 1099051.5235 | 1099051.5235 | 1099051.5235 | 1099051.5235 | [8 empty] | 4396206.0941 | 1099051.5235 | 1099051.5235 | 1099051.5235 | 1099051.5235 | [8 empty] | 4396206.0941 | 1099051.5235 | 1099051.5235 | 0 | 0 | [8 empty] | 2198103.047 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 19910255.1991 | 32965169.5287 | 41055563.9493 | 80.03 | 80.03: 32965169.5287 |  | 2347299.9905 | 19910255.1991 | 80.03 | 0 | 0 | 19910255.1991 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 |  | 80.03: 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.04 | Construction Manager |  |  | TBD | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 80.04 | Construction Manager | M. Benson | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2209289.3221 | 3020294.2631 | 3761542.4412 |  | 80.03: 3020294.2631 |  | 139828.4381 | 2209289.3221 | 80.04 | 0 | 0 | 0 | 2209289.3221 | 0 | 0 | 0 | 0
| 80.04 | Safety |  |  | TBD | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 80.04 | Program Safety Manager | D. Matlock | PM/CM | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2209289.3221 | 3020294.2631 | 3761542.4412 |  | 80.03: 3020294.2631 |  | 139828.4381 | 2209289.3221 | 80.04 | 0 | 0 | 0 | 2209289.3221 | 0 | 0 | 0 | 0
| 80.04 | CM Staff |  |  | Various | PM/CM | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 31237.6731 | 374852.0769 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 858099.159 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 71508.2632 | 80.04 | CM Staff | Various* (see details below) | PM/CM | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | 651181.0363 | 125845.5943 | 125845.5943 | 125845.5943 | 125845.5943 | [8 empty] | 503382.3772 | 125845.5943 | 125845.5943 | 125845.5943 | 125845.5943 | [8 empty] | 503382.3772 | 125845.5943 | 125845.5943 | 125845.5943 | 125845.5943 | [8 empty] | 503382.3772 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1803786.8516 | 3394279.4037 | 4227311.9511 |  | 80.03: 3394279.4037 |  | 357541.3162 | 1803786.8516 | 80.04 | 0 | 0 | 0 | 1803786.8516 | 0 | 0 | 0 | 0
| 80.04 | Mat'l Testing |  |  | Various | PM/CM | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 708091.2106 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 708091.2106 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 80.04 | Mat'l Testing | TBD | PM/CM | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 59007.6009 | 708091.2106 | 177022.8026 | 177022.8026 | 177022.8026 | 177022.8026 | [8 empty] | 708091.2106 | 113261.0349 | 113261.0349 | 113261.0349 | 113261.0349 | [8 empty] | 453044.1395 | 113261.0349 | 113261.0349 | 113261.0349 | 113261.0349 | [8 empty] | 453044.1395 | 113261.0349 | 113261.0349 | 113261.0349 | 113261.0349 | [8 empty] | 453044.1395 | 113261.0349 | 0 | 0 | 0 | [8 empty] | 113261.0349 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2593537.87 | 4304758.2955 | 5361242.8516 |  | 80.03: 4304758.2955 |  | 295038.0044 | 2593537.87 | 80.04 | 0 | 0 | 0 | 2593537.87 | 0 | 0 | 0 | 0
| 80.04 | Utility CM's/RE's |  |  | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 27965.6876 | 335588.2515 | 0 | 0 | 0 | 0 | 0 | 80.04 | Safety & Security Certification | Wayne Giles | PM/CM | 6991.4219 | 6991.4219 | 6991.4219 | 6991.4219 | 6991.4219 | 6991.4219 | 6991.4219 | 48939.9533 | 20974.2657 | 20974.2657 | 20974.2657 | 20974.2657 | [8 empty] | 83897.0629 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 132837.0162 | 468425.2677 | 583387.3694 |  | 80.03: 468425.2677 |  | 0 | 132837.0162 | 80.04 | 0 | 0 | 0 | 132837.0162 | 0 | 0 | 0 | 0
| 80.04 | Utility Staff |  |  | Various | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 167794.1257 | 0 | 0 | 0 | 0 | 0 | 80.04 | CCO | A.Butler/D.Butler | PM/CM | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 97879.9067 | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | [8 empty] | 167794.1257 | 41948.5314 | 41948.5314 | 41948.5314 | 41948.5314 | [8 empty] | 167794.1257 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 433468.1581 | 601262.2839 | 748825.5786 |  | 80.03: 601262.2839 |  | 0 | 433468.1581 | 80.04 | 0 | 0 | 0 | 433468.1581 | 0 | 0 | 0 | 0
| 80.04 | Tunnel CM's/RE's |  |  | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27965.6876 | 27965.6876 | 27965.6876 | 55931.3752 | 55931.3752 | 55931.3752 | 251691.1886 | 55931.3752 | 55931.3752 | 55931.3752 | 55931.3752 | 55931.3752 | 80.04 | Tunnel RE/ARE | S. Wilson/M.Leong | PM/CM | 55931.3752 | 55931.3752 | 55931.3752 | 55931.3752 | 55931.3752 | 55931.3752 | 55931.3752 | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 83897.0629 | 0 | 0 | [8 empty] | 251691.1886 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2656740.324 | 3188088.3888 | 3970517.0213 |  | 80.03: 3188088.3888 |  | 279656.8762 | 2656740.324 | 80.04 | 0 | 0 | 0 | 2656740.324 | 0 | 0 | 0 | 0
| 80.04 | Tunnel Staff |  |  | Various | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178700.7439 | 178700.7439 | 178700.7439 | 536102.2317 | 178700.7439 | 178700.7439 | 178700.7439 | 178700.7439 | 178700.7439 | 80.04 | Tunnel Staff (OE,IE,Insp) | Various* (see details below) | PM/CM | 178700.7439 | 178700.7439 | 178700.7439 | 178700.7439 | 178700.7439 | 195759.8133 | 195759.8133 | 2178527.0657 | 587279.44 | 755073.5658 | 922867.6915 | 922867.6915 | [8 empty] | 3188088.3888 | 922867.6915 | 922867.6915 | 419485.3143 | 419485.3143 | [8 empty] | 2684706.0116 | 419485.3143 | 335588.2515 | 167794.1257 | 83897.0629 | [8 empty] | 1006764.7544 | 83897.0629 | 83897.0629 | 0 | 0 | [8 empty] | 167794.1257 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 8332376.6268 | 9761982.578 | 12157792.7774 |  | 80.03: 9761982.578 |  | 893503.7195 | 8332376.6268 | 80.04 | 0 | 0 | 0 | 8332376.6268 | 0 | 0 | 0 | 0
| 80.04 | UMS CM's/RE's |  |  | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.04 | UMS RE/ARE | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 503382.3772 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 3188088.3888 | 3188088.3888 | 3970517.0213 |  | 80.03: 3188088.3888 |  | 0 | 3188088.3888 | 80.04 | 0 | 0 | 0 | 3188088.3888 | 0 | 0 | 0 | 0
| 80.04 | UMS Staff |  |  | Various | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 13982.8438 | 167794.1257 | 0 | 0 | 0 | 0 | 0 | 80.04 | UMS Staff (OE,IE,Insp) | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281894.1312 | 281894.1312 | 281894.1312 | [8 empty] | 845682.3937 | 281894.1312 | 281894.1312 | 281894.1312 | 281894.1312 | [8 empty] | 1127576.5249 | 281894.1312 | 282453.445 | 282453.445 | 282453.445 | [8 empty] | 1129254.4661 | 282453.445 | 282453.445 | 282453.445 | 282453.445 | [8 empty] | 1129813.7799 | 282453.445 | 282453.445 | 282453.445 | 167794.1257 | [8 empty] | 1015154.4607 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 5247481.6253 | 5415275.751 | 6744306.2807 |  | 80.03: 5415275.751 |  | 0 | 5247481.6253 | 80.04 | 0 | 0 | 0 | 5247481.6253 | 0 | 0 | 0 | 0
| 80.04 | CTS CM's/RE's |  |  | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.04 | CTS RE/ARE | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 503382.3772 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 0 | 0 | [8 empty] | 335588.2515 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 3523676.6403 | 3523676.6403 | 4388466.1814 |  | 80.03: 3523676.6403 |  | 0 | 3523676.6403 | 80.04 | 0 | 0 | 0 | 3523676.6403 | 0 | 0 | 0 | 0
7 | 80.04 | CTS Staff |  |  | Various | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.04 | CTS Staff (OE,IE,Insp) | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332232.3689 | 332232.3689 | 332232.3689 | [8 empty] | 996697.1068 | 332232.3689 | 332232.3689 | 332232.3689 | 332232.3689 | [8 empty] | 1328929.4758 | 332232.3689 | 282453.445 | 282453.445 | 282453.445 | [8 empty] | 1179592.7039 | 282453.445 | 282453.445 | 282453.445 | 282453.445 | [8 empty] | 1129813.7799 | 282453.445 | 282453.445 | 282453.445 | 282453.445 | [8 empty] | 1129813.7799 | 167794.1257 | 0 | 0 | 0 | [8 empty] | 167794.1257 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 5932640.972 | 5932640.972 | 7388644.5693 |  | 80.03: 5932640.972 |  | 0 | 5932640.972 | 80.04 | 0 | 0 | 0 | 5932640.972 | 0 | 0 | 0 | 0
8 | 80.04 | MOS CM's/RE's |  |  | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.04 | YB\MOS RE/ARE | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 503382.3772 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 167794.1257 | 167794.1257 | [8 empty] | 671176.5029 | 167794.1257 | 167794.1257 | 83897.0629 | 0 | [8 empty] | 419485.3143 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2936397.2002 | 2936397.2002 | 3657055.1512 |  | 80.03: 2936397.2002 |  | 0 | 2936397.2002 | 80.04 | 0 | 0 | 0 | 2936397.2002 | 0 | 0 | 0 | 0
9 | 80.04 | MOS Staff |  |  | Various | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.04 | YB\MOS Staff (OE,IE,Insp) | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298673.5438 | 298673.5438 | 298673.5438 | [8 empty] | 896020.6314 | 298673.5438 | 298673.5438 | 298673.5438 | 298673.5438 | [8 empty] | 1194694.1752 | 298673.5438 | 332232.3689 | 332232.3689 | 332232.3689 | [8 empty] | 1295370.6506 | 332232.3689 | 332232.3689 | 332232.3689 | 332232.3689 | [8 empty] | 1328929.4758 | 332232.3689 | 167794.1257 | 0 | 0 | [8 empty] | 500026.4947 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 5215041.4276 | 5215041.4276 | 6494929.9485 |  | 80.03: 5215041.4276 |  | 0 | 5215041.4276 | 80.04 | 0 | 0 | 0 | 5215041.4276 | 0 | 0 | 0 | 0
| 80.04 | STS CM's/RE's |  |  | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.04 | STS RE/ARE | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 251691.1886 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 83897.0629 | 0 | [8 empty] | 251691.1886 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1845735.383 | 1845735.383 | 2298720.3807 |  | 80.03: 1845735.383 |  | 0 | 1845735.383 | 80.04 | 0 | 0 | 0 | 1845735.383 | 0 | 0 | 0 | 0
| 80.04 | STS Staff |  |  | Various | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.04 | STS Staff (OE,IE,Insp) | TBD | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 251691.1886 | 83897.0629 | 83897.0629 | 83897.0629 | 83897.0629 | [8 empty] | 335588.2515 | 83897.0629 | 83897.0629 | 257284.3261 | 257284.3261 | [8 empty] | 682362.778 | 257284.3261 | 257284.3261 | 257284.3261 | 257284.3261 | [8 empty] | 1029137.3045 | 257284.3261 | 257284.3261 | 257284.3261 | 257284.3261 | [8 empty] | 1029137.3045 | 257284.3261 | 167794.1257 | 0 | 0 | [8 empty] | 425078.4518 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 3752995.2788 | 3752995.2788 | 4674064.7742 |  | 80.03: 3752995.2788 |  | 0 | 3752995.2788 | 80.04 | 0 | 0 | 0 | 3752995.2788 | 0 | 0 | 0 | 0
| 80.08 | Start-Up, Testing and Commissioning |  |  | Various | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.08 | Start-Up, Testing and Commissioning | 0 | PM/CM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 229318.6385 | 229318.6385 | [8 empty] | 458637.277 | 251691.1886 | 251691.1886 | 384528.2048 | 0 | [8 empty] | 887910.582 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1346547.859 | 1346547.859 | 1677021.005 |  | 80.03: 1346547.859 |  | 0 | 1346547.859 | 80.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346547.859
[19 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [18 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtotals: Group: Central Subway Partnership - Program Management/Construction Management |  |  |  |  | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 822107.319 | 9865287.828 | 936962.3981 | 936962.3981 | 936962.3981 | 936962.3981 | 936962.3981 | 936962.3981 | 964928.0857 | 964928.0857 | 964928.0857 | 1171594.5172 | 1171594.5172 | 1171594.5172 | 12031342.1971 | 1058333.4823 | 1058333.4823 | 1058333.4823 | 1058333.4823 | 1058333.4823 |  |  |  |  | 1077713.7039 | 1077713.7039 | 1077713.7039 | 1077713.7039 | 1077713.7039 | 1094772.7733 | 1094772.7733 | 12869781.4776 | 3228386.9447 | 4980157.6173 | 5147951.743 | 5147951.743 | [8 empty] | 18504448.048 | 4725921.5511 | 4725921.5511 | 4222539.1739 | 4222539.1739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17896921.4501 | 4180590.6425 | 4081032.7946 | 4086625.9321 | 4002728.8692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16350978.2384 | 3751037.6806 | 3667140.6178 | 2316397.9057 | 2316397.9057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12050974.1098 | 2316397.9057 | 2038698.6276 | 2016326.0775 | 1817769.6954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8189192.3061 | 1389894.6748 | 1132610.3487 | 929859.1134 | 461433.8458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3913797.9826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84484426.201 | 111672723.6379 | 139079723 |  |  | 0 | 111672723.6379 | 0 | 0 | 0 | 0 | 0 |  |  | 5291667.4117 | 84484426.201 |  | 0 | 0 | 31124495.9352 | 52013382.4069 | 0 | 0 | 0 | 1346547.859
[155 empty] | 0 | 0
[155 empty] | 0 | 0
[155 empty] | 0 | 0
|  | Group: PCC | [152 empty] | 0 | 0
| 80.03 | Estimating | 150 | 200 | Various | PCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18835.7616 | 18835.7616 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 75826.0146 | 909912.1757 | 33002.8302 | 33002.8302 | 33002.8302 | 33002.8302 | 33002.8302 | 80.03 | Estimating | C.J.Dombrowski | PCC | 33002.8302 | 33002.8302 | 33002.8302 | 33002.8302 | 33002.8302 | 33002.8302 | 33002.8302 | 396033.9618 | 58600.1472 | 58600.1472 | 58600.1472 | 58600.1472 | [8 empty] | 234400.5888 | 60853.999 | 60853.999 | 60853.999 | 60853.999 | [8 empty] | 243415.9961 | 60853.999 | 60853.999 | 60853.999 | 60853.999 | [8 empty] | 243415.9961 | 60853.999 | 60853.999 | 60853.999 | 60853.999 | [8 empty] | 243415.9961 | 60853.999 | 60853.999 | 60853.999 | 60853.999 | [8 empty] | 243415.9961 | 50228.6976 | 50228.6976 | 50228.6976 | 50228.6976 | [8 empty] | 200914.7904 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1639999.1745 | 2733761.2626 | 2722877.884 | 80.03 | 80.03: 2733761.2626 |  | 165014.1508 | 1639999.1745 | 80.03 | 0 | 0 | 1639999.1745 | 0 | 0 | 0 | 0 | 0
| 80.03 | Cost Schedule | 150 | 320 | Various | PCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22538.5182 | 22538.5182 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 40730.3221 | 488763.8651 | 35739.6502 | 35739.6502 | 35739.6502 | 35739.6502 | 35739.6502 | 80.03 | Cost /Schedule | Various* (see detailsbelow) | PCC | 35739.6502 | 35739.6502 | 35739.6502 | 35739.6502 | 35739.6502 | 35739.6502 | 35739.6502 | 428875.8026 | 106574.993 | 106574.993 | 106574.993 | 106574.993 | [8 empty] | 426299.9719 | 106574.993 | 106574.993 | 106574.993 | 106574.993 | [8 empty] | 426299.9719 | 106574.993 | 106574.993 | 106574.993 | 106574.993 | [8 empty] | 426299.9719 | 106574.993 | 106574.993 | 106574.993 | 106574.993 | [8 empty] | 426299.9719 | 106574.993 | 106574.993 | 106574.993 | 106574.993 | [8 empty] | 426299.9719 | 23182.4758 | 23182.4758 | 23182.4758 | 23182.4758 | [8 empty] | 92729.9033 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2474407.3144 | 3164407.9488 | 3151810.1224 | 80.03 | 80.03: 3164407.9488 |  | 178698.2511 | 2474407.3144 | 80.03 | 0 | 0 | 2474407.3144 | 0 | 0 | 0 | 0 | 0
| 80.03 | Systems/Project Reporting | 305 | 431 | Various | PCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26080.2853 | 26080.2853 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 103033.2258 | 1236398.7101 | 92246.935 | 92246.935 | 92246.935 | 92246.935 | 92246.935 | 80.03 | Systems/Project Reporting | Various* (see detailsbelow) | PCC | 92246.935 | 92246.935 | 92246.935 | 92246.935 | 92246.935 | 92246.935 | 92246.935 | 1106963.2202 | 275774.8686 | 275774.8686 | 275774.8686 | 275774.8686 | [8 empty] | 1103099.4742 | 275774.8686 | 275774.8686 | 275774.8686 | 275774.8686 | [8 empty] | 1103099.4742 | 275774.8686 | 275774.8686 | 275774.8686 | 275774.8686 | [8 empty] | 1103099.4742 | 275774.8686 | 275774.8686 | 275774.8686 | 275774.8686 | [8 empty] | 1103099.4742 | 275774.8686 | 275774.8686 | 275774.8686 | 275774.8686 | [8 empty] | 1103099.4742 | 95144.7445 | 95144.7445 | 95144.7445 | 95144.7445 | [8 empty] | 380578.978 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 6541804.8941 | 8265518.5646 | 8232612.7036 | 80.03 | 80.03: 8265518.5646 |  | 461234.6751 | 6541804.8941 | 80.03 | 0 | 0 | 6541804.8941 | 0 | 0 | 0 | 0 | 0
| 80.03 | Contract Admin | 305 | 432 | Various | PCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18030.8145 | 18030.8145 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 22377.5287 | 268530.3449 | 35900.6396 | 35900.6396 | 35900.6396 | 35900.6396 | 35900.6396 | 80.03 | Contract Admin | TBD | PCC | 35900.6396 | 35900.6396 | 35900.6396 | 35900.6396 | 35900.6396 | 35900.6396 | 35900.6396 | 430807.6756 | 107701.9189 | 107701.9189 | 107701.9189 | 107701.9189 | [8 empty] | 430807.6756 | 107540.9295 | 107540.9295 | 107540.9295 | 107540.9295 | [8 empty] | 430163.7179 | 107540.9295 | 107540.9295 | 107540.9295 | 107540.9295 | [8 empty] | 430163.7179 | 107540.9295 | 107540.9295 | 107540.9295 | 107540.9295 | [8 empty] | 430163.7179 | 107540.9295 | 107540.9295 | 107540.9295 | 107540.9295 | [8 empty] | 430163.7179 | 37188.555 | 37188.555 | 37188.555 | 37188.555 | [8 empty] | 148754.2198 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 2551521.2444 | 3017585.6019 | 3005572.2901 | 80.03 | 80.03: 3017585.6019 |  | 179503.1982 | 2551521.2444 | 80.03 | 0 | 0 | 2551521.2444 | 0 | 0 | 0 | 0 | 0
| 80.03 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.03 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 80.03 | 80.03: 0 |  | 0 | 0 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtotals: Group: PCC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85485.3796 | 85485.3796 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 241967.0913 | 2903605.0958 | 196890.055 | 196890.055 | 196890.055 | 196890.055 | 196890.055 |  |  |  |  | 196890.055 | 196890.055 | 196890.055 | 196890.055 | 196890.055 | 196890.055 | 196890.055 | 2362680.6602 | 548651.9276 | 548651.9276 | 548651.9276 | 548651.9276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2194607.7105 | 550744.79 | 550744.79 | 550744.79 | 550744.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2202979.1601 | 550744.79 | 550744.79 | 550744.79 | 550744.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2202979.1601 | 550744.79 | 550744.79 | 550744.79 | 550744.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2202979.1601 | 550744.79 | 550744.79 | 550744.79 | 550744.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2202979.1601 | 205744.4729 | 205744.4729 | 205744.4729 | 205744.4729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822977.8914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13207732.6274 | 17181273.3779 | 17112873 |  |  | 0 | 17181273.3779 | 0 | 0 | 0 | 0 | 0 |  |  | 984450.2751 | 13207732.6274 |  | 0 | 0 | 13207732.6274 | 0 | 0 | 0 | 0 | 0
Group: PB Telamon - Final Design for Utility Relocations and Tunnel (DP1)
1 | 80.02 | Project Managers | 150 | 200 | Various | DP1 | 17668.1211 | 18711.8398 | 14620.9716 | 15378.3041 | 18486.5493 | 23790.4222 | 19717.3736 | 14116.9318 | 12398.6145 | 9802.046 | 7771.8858 | 7771.8858 | 180234.9455 | 6499.0581 | 5862.6443 | 5862.6443 | 4824.0169 | 4938.5714 | 5053.1259 | 5053.1259 | 5053.1259 | 6593.2474 | 3388.2673 | 3273.7128 | 3273.7128 | 59675.2531 | 4668.7319 | 4668.7319 | 4378.5272 | 7084.5589 | 7084.5589 | 80.03 | Project Managers | 0 | DP1 | 6855.4499 | 8281.0169 | 7937.3534 | 7708.2444 | 7708.2444 | 7708.2444 | 7708.2444 | 81791.9069 | 14690.9771 | 14690.9771 | 11839.8431 | 11839.8431 | [8 empty] | 53061.6404 | 6137.5751 | 6137.5751 | 6137.5751 | 0 | [8 empty] | 18412.7253 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125381.1637 | 393176.4711 | 393176.4711 | 80.02 | 80.02: 393176.4711 |  | 27885.1089 | 125381.1637 | 80.02 | 0 | 125381.1637 | 0 | 0 | 0 | 0 | 0 | 0
2 | 80.02 | Project Controls and Admin | 150 | 320 | Various | DP1 | 10412.7487 | 11125.5322 | 15505.0777 | 16650.6226 | 23576.8417 | 30795.8112 | 30286.6801 | 31070.742 | 45756.6278 | 42925.859 | 37770.9069 | 34716.1205 | 330593.5704 | 27842.851 | 31024.9202 | 36816.2861 | 34116.8732 | 114305.0172 | 21388.5964 | 15024.458 | 15024.458 | 15285.3876 | 6423.4522 | 6448.9087 | 6448.9087 | 330150.1173 | 5659.501 | 5659.501 | 4195.24 | 3794.0448 | 14027.5793 | 80.03 | Project Controls and Admin | 0 | DP1 | 3946.7841 | 4105.8875 | 4105.8875 | 4360.4531 | 4360.4531 | 4309.54 | 4436.8227 | 62961.6941 | 4385.6551 | 4385.6551 | 4067.4481 | 4067.4481 | [8 empty] | 16906.2064 | 2794.6205 | 2794.6205 | 2794.6205 | 0 | [8 empty] | 8383.8614 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54915.8958 | 748995.4496 | 748995.4496 | 80.02 | 80.02: 748995.4496 |  | 33335.8661 | 54915.8958 | 80.02 | 0 | 54915.8958 | 0 | 0 | 0 | 0 | 0 | 0
3 | 80.02 | Geo-Engineers | 150 | 320 | Various | DP1 | 46431.481 | 66523.066 | 109307.8957 | 127343.864 | 133629.0871 | 107368.1063 | 102022.23 | 72101.8697 | 76937.3421 | 38062.639 | 24163.3607 | 27218.1472 | 931109.0888 | 12771.553 | 5452.7938 | 4880.0213 | 4429.4403 | 5880.4639 | 5995.0184 | 5995.0184 | 3322.0803 | 6325.9536 | 5088.7651 | 4974.2106 | 4974.2106 | 70089.5292 | 9306.916 | 9306.916 | 9291.6421 | 17735.5809 | 17735.5809 | 80.03 | Geo-Engineers | 0 | DP1 | 17506.4719 | 21732.2598 | 21388.5964 | 21159.4874 | 21159.4874 | 21159.4874 | 21159.4874 | 208641.9137 | 42280.7899 | 42280.7899 | 33829.2141 | 33829.2141 | [8 empty] | 152220.0082 | 16926.0625 | 16926.0625 | 16926.0625 | 0 | [8 empty] | 50778.1876 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348263.4735 | 1412838.7273 | 1412838.7273 | 80.02 | 80.02: 1412838.7273 |  | 63376.636 | 348263.4735 | 80.02 | 0 | 348263.4735 | 0 | 0 | 0 | 0 | 0 | 0
4 | 80.02 | Civil Engineers | 305 | 431 | Various | DP1 | 44867.1758 | 52045.9239 | 91058.0924 | 95131.141 | 131075.7947 | 78698.9356 | 48469.2781 | 32991.6935 | 33844.4881 | 24896.5095 | 16786.0515 | 18608.7407 | 668473.8248 | 18023.24 | 17259.5434 | 14433.8659 | 10093.5235 | 11480.9057 | 12753.7334 | 12753.7334 | 12524.6244 | 13759.2672 | 9495.2945 | 8222.4668 | 8222.4668 | 149022.665 | 9508.0228 | 9508.0228 | 9380.74 | 19652.4594 | 17004.9778 | 80.03 | Civil Engineers | 0 | DP1 | 6924.1826 | 7000.5523 | 3182.0692 | 636.4138 | 636.4138 | 636.4138 | 636.4138 | 84706.6823 | 11137.2422 | 11137.2422 | 801.8814 | 801.8814 | [8 empty] | 23878.2473 | 496.4028 | 496.4028 | 496.4028 | 0 | [8 empty] | 1489.2084 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45019.9151 | 927570.6278 | 927570.6278 | 80.02 | 80.02: 927570.6278 |  | 65054.2228 | 45019.9151 | 80.02 | 0 | 45019.9151 | 0 | 0 | 0 | 0 | 0 | 0
5 | 80.02 | Structural Engineers | 305 | 432 | Various | DP1 | 0 | 0 | 0 | 0 | 0 | 37444.0448 | 39518.7539 | 157189.1275 | 156450.8874 | 191741.3077 | 184506.5552 | 170632.7334 | 937483.4098 | 127305.6791 | 28152.4027 | 11580.1863 | 13871.2761 | 38693.9615 | 28126.9461 | 25072.1597 | 25072.1597 | 23063.6376 | 24234.6391 | 24260.0956 | 3894.8527 | 373327.9962 | 1603.7629 | 1318.6495 | 1293.1929 | 1293.1929 | 26426.4483 | 80.03 | Structural Engineers | 0 | DP1 | 2436.1922 | 2436.1922 | 2431.1009 | 4668.7319 | 4668.7319 | 4617.8188 | 5737.9072 | 58931.9217 | 15793.2459 | 7647.1487 | 25975.8673 | 25975.8673 | [8 empty] | 75392.1293 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102388.8044 | 1445135.4569 | 1445135.4569 | 80.02 | 80.02: 1445135.4569 |  | 31935.2465 | 102388.8044 | 80.02 | 0 | 102388.8044 | 0 | 0 | 0 | 0 | 0 | 0
6 | 80.02 | Environmental & Hydrology |  |  | Various | DP1 | 9826.2297 | 11022.6877 | 14382.9528 | 21739.8968 | 23929.1604 | 30624.234 | 31642.4962 | 29020.4712 | 33118.9763 | 22783.6155 | 17717.7613 | 15172.106 | 260980.588 | 5498.6156 | 661.8704 | 661.8704 | 458.218 | 509.1311 | 560.0442 | 560.0442 | 560.0442 | 1069.1753 | 814.6097 | 763.6966 | 763.6966 | 12881.0161 | 1272.8277 | 1272.8277 | 1272.8277 | 2189.2636 | 2189.2636 | 80.03 | Environmental & Hydrology | 0 | DP1 | 2087.4374 | 2545.6554 | 2392.916 | 2291.0898 | 2291.0898 | 2291.0898 | 2291.0898 | 24387.3784 | 4582.1797 | 4582.1797 | 3665.7437 | 3665.7437 | [8 empty] | 16495.8468 | 1832.8719 | 1832.8719 | 1832.8719 | 0 | [8 empty] | 5498.6156 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38184.8305 | 320243.4449 | 320243.4449 | 80.02 | 80.02: 320243.4449 |  | 8197.0103 | 38184.8305 | 80.02 | 0 | 38184.8305 | 0 | 0 | 0 | 0 | 0 | 0
7 | 80.02 | Architectural & Landscaping |  |  | Various | DP1 | 1400.1105 | 1400.1105 | 1400.1105 | 2800.2209 | 2800.2209 | 4200.3314 | 4200.3314 | 4200.3314 | 4327.6141 | 1654.676 | 381.8483 | 381.8483 | 29147.7539 | 127.2828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.3697 | 76.3697 | 76.3697 | 76.3697 | 432.7614 | 152.7393 | 152.7393 | 152.7393 | 305.4786 | 305.4786 | 80.03 | Architectural & Landscaping | 0 | DP1 | 305.4786 | 381.8483 | 381.8483 | 381.8483 | 381.8483 | 381.8483 | 381.8483 | 3665.7437 | 763.6966 | 763.6966 | 610.9573 | 610.9573 | [8 empty] | 2749.3078 | 305.4786 | 305.4786 | 305.4786 | 0 | [8 empty] | 916.4359 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6262.3122 | 36912.0028 | 36912.0028 | 80.02 | 80.02: 36912.0028 |  | 1069.1753 | 6262.3122 | 80.02 | 0 | 6262.3122 | 0 | 0 | 0 | 0 | 0 | 0
8 | 80.02 | CAD |  |  | Various | DP1 | 7509.6833 | 8655.2282 | 10946.3181 | 17310.4565 | 17310.4565 | 23929.1604 | 26474.8158 | 24871.0529 | 24641.9439 | 11455.4491 | 2545.6554 | 0 | 175650.2202 | 0 | 0 | 0 | 203.6524 | 254.5655 | 305.4786 | 305.4786 | 305.4786 | 560.0442 | 560.0442 | 509.1311 | 509.1311 | 3513.0044 | 763.6966 | 763.6966 | 763.6966 | 1171.0015 | 1171.0015 | 80.03 | CAD | 0 | DP1 | 1069.1753 | 1272.8277 | 1120.0884 | 1018.2621 | 1018.2621 | 1018.2621 | 1018.2621 | 12168.2326 | 2036.5243 | 2036.5243 | 1629.2194 | 1629.2194 | [8 empty] | 7331.4874 | 814.6097 | 814.6097 | 814.6097 | 0 | [8 empty] | 2443.8291 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17310.4565 | 201106.7738 | 201106.7738 | 80.02 | 80.02: 201106.7738 |  | 4633.0928 | 17310.4565 | 80.02 | 0 | 17310.4565 | 0 | 0 | 0 | 0 | 0 | 0
9 | [5 empty] | DP1 | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [5 empty] | DP1 | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtotals - Group: PB Telamon - Final Design for Utility Relocations and Tunnel (DP1) |  |  |  |  | 138115.5501 | 169484.3883 | 257221.4187 | 296354.5058 | 350808.1106 | 336851.0459 | 302331.9592 | 365562.2199 | 387476.4941 | 343322.1018 | 291644.0251 | 274501.5819 | 3513673.4013 | 198068.2796 | 88414.1747 | 74234.8743 | 67997.0004 | 176062.6163 | 74182.943 | 64764.0181 | 61861.971 | 66733.0826 | 50081.4417 | 48528.5919 | 28163.349 | 999092.3427 | 32936.1982 | 32651.0848 | 30728.6059 | 53225.5806 | 85944.889 |  |  |  |  | 41131.172 | 47756.2401 | 42939.8601 | 42224.531 | 42224.531 | 42122.7048 | 43370.0759 | 537255.4734 | 95670.3108 | 87524.2136 | 82420.1746 | 82420.1746 | [8 empty] | 348034.8736 | 29307.6211 | 29307.6211 | 29307.6211 | 0 | [8 empty] | 87922.8632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 737726.8516 | 5485978.9542 | 5485978.9542 |  |  | 5485978.9542 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 235486.3586 | 737726.8516 |  | 0 | 737726.8516 | 0 | 0 | 0 | 0 | 0 | 0
[155 empty] | 0 | 0
|  | Group: CSDG - Final Design for Stations (DP2) | [152 empty] | 0 | 0
1 | 80.02 | Principal in Charge | 150 | 200 | R Hornbuckle | DP2 |  |  |  | 1301.6582 | 2733.4822 | 4360.555 | 4360.555 | 4360.555 | 4360.555 | 4360.555 | 4360.555 | 4360.555 | 34559.0254 | 4360.555 | 4360.555 | 4360.555 | 4360.555 | 4360.555 | 4360.555 | 4360.555 | 0 | 0 | 0 | 0 | 0 | 30523.885 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 65082.9104 | 65082.9104 | 80.02 | 80.02: 65082.9104 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 80.02 | Project Manager | 150 | 320 | N Munfah | DP2 |  |  |  | 6096.0993 | 12801.8085 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 161859.0288 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 0 | 0 | 0 | 0 | 0 | 142961.121 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 304820.1498 | 304820.1498 | 80.02 | 80.02: 304820.1498 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 80.02 | Deputy Project Manager | 150 | 320 | A Read | DP2 |  |  |  | 6096.0993 | 12801.8085 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 161859.0288 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 0 | 0 | 0 | 0 | 0 | 142961.121 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 304820.1498 | 304820.1498 | 80.02 | 80.02: 304820.1498 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 80.02 | Package Manager - UMS | 305 | 431 |  | DP2 |  |  |  | 6096.0993 | 12801.8085 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 161859.0288 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 0 | 0 | 0 | 0 | 0 | 142961.121 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 304820.1498 | 304820.1498 | 80.02 | 80.02: 304820.1498 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 80.02 | Package Manager - CTS | 305 | 432 |  | DP2 |  |  |  | 6096.0993 | 12801.8085 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 161859.0288 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 0 | 0 | 0 | 0 | 0 | 142961.121 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 304820.1498 | 304820.1498 | 80.02 | 80.02: 304820.1498 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 80.02 | Package Manager - MOS |  |  |  | DP2 |  |  |  | 6096.0993 | 12801.8085 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 161859.0288 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 20423.0173 | 0 | 0 | 0 | 0 | 0 | 142961.121 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 304820.1498 | 304820.1498 | 80.02 | 80.02: 304820.1498 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Manager/Sr Specialist |  |  | Various | DP2 |  |  |  | 34359.4378 | 72153.0839 | 115096.9577 | 115096.9577 | 115096.9577 | 115096.9577 | 115096.9577 | 115096.9577 | 115096.9577 | 912191.2254 | 115096.9577 | 115096.9577 | 115096.9577 | 115096.9577 | 115096.9577 | 115096.9577 | 115096.9577 | 0 | 0 | 0 | 0 | 0 | 805678.7036 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 1717869.9289 | 1717869.9289 | 80.02 | 80.02: 1717869.9289 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Senior Technical |  |  | Various | DP2 |  |  |  | 166905.1238 | 350501.8447 | 559131.6223 | 559131.6223 | 559131.6223 | 559131.6223 | 559131.6223 | 559131.6223 | 559131.6223 | 4431328.3247 | 559131.6223 | 559131.6223 | 559131.6223 | 559131.6223 | 559131.6223 | 559131.6223 | 559131.6223 | 0 | 0 | 0 | 0 | 0 | 3913921.3562 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 8345249.6809 | 8345249.6809 | 80.02 | 80.02: 8345249.6809 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Staff Technical |  |  | Various | DP2 |  |  |  | 126234.8131 | 265091.3719 | 422882.7188 | 422882.7188 | 422882.7188 | 422882.7188 | 422882.7188 | 422882.7188 | 422882.7188 | 3351505.2164 | 422882.7188 | 422882.7188 | 422882.7188 | 422882.7188 | 422882.7188 | 422882.7188 | 422882.7188 | 0 | 0 | 0 | 0 | 0 | 2960179.0314 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 6311684.2478 | 6311684.2478 | 80.02 | 80.02: 6311684.2478 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Technician |  |  | Various | DP2 |  |  |  | 97450.8112 | 204646.7035 | 326460.2176 | 326460.2176 | 326460.2176 | 326460.2176 | 326460.2176 | 326460.2176 | 326460.2176 | 2587319.0376 | 326460.2176 | 326460.2176 | 326460.2176 | 326460.2176 | 326460.2176 | 326460.2176 | 326460.2176 | 0 | 0 | 0 | 0 | 0 | 2285221.5229 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 4872540.5605 | 4872540.5605 | 80.02 | 80.02: 4872540.5605 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Support Staff |  |  | Various | DP2 |  |  |  | 9968.5324 | 20935.0029 | 33394.0413 | 33394.0413 | 33394.0413 | 33394.0413 | 33394.0413 | 33394.0413 | 33394.0413 | 264661.8247 | 33394.0413 | 33394.0413 | 33394.0413 | 33394.0413 | 33394.0413 | 33394.0413 | 33394.0413 | 0 | 0 | 0 | 0 | 0 | 233758.2894 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 498420.114 | 498420.114 | 80.02 | 80.02: 498420.114 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Trainee |  |  | Various | DP2 |  |  |  | 50113.841 | 105239.0662 | 167881.3674 | 167881.3674 | 167881.3674 | 167881.3674 | 167881.3674 | 167881.3674 | 167881.3674 | 1330522.4793 | 167881.3674 | 167881.3674 | 167881.3674 | 167881.3674 | 167881.3674 | 167881.3674 | 167881.3674 | 0 | 0 | 0 | 0 | 0 | 1175169.5721 | 0 | 0 | 0 | 0 | 0 | 80.02 | 0 | 0 | DP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 2505692.0513 | 2505692.0513 | 80.02 | 80.02: 2505692.0513 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 80.02 | Support During Construction |  |  | Various | DP2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24406.0914 | 24406.0914 | 48812.1828 | 24406.0914 | 24406.0914 | 24406.0914 | 24406.0914 | 168809.8836 | 80.03 | Support During Construction | 0 | DP2 | 168809.8836 | 168809.8836 | 168809.8836 | 144403.7922 | 144403.7922 | 240672.2639 | 240672.2639 | 1543016.0124 | 561570.062 | 481331.5112 | 455580.373 | 455580.373 | [8 empty] | 1954062.3192 | 433211.3767 | 433211.3767 | 433211.3767 | 433211.3767 | [8 empty] | 1732845.5066 | 433211.3767 | 433211.3767 | 433211.3767 | 433211.3767 | [8 empty] | 1732845.5066 | 433211.3767 | 433211.3767 | 433211.3767 | 0 | [8 empty] | 1299634.13 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 7995969.2255 | 8311215.6576 | 8311215.6576 | 80.02 | 80.02: 8311215.6576 |  | 266434.2493 | 7995969.2255 | 80.02 | 0 | 7995969.2255 | 0 | 0 | 0 | 0 | 0 | 0
8 | [18 empty] | 0 | [12 empty] | 0 | [8 empty] | 0 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [18 empty] | 0 | [12 empty] | 0 | [8 empty] | 0 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [18 empty] | 0 | [12 empty] | 0 | [8 empty] | 0 | [7 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtotals - Group: Central Subway Design Group (CSDG) - Final Design for Stations (DP2) |  |  |  |  | 0 | 0 | 0 | 516814.714 | 1085309.5977 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 13721382.2774 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 1731322.5665 | 0 | 0 | 0 | 24406.0914 | 24406.0914 | 12168070.1486 | 24406.0914 | 24406.0914 | 24406.0914 | 24406.0914 | 168809.8836 |  |  |  |  | 168809.8836 | 168809.8836 | 168809.8836 | 144403.7922 | 144403.7922 | 240672.2639 | 240672.2639 | 1543016.0124 | 561570.062 | 481331.5112 | 455580.373 | 455580.373 | [8 empty] | 1954062.3192 | 433211.3767 | 433211.3767 | 433211.3767 | 433211.3767 | [8 empty] | 1732845.5066 | 433211.3767 | 433211.3767 | 433211.3767 | 433211.3767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1732845.5066 | 433211.3767 | 433211.3767 | 433211.3767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1299634.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7995969.2255 | 34151855.9007 | 34151855.9007 |  |  | 34151855.9007 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 266434.2493 | 7995969.2255 |  | 0 | 7995969.2255 | 0 | 0 | 0 | 0 | 0 | 0
[155 empty] | 0 | 0
[155 empty] | 0 | 0
[155 empty] | 0 | 0
|  | Group: HNTB-B&C Transit - Final Design for Surface, Trackway & Systems (DP3) | [152 empty] | 0 | 0
1 | 80.02 | Project Managers | 150 | 200 | Various | DP3 |  |  |  | 0 | 20077.7223 | 20077.7223 | 20077.7223 | 20077.7223 | 20077.7223 | 40155.4445 | 40155.4445 | 40155.4445 | 220854.9448 | 40155.4445 | 40155.4445 | 40155.4445 | 40155.4445 | 40155.4445 | 20077.7223 | 20077.7223 | 20077.7223 | 20077.7223 | 20077.7223 | 20077.7223 | 20077.7223 | 341321.2783 | 20077.7223 | 15096.0318 | 15096.0318 | 15096.0318 | 15096.0318 | 80.03 | Project Managers | 0 | DP3 | 15096.0318 | 15096.0318 | 15096.0318 | 15096.0318 | 15096.0318 | 15096.0318 | 15096.0318 | 186134.0717 | 26870.9366 | 26870.9366 | 26870.9366 | 26870.9366 | [8 empty] | 107483.7462 | 26870.9366 | 26870.9366 | 26870.9366 | 26870.9366 | [8 empty] | 107483.7462 | 50584.655 | 50584.655 | 50584.655 | 50584.655 | [8 empty] | 202338.6199 | 50584.655 | 50584.655 | 50584.655 | 50584.655 | [8 empty] | 202338.6199 | 50584.655 | 50584.655 | 50584.655 | 50584.655 | [8 empty] | 202338.6199 | 27666.0048 | 27666.0048 | 27666.0048 | 27666.0048 | [8 empty] | 110664.0193 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1038319.5937 | 1680957.6661 | 1680957.6661 | 80.02 | 80.02: 1680957.6661 |  | 80461.8493 | 1038319.5937 | 80.02 | 0 | 1038319.5937 | 0 | 0 | 0 | 0 | 0 | 0
2 | 80.02 | Integration Coord & Quality Control | 150 | 320 | Various | DP3 |  |  |  | 0 | 37509.0249 | 37509.0249 | 37509.0249 | 37509.0249 | 37509.0249 | 75018.0498 | 75018.0498 | 75018.0498 | 412599.2741 | 75018.0498 | 75018.0498 | 75018.0498 | 75018.0498 | 75018.0498 | 37509.0249 | 37509.0249 | 37509.0249 | 37509.0249 | 37509.0249 | 37509.0249 | 37509.0249 | 637653.4237 | 37509.0249 | 28202.2744 | 28202.2744 | 28202.2744 | 28202.2744 | 80.03 | Integration Coord & Quality Control | 0 | DP3 | 28202.2744 | 28202.2744 | 28202.2744 | 28202.2744 | 28202.2744 | 28202.2744 | 28202.2744 | 347734.0431 | 50200.0484 | 50200.0484 | 50200.0484 | 50200.0484 | [8 empty] | 200800.1936 | 50200.0484 | 50200.0484 | 50200.0484 | 50200.0484 | [8 empty] | 200800.1936 | 50200.0484 | 50200.0484 | 50200.0484 | 50200.0484 | [8 empty] | 200800.1936 | 50200.0484 | 50200.0484 | 50200.0484 | 50200.0484 | [8 empty] | 200800.1936 | 50200.0484 | 50200.0484 | 50200.0484 | 50200.0484 | [8 empty] | 200800.1936 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1201416.8885 | 2401987.7088 | 2401987.7088 | 80.02 | 80.02: 2401987.7088 |  | 150318.1224 | 1201416.8885 | 80.02 | 0 | 1201416.8885 | 0 | 0 | 0 | 0 | 0 | 0
3 | 80.02 | Project Controls & Admin | 150 | 320 | Various | DP3 |  |  |  | 0 | 40254.4093 | 40254.4093 | 40254.4093 | 40254.4093 | 40254.4093 | 80508.8186 | 80508.8186 | 80508.8186 | 442798.5026 | 80508.8186 | 80508.8186 | 80508.8186 | 80508.8186 | 80508.8186 | 40254.4093 | 40254.4093 | 40254.4093 | 40254.4093 | 40254.4093 | 40254.4093 | 40254.4093 | 684324.9585 | 40254.4093 | 30266.4732 | 30266.4732 | 30266.4732 | 30266.4732 | 80.03 | Project Controls & Admin | 0 | DP3 | 30266.4732 | 30266.4732 | 30266.4732 | 30266.4732 | 30266.4732 | 30266.4732 | 30266.4732 | 373185.6143 | 53874.3223 | 53874.3223 | 53874.3223 | 53874.3223 | [8 empty] | 215497.289 | 53874.3223 | 53874.3223 | 53874.3223 | 53874.3223 | [8 empty] | 215497.289 | 94539.2919 | 94539.2919 | 94539.2919 | 94539.2919 | [8 empty] | 378157.1674 | 94539.2919 | 94539.2919 | 94539.2919 | 94539.2919 | [8 empty] | 378157.1674 | 94539.2919 | 94539.2919 | 94539.2919 | 94539.2919 | [8 empty] | 378157.1674 | 47442.4645 | 47442.4645 | 47442.4645 | 47442.4645 | [8 empty] | 189769.8581 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1967101.2506 | 3255545.0138 | 3255545.0138 | 80.02 | 80.02: 3255545.0138 |  | 161320.302 | 1967101.2506 | 80.02 | 0 | 1967101.2506 | 0 | 0 | 0 | 0 | 0 | 0
4 | 80.02 | Civil/Track & Utilities | 305 | 431 | Various | DP3 |  |  |  | 0 | 27184.3584 | 27184.3584 | 27184.3584 | 27184.3584 | 27184.3584 | 54368.7169 | 54368.7169 | 54368.7169 | 299027.9427 | 54368.7169 | 54368.7169 | 54368.7169 | 54368.7169 | 54368.7169 | 27184.3584 | 27184.3584 | 27184.3584 | 27184.3584 | 27184.3584 | 27184.3584 | 27184.3584 | 462134.0933 | 27184.3584 | 20439.3672 | 20439.3672 | 20439.3672 | 20439.3672 | 80.03 | Civil/Track & Utilities | 0 | DP3 | 20439.3672 | 20439.3672 | 20439.3672 | 20439.3672 | 20439.3672 | 20439.3672 | 20439.3672 | 252017.3981 | 36382.0737 | 36382.0737 | 36382.0737 | 36382.0737 | [8 empty] | 145528.2948 | 36382.0737 | 36382.0737 | 36382.0737 | 36382.0737 | [8 empty] | 145528.2948 | 36382.0737 | 36382.0737 | 36382.0737 | 36382.0737 | [8 empty] | 145528.2948 | 36382.0737 | 36382.0737 | 36382.0737 | 36382.0737 | [8 empty] | 145528.2948 | 36382.0737 | 36382.0737 | 36382.0737 | 36382.0737 | [8 empty] | 145528.2948 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 870717.0445 | 1740820.9079 | 1740820.9079 | 80.02 | 80.02: 1740820.9079 |  | 108941.8274 | 870717.0445 | 80.02 | 0 | 870717.0445 | 0 | 0 | 0 | 0 | 0 | 0
5 | 80.02 | Structural | 305 | 432 | Various | DP3 |  |  |  | 0 | 3722.2696 | 3722.2696 | 3722.2696 | 3722.2696 | 3722.2696 | 7444.5393 | 7444.5393 | 7444.5393 | 40944.9661 | 7444.5393 | 7444.5393 | 7444.5393 | 7444.5393 | 7444.5393 | 3722.2696 | 3722.2696 | 3722.2696 | 3722.2696 | 3722.2696 | 3722.2696 | 3722.2696 | 63278.584 | 3722.2696 | 2798.699 | 2798.699 | 2798.699 | 2798.699 | 80.03 | Structural | 0 | DP3 | 2798.699 | 2798.699 | 2798.699 | 2798.699 | 2798.699 | 2798.699 | 2798.699 | 34507.9585 | 4981.6842 | 4981.6842 | 4981.6842 | 4981.6842 | [8 empty] | 19926.7368 | 4981.6842 | 4981.6842 | 4981.6842 | 4981.6842 | [8 empty] | 19926.7368 | 4981.6842 | 4981.6842 | 4981.6842 | 4981.6842 | [8 empty] | 19926.7368 | 4981.6842 | 4981.6842 | 4981.6842 | 4981.6842 | [8 empty] | 19926.7368 | 4981.6842 | 4981.6842 | 4981.6842 | 4981.6842 | [8 empty] | 19926.7368 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 119224.5767 | 238365.1925 | 238365.1925 | 80.02 | 80.02: 238365.1925 |  | 14917.0656 | 119224.5767 | 80.02 | 0 | 119224.5767 | 0 | 0 | 0 | 0 | 0 | 0
6 | 80.02 | Environmental and Sustainability | 275 | 420 | Various | DP3 |  |  |  | 0 | 4143.3409 | 4143.3409 | 4143.3409 | 4143.3409 | 4143.3409 | 8286.6818 | 8286.6818 | 8286.6818 | 45576.7496 | 8286.6818 | 8286.6818 | 8286.6818 | 8286.6818 | 8286.6818 | 4143.3409 | 4143.3409 | 4143.3409 | 4143.3409 | 4143.3409 | 4143.3409 | 4143.3409 | 70436.7949 | 4143.3409 | 3115.2939 | 3115.2939 | 3115.2939 | 3115.2939 | 80.03 | Environmental and Sustainability | 0 | DP3 | 3115.2939 | 3115.2939 | 3115.2939 | 3115.2939 | 3115.2939 | 3115.2939 | 3115.2939 | 38411.5737 | 5545.2231 | 5545.2231 | 5545.2231 | 5545.2231 | [8 empty] | 22180.8925 | 5545.2231 | 5545.2231 | 5545.2231 | 5545.2231 | [8 empty] | 22180.8925 | 5545.2231 | 5545.2231 | 5545.2231 | 5545.2231 | [8 empty] | 22180.8925 | 5545.2231 | 5545.2231 | 5545.2231 | 5545.2231 | [8 empty] | 22180.8925 | 5545.2231 | 5545.2231 | 5545.2231 | 5545.2231 | [8 empty] | 22180.8925 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 132711.5198 | 265329.5808 | 265329.5808 | 80.02 | 80.02: 265329.5808 |  | 16604.5164 | 132711.5198 | 80.02 | 0 | 132711.5198 | 0 | 0 | 0 | 0 | 0 | 0
7 | 80.02 | Controls & Comms | 275 | 420 | Various | DP3 |  |  |  | 0 | 16017.5495 | 16017.5495 | 16017.5495 | 16017.5495 | 16017.5495 | 32035.099 | 32035.099 | 32035.099 | 176193.0443 | 32035.099 | 32035.099 | 32035.099 | 32035.099 | 32035.099 | 16017.5495 | 16017.5495 | 16017.5495 | 16017.5495 | 16017.5495 | 16017.5495 | 16017.5495 | 272298.3412 | 16017.5495 | 12043.2703 | 12043.2703 | 12043.2703 | 12043.2703 | 80.03 | Controls & Comms | 0 | DP3 | 12043.2703 | 12043.2703 | 12043.2703 | 12043.2703 | 12043.2703 | 12043.2703 | 12043.2703 | 148493.5227 | 21437.0211 | 21437.0211 | 21437.0211 | 21437.0211 | [8 empty] | 85748.0845 | 21437.0211 | 21437.0211 | 21437.0211 | 21437.0211 | [8 empty] | 85748.0845 | 21437.0211 | 21437.0211 | 21437.0211 | 21437.0211 | [8 empty] | 85748.0845 | 21437.0211 | 21437.0211 | 21437.0211 | 21437.0211 | [8 empty] | 85748.0845 | 21437.0211 | 21437.0211 | 21437.0211 | 21437.0211 | [8 empty] | 85748.0845 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 513043.3143 | 1025725.3305 | 1025725.3305 | 80.02 | 80.02: 1025725.3305 |  | 64190.6306 | 513043.3143 | 80.02 | 0 | 513043.3143 | 0 | 0 | 0 | 0 | 0 | 0
8 | 80.02 | Train Control |  |  | Various | DP3 |  |  |  | 0 | 16219.6637 | 16219.6637 | 16219.6637 | 16219.6637 | 16219.6637 | 32439.3273 | 32439.3273 | 32439.3273 | 178416.3004 | 32439.3273 | 32439.3273 | 32439.3273 | 32439.3273 | 32439.3273 | 16219.6637 | 16219.6637 | 16219.6637 | 16219.6637 | 16219.6637 | 16219.6637 | 16219.6637 | 275734.2824 | 16219.6637 | 12195.2358 | 12195.2358 | 12195.2358 | 12195.2358 | 80.03 | Train Control | 0 | DP3 | 12195.2358 | 12195.2358 | 12195.2358 | 12195.2358 | 12195.2358 | 12195.2358 | 12195.2358 | 150367.258 | 21707.5198 | 21707.5198 | 21707.5198 | 21707.5198 | [8 empty] | 86830.0792 | 21707.5198 | 21707.5198 | 21707.5198 | 21707.5198 | [8 empty] | 86830.0792 | 21707.5198 | 21707.5198 | 21707.5198 | 21707.5198 | [8 empty] | 86830.0792 | 21707.5198 | 21707.5198 | 21707.5198 | 21707.5198 | [8 empty] | 86830.0792 | 21707.5198 | 21707.5198 | 21707.5198 | 21707.5198 | [8 empty] | 86830.0792 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 519517.047 | 1038668.2369 | 1038668.2369 | 80.02 | 80.02: 1038668.2369 |  | 65000.6071 | 519517.047 | 80.02 | 0 | 519517.047 | 0 | 0 | 0 | 0 | 0 | 0
9 | 80.02 | OCS |  |  | Various | DP3 |  |  |  | 0 | 11571.0373 | 11571.0373 | 11571.0373 | 11571.0373 | 11571.0373 | 23142.0746 | 23142.0746 | 23142.0746 | 127281.4106 | 23142.0746 | 23142.0746 | 23142.0746 | 23142.0746 | 23142.0746 | 11571.0373 | 11571.0373 | 11571.0373 | 11571.0373 | 11571.0373 | 11571.0373 | 11571.0373 | 196707.6345 | 11571.0373 | 8700.0281 | 8700.0281 | 8700.0281 | 8700.0281 | 80.03 | OCS | 0 | DP3 | 8700.0281 | 8700.0281 | 8700.0281 | 8700.0281 | 8700.0281 | 8700.0281 | 8700.0281 | 107271.346 | 15486.05 | 15486.05 | 15486.05 | 15486.05 | [8 empty] | 61944.1998 | 15486.05 | 15486.05 | 15486.05 | 15486.05 | [8 empty] | 61944.1998 | 15486.05 | 15486.05 | 15486.05 | 15486.05 | [8 empty] | 61944.1998 | 15486.05 | 15486.05 | 15486.05 | 15486.05 | [8 empty] | 61944.1998 | 15486.05 | 15486.05 | 15486.05 | 15486.05 | [8 empty] | 61944.1998 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 370621.1955 | 740981.3902 | 740981.3902 | 80.02 | 80.02: 740981.3902 |  | 46371.1496 | 370621.1955 | 80.02 | 0 | 370621.1955 | 0 | 0 | 0 | 0 | 0 | 0
10 | 80.02 | Corrosion Control |  |  | Various | DP3 |  |  |  | 0 | 1094.7852 | 1094.7852 | 1094.7852 | 1094.7852 | 1094.7852 | 2189.5704 | 2189.5704 | 2189.5704 | 12042.6371 | 2189.5704 | 2189.5704 | 2189.5704 | 2189.5704 | 2189.5704 | 1094.7852 | 1094.7852 | 1094.7852 | 1094.7852 | 1094.7852 | 1094.7852 | 1094.7852 | 18611.3482 | 1094.7852 | 823.1468 | 823.1468 | 823.1468 | 823.1468 | 80.03 | Corrosion Control | 0 | DP3 | 823.1468 | 823.1468 | 823.1468 | 823.1468 | 823.1468 | 823.1468 | 823.1468 | 10149.3996 | 1465.2012 | 1465.2012 | 1465.2012 | 1465.2012 | [8 empty] | 5860.8049 | 1465.2012 | 1465.2012 | 1465.2012 | 1465.2012 | [8 empty] | 5860.8049 | 1465.2012 | 1465.2012 | 1465.2012 | 1465.2012 | [8 empty] | 5860.8049 | 1465.2012 | 1465.2012 | 1465.2012 | 1465.2012 | [8 empty] | 5860.8049 | 1465.2012 | 1465.2012 | 1465.2012 | 1465.2012 | [8 empty] | 5860.8049 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 35066.052 | 70107.4096 | 70107.4096 | 80.02 | 80.02: 70107.4096 |  | 4387.3722 | 35066.052 | 80.02 | 0 | 35066.052 | 0 | 0 | 0 | 0 | 0 | 0
11 | 80.02 | Fare Collection | 150 | 320 | Various | DP3 |  |  |  | 0 | 673.714 | 673.714 | 673.714 | 673.714 | 673.714 | 1347.4279 | 1347.4279 | 1347.4279 | 7410.8536 | 1347.4279 | 1347.4279 | 1347.4279 | 1347.4279 | 1347.4279 | 673.714 | 673.714 | 673.714 | 673.714 | 673.714 | 673.714 | 673.714 | 11453.1374 | 673.714 | 506.5519 | 506.5519 | 506.5519 | 506.5519 | 80.03 | Fare Collection | 0 | DP3 | 506.5519 | 506.5519 | 506.5519 | 506.5519 | 506.5519 | 506.5519 | 506.5519 | 6245.7843 | 901.6623 | 901.6623 | 901.6623 | 901.6623 | [8 empty] | 3606.6492 | 901.6623 | 901.6623 | 901.6623 | 901.6623 | [8 empty] | 3606.6492 | 901.6623 | 901.6623 | 901.6623 | 901.6623 | [8 empty] | 3606.6492 | 901.6623 | 901.6623 | 901.6623 | 901.6623 | [8 empty] | 3606.6492 | 901.6623 | 901.6623 | 901.6623 | 901.6623 | [8 empty] | 3606.6492 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 21579.1089 | 43143.0213 | 43143.0213 | 80.02 | 80.02: 43143.0213 |  | 2699.9214 | 21579.1089 | 80.02 | 0 | 21579.1089 | 0 | 0 | 0 | 0 | 0 | 0
12 | 80.02 | Systems Safety | 305 | 431 | Various | DP3 |  |  |  | 0 | 6029.74 | 6029.74 | 6029.74 | 6029.74 | 6029.74 | 12059.4799 | 12059.4799 | 12059.4799 | 66327.1397 | 12059.4799 | 12059.4799 | 12059.4799 | 12059.4799 | 12059.4799 | 6029.74 | 6029.74 | 6029.74 | 6029.74 | 6029.74 | 6029.74 | 6029.74 | 102505.5796 | 6029.74 | 4533.6391 | 4533.6391 | 4533.6391 | 4533.6391 | 80.03 | Systems Safety | 0 | DP3 | 4533.6391 | 4533.6391 | 4533.6391 | 4533.6391 | 4533.6391 | 4533.6391 | 4533.6391 | 55899.7698 | 8069.8776 | 8069.8776 | 8069.8776 | 8069.8776 | [8 empty] | 32279.5102 | 8069.8776 | 8069.8776 | 8069.8776 | 8069.8776 | [8 empty] | 32279.5102 | 8069.8776 | 8069.8776 | 8069.8776 | 8069.8776 | [8 empty] | 32279.5102 | 8069.8776 | 8069.8776 | 8069.8776 | 8069.8776 | [8 empty] | 32279.5102 | 8069.8776 | 8069.8776 | 8069.8776 | 8069.8776 | [8 empty] | 32279.5102 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 193133.0247 | 386130.0403 | 386130.0403 | 80.02 | 80.02: 386130.0403 |  | 24164.2963 | 193133.0247 | 80.02 | 0 | 193133.0247 | 0 | 0 | 0 | 0 | 0 | 0
13 | 80.02 | Elect/Mech | 305 | 432 | Various | DP3 |  |  |  | 0 | 11705.7801 | 11705.7801 | 11705.7801 | 11705.7801 | 11705.7801 | 23411.5602 | 23411.5602 | 23411.5602 | 128763.5813 | 23411.5602 | 23411.5602 | 23411.5602 | 23411.5602 | 23411.5602 | 11705.7801 | 11705.7801 | 11705.7801 | 11705.7801 | 11705.7801 | 11705.7801 | 11705.7801 | 198998.262 | 11705.7801 | 8801.3384 | 8801.3384 | 8801.3384 | 8801.3384 | 80.03 | Elect/Mech | 0 | DP3 | 8801.3384 | 8801.3384 | 8801.3384 | 8801.3384 | 8801.3384 | 8801.3384 | 8801.3384 | 108520.5029 | 15666.3824 | 15666.3824 | 15666.3824 | 15666.3824 | [8 empty] | 62665.5297 | 15666.3824 | 15666.3824 | 15666.3824 | 15666.3824 | [8 empty] | 62665.5297 | 15666.3824 | 15666.3824 | 15666.3824 | 15666.3824 | [8 empty] | 62665.5297 | 15666.3824 | 15666.3824 | 15666.3824 | 15666.3824 | [8 empty] | 62665.5297 | 15666.3824 | 15666.3824 | 15666.3824 | 15666.3824 | [8 empty] | 62665.5297 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 374937.0173 | 749609.9944 | 749609.9944 | 80.02 | 80.02: 749609.9944 |  | 46911.1339 | 374937.0173 | 80.02 | 0 | 374937.0173 | 0 | 0 | 0 | 0 | 0 | 0
14 | 80.02 | CADD | 275 | 420 | Various | DP3 |  |  |  | 0 | 18644.8247 | 18644.8247 | 18644.8247 | 18644.8247 | 18644.8247 | 37289.6494 | 37289.6494 | 37289.6494 | 205093.0719 | 37289.6494 | 37289.6494 | 37289.6494 | 37289.6494 | 37289.6494 | 18644.8247 | 18644.8247 | 18644.8247 | 18644.8247 | 18644.8247 | 18644.8247 | 18644.8247 | 316962.0201 | 18644.8247 | 14018.6652 | 14018.6652 | 14018.6652 | 14018.6652 | 80.03 | CADD | 0 | DP3 | 14018.6652 | 14018.6652 | 14018.6652 | 14018.6652 | 14018.6652 | 14018.6652 | 14018.6652 | 172850.1419 | 24953.2241 | 24953.2241 | 24953.2241 | 24953.2241 | [8 empty] | 99812.8962 | 24953.2241 | 24953.2241 | 24953.2241 | 24953.2241 | [8 empty] | 99812.8962 | 24953.2241 | 24953.2241 | 24953.2241 | 24953.2241 | [8 empty] | 99812.8962 | 24953.2241 | 24953.2241 | 24953.2241 | 24953.2241 | [8 empty] | 99812.8962 | 24953.2241 | 24953.2241 | 24953.2241 | 24953.2241 | [8 empty] | 99812.8962 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 597195.1375 | 1193969.715 | 1193969.715 | 80.02 | 80.02: 1193969.715 |  | 74719.4855 | 597195.1375 | 80.02 | 0 | 597195.1375 | 0 | 0 | 0 | 0 | 0 | 0
15 | 80.02 | Architectural | 275 | 420 | Various | DP3 |  |  |  | 0 | 471.5998 | 471.5998 | 471.5998 | 471.5998 | 471.5998 | 943.1995 | 943.1995 | 943.1995 | 5187.5975 | 943.1995 | 943.1995 | 943.1995 | 943.1995 | 943.1995 | 471.5998 | 471.5998 | 471.5998 | 471.5998 | 471.5998 | 471.5998 | 471.5998 | 8017.1962 | 471.5998 | 354.5863 | 354.5863 | 354.5863 | 354.5863 | 80.03 | Architectural | 0 | DP3 | 354.5863 | 354.5863 | 354.5863 | 354.5863 | 354.5863 | 354.5863 | 354.5863 | 4372.049 | 631.1636 | 631.1636 | 631.1636 | 631.1636 | [8 empty] | 2524.6544 | 631.1636 | 631.1636 | 631.1636 | 631.1636 | [8 empty] | 2524.6544 | 631.1636 | 631.1636 | 631.1636 | 631.1636 | [8 empty] | 2524.6544 | 631.1636 | 631.1636 | 631.1636 | 631.1636 | [8 empty] | 2524.6544 | 631.1636 | 631.1636 | 631.1636 | 631.1636 | [8 empty] | 2524.6544 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 15105.3762 | 30200.1149 | 30200.1149 | 80.02 | 80.02: 30200.1149 |  | 1889.945 | 15105.3762 | 80.02 | 0 | 15105.3762 | 0 | 0 | 0 | 0 | 0 | 0
16 | 80.02 | Traffic |  |  | Various | DP3 |  |  |  | 0 | 336.857 | 336.857 | 336.857 | 336.857 | 336.857 | 673.714 | 673.714 | 673.714 | 3705.4268 | 673.714 | 673.714 | 673.714 | 673.714 | 673.714 | 336.857 | 336.857 | 336.857 | 336.857 | 336.857 | 336.857 | 336.857 | 5726.5687 | 336.857 | 253.2759 | 253.2759 | 253.2759 | 253.2759 | 80.03 | Traffic | 0 | DP3 | 253.2759 | 253.2759 | 253.2759 | 253.2759 | 253.2759 | 253.2759 | 253.2759 | 3122.8922 | 450.8311 | 450.8311 | 450.8311 | 450.8311 | [8 empty] | 1803.3246 | 450.8311 | 450.8311 | 450.8311 | 450.8311 | [8 empty] | 1803.3246 | 450.8311 | 450.8311 | 450.8311 | 450.8311 | [8 empty] | 1803.3246 | 450.8311 | 450.8311 | 450.8311 | 450.8311 | [8 empty] | 1803.3246 | 450.8311 | 450.8311 | 450.8311 | 450.8311 | [8 empty] | 1803.3246 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 10789.5545 | 21571.5106 | 21571.5106 | 80.02 | 80.02: 21571.5106 |  | 1349.9607 | 10789.5545 | 80.02 | 0 | 10789.5545 | 0 | 0 | 0 | 0 | 0 | 0
|  | Subtotals - Group: HNTB-B&C Transit - Final Design for Surface, Trackway & Systems (DP3) |  |  |  |  | 0 | 0 | 0 | 0 | 215656.6767 | 215656.6767 | 215656.6767 | 215656.6767 | 215656.6767 | 431313.3533 | 431313.3533 | 431313.3533 | 2372223.4432 | 431313.3533 | 431313.3533 | 431313.3533 | 431313.3533 | 431313.3533 | 215656.6767 | 215656.6767 | 215656.6767 | 215656.6767 | 215656.6767 | 215656.6767 | 215656.6767 | 3666163.5032 | 215656.6767 | 162147.8772 | 162147.8772 | 162147.8772 | 162147.8772 |  |  |  |  | 162147.8772 | 162147.8772 | 162147.8772 | 162147.8772 | 162147.8772 | 162147.8772 | 162147.8772 | 1999283.3257 | 288623.2214 | 288623.2214 | 288623.2214 | 288623.2214 | [8 empty] | 1154492.8856 | 288623.2214 | 288623.2214 | 288623.2214 | 288623.2214 | [8 empty] | 1154492.8856 | 353001.9094 | 353001.9094 | 353001.9094 | 353001.9094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412007.6376 | 353001.9094 | 353001.9094 | 353001.9094 | 353001.9094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412007.6376 | 353001.9094 | 353001.9094 | 353001.9094 | 353001.9094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412007.6376 | 75108.4694 | 75108.4694 | 75108.4694 | 75108.4694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300433.8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7980477.7017 | 14883112.8334 | 14883112.8334 |  |  | 14883112.8334 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 864248.1854 | 7980477.7017 |  | 0 | 7980477.7017 | 0 | 0 | 0 | 0 | 0 | 0
[155 empty] | 0 | 0
[155 empty] | 0 | 0
|  | Group: Department of Public Works (DPW) | [152 empty] | 0 | 0
| 80.02 | BOE Coordination |  |  | Lesley Wong | EHY | 12859.072 | 13586.944 | 13586.944 | 26931.264 | 27901.76 | 29842.752 | 31541.12 | 29600.128 | 24505.024 | 23777.152 | 23777.152 | 18682.048 | 276591.36 | 16498.432 | 16255.808 | 18682.048 | 18682.048 | 18682.048 | 21108.288 | 21108.288 | 21108.288 | 21108.288 | 21108.288 | 21108.288 | 21108.288 | 236558.4 | 13344.32 | 8734.464 | 8734.464 | 5337.728 | 11403.328 | 80.02 | BOE Coordination | 0 | EHY | 8491.84 | 8491.84 | 11888.576 | 11888.576 | 13586.944 | 13586.944 | 13586.944 | 129075.968 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 81521.664 | 642225.728 |  | 80.02 | 80.02: 642225.728 |  | 47554.304 | 81521.664 | 80.02 | 0 | 81521.664 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Sewer Design & Hydraulic Studies |  |  | Yuan Wu | EHY | 4639.1662 | 3313.6901 | 1656.8451 | 4142.1127 | 2982.3211 | 6296.0113 | 4970.5352 | 3645.0592 | 3645.0592 | 3313.6901 | 3313.6901 | 3313.6901 | 45231.8704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.02 | Sewer Design & Hydraulic Studies | 0 | EHY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 45231.8704 |  | 80.02 | 80.02: 45231.8704 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Sewer Design |  |  | Kevin Day | EHY | 16255.5072 | 15905.9264 | 14507.6032 | 18527.7824 | 18877.3632 | 21674.0096 | 20800.0576 | 20974.848 | 9963.0528 | 9089.1008 | 9963.0528 | 5593.2928 | 182131.5968 | 10487.424 | 10487.424 | 10487.424 | 10487.424 | 10487.424 | 10662.2144 | 10662.2144 | 10662.2144 | 10662.2144 | 10662.2144 | 10662.2144 | 10662.2144 | 127072.6208 | 6642.0352 | 4369.76 | 4369.76 | 3670.5984 | 4020.1792 | 80.02 | Sewer Design | 0 | EHY | 4020.1792 | 524.3712 | 699.1616 | 699.1616 | 1048.7424 | 1048.7424 | 1048.7424 | 32161.4336 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 9089.1008 | 341365.6512 |  | 80.02 | 80.02: 341365.6512 |  | 23072.3328 | 9089.1008 | 80.02 | 0 | 9089.1008 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Sewer Design |  |  | Cheung/Fong/Helmuth/Others | EHY | 6864 | 6864 | 10608 | 14560 | 13936 | 13728 | 17056 | 18512 | 9568 | 10816 | 9984 | 4992 | 137488 | 7072 | 7072 | 7072 | 7072 | 7072 | 7072 | 7072 | 7072 | 7072 | 7072 | 7072 | 7072 | 84864 | 3744 | 3744 | 3744 | 3328 | 3328 | 80.02 | Sewer Design | 0 | EHY | 3328 | 0 | 0 | 0 | 0 | 0 | 0 | 21216 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 3328 | 243568 |  | 80.02 | 80.02: 243568 |  | 17888 | 3328 | 80.02 | 0 | 3328 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | AWSS Design |  |  | Mike Smith | EME | 6493.056 | 5275.608 | 5275.608 | 11971.572 | 11971.572 | 13594.836 | 11971.572 | 13189.02 | 7913.412 | 7913.412 | 7913.412 | 6898.872 | 110381.952 | 6898.872 | 7101.78 | 7101.78 | 7101.78 | 7101.78 | 7304.688 | 7101.78 | 7101.78 | 7304.688 | 7101.78 | 7101.78 | 7101.78 | 85424.268 | 4463.976 | 3043.62 | 3043.62 | 1623.264 | 2231.988 | 80.02 | AWSS Design | 0 | EME | 811.632 | 811.632 | 1217.448 | 1217.448 | 1623.264 | 1623.264 | 1826.172 | 23537.328 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 9130.86 | 219343.548 |  | 80.02 | 80.02: 219343.548 |  | 14406.468 | 9130.86 | 80.02 | 0 | 9130.86 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | AWSS Design |  |  | Lee/Wong/Others | EME | 1368 | 1368 | 1368 | 3496 | 2584 | 3496 | 4712 | 5928 | 4104 | 9120 | 6080 | 3040 | 46664 | 3192 | 3192 | 3192 | 3192 | 3192 | 3192 | 3192 | 3192 | 3192 | 3192 | 3192 | 3192 | 38304 | 1824 | 1824 | 1824 | 760 | 760 | 80.02 | AWSS Design | 0 | EME | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6992 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 91960 |  | 80.02 | 80.02: 91960 |  | 6992 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Roadway Renovation Design |  |  | Steve O'Sullivan | ESH | 29931.4685 | 29931.4685 | 27536.951 | 38551.7315 | 36157.214 | 40946.249 | 40706.7972 | 40706.7972 | 31847.0825 | 31128.7273 | 31128.7273 | 19156.1399 | 397729.3538 | 20113.9469 | 20113.9469 | 20113.9469 | 20113.9469 | 20113.9469 | 22508.4643 | 22508.4643 | 22508.4643 | 22508.4643 | 22508.4643 | 22508.4643 | 22508.4643 | 258128.9846 | 17958.8811 | 13169.8462 | 13169.8462 | 8380.8112 | 10296.4252 | 80.02 | Roadway Renovation Design | 0 | ESH | 4310.1315 | 4310.1315 | 5746.842 | 5746.842 | 7423.0042 | 7423.0042 | 7423.0042 | 105358.7692 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 42382.9594 | 761217.1077 |  | 80.02 | 80.02: 761217.1077 |  | 62975.8098 | 42382.9594 | 80.02 | 0 | 42382.9594 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Roadway Renovation Design |  |  | Yu/Hernandez/Others | ESH | 3496 | 2280 | 8360 | 9424 | 9424 | 12464 | 15352 | 14592 | 10792 | 10792 | 10792 | 6992 | 114760 | 6992 | 6992 | 6992 | 6992 | 6992 | 6992 | 6992 | 6992 | 6992 | 6992 | 6992 | 6992 | 83904 | 4712 | 4712 | 4712 | 3496 | 3496 | 80.02 | Roadway Renovation Design | 0 | ESH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21128 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 219792 |  | 80.02 | 80.02: 219792 |  | 21128 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Structural Sewer Design |  |  | Joseph Elek | EST | 1570.064 | 0 | 0 | 1570.064 | 0 | 6280.256 | 4906.45 | 4906.45 | 3925.16 | 4513.934 | 4906.45 | 4906.45 | 37485.278 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 40036.632 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 3336.386 | 80.02 | Structural Sewer Design | 0 | EST | 0 | 0 | 0 | 0 | 196.258 | 196.258 | 196.258 | 17270.704 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 588.774 | 94792.614 |  | 80.02 | 80.02: 94792.614 |  | 16681.93 | 588.774 | 80.02 | 0 | 588.774 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Structural Sewer Design |  |  | Others | EST | 0 | 0 | 0 | 0 | 0 | 0 | 1064 | 1064 | 2280 | 2280 | 2280 | 2280 | 11248 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 27360 | 2280 | 2280 | 2280 | 2280 | 2280 | 80.02 | Structural Sewer Design | 0 | EST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11400 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 50008 |  | 80.02 | 80.02: 50008 |  | 11400 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Specs/Site Ass'm't & Remediation |  |  | Carmen Ynami | BCM/ | 6891.78 | 7285.596 | 7285.596 | 10042.308 | 9845.4 | 10829.94 | 10829.94 | 11420.664 | 10436.124 | 10436.124 | 10436.124 | 8467.044 | 114206.64 | 14177.376 | 14177.376 | 14177.376 | 14177.376 | 14177.376 | 26385.672 | 26385.672 | 26385.672 | 26582.58 | 26582.58 | 26582.58 | 26582.58 | 256374.216 | 24613.5 | 13783.56 | 13783.56 | 12995.928 | 31899.096 | 80.02 | Specs/Site Ass'm't & Remediation | 0 | BCM/ | 31111.464 | 31111.464 | 41744.496 | 41744.496 | 44698.116 | 44698.116 | 44698.116 | 376881.912 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 279806.268 | 747462.768 |  | 80.02 | 80.02: 747462.768 |  | 97075.644 | 279806.268 | 80.02 | 0 | 279806.268 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Specs/Site Ass'm't & Remediation |  |  | Others | BCM | 1632 | 1632 | 1632 | 2720 | 1632 | 1632 | 1632 | 1632 | 1632 | 1632 | 1632 | 1496 | 20536 | 1088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088 | 1088 | 0 | 0 | 0 | 0 | 80.02 | Specs/Site Ass'm't & Remediation | 0 | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 22712 |  | 80.02 | 80.02: 22712 |  | 1088 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | Force Main Design |  |  | Elliot Szkup | EME | 0 | 0 | 0 | 704 | 704 | 704 | 4928 | 4928 | 4928 | 4928 | 6195.2 | 704 | 28723.2 | 704 | 704 | 704 | 704 | 704 | 844.8 | 844.8 | 844.8 | 844.8 | 844.8 | 844.8 | 844.8 | 9433.6 | 844.8 | 844.8 | 844.8 | 140.8 | 140.8 | 80.02 | Force Main Design | 0 | EME | 140.8 | 140.8 | 281.6 | 281.6 | 140.8 | 140.8 | 281.6 | 4224 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1408 | 42380.8 |  | 80.02 | 80.02: 42380.8 |  | 2816 | 1408 | 80.02 | 0 | 1408 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | PUC Sewer Operations (TV Tape) |  |  | Others | PUC | 0 | 0 | 0 | 0 | 0 | 3200 | 3200 | 6400 | 4800 | 6400 | 8000 | 0 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.02 | PUC Sewer Operations (TV Tape) | 0 | PUC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 32000 |  | 80.02 | 80.02: 32000 |  | 0 | 0 | 80.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.02 | AWSS Cistern Design |  |  | Frank Piruzmand | EST | 0 | 0 | 0 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 19324.8 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 2147.2 | 25766.4 | 0 | 0 | 0 | 0 | 195.2 | 80.02 | AWSS Cistern Design | 0 | EST | 195.2 | 195.2 | 195.2 | 195.2 | 195.2 | 195.2 | 195.2 | 1561.6 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1366.4 | 46652.8 |  | 80.02 | 80.02: 46652.8 |  | 195.2 | 1366.4 | 80.02 | 0 | 1366.4 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.04 | Resident Engineer (1250) |  |  | Mike Acosta | BCM | 0 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 202400 | 18400 | 18400 | 18400 | 18400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73600 | 0 | 0 | 0 | 0 | 0 | 80.04 | Resident Engineer (1250) | 0 | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 276000 |  | 80.04 | 80.04: 276000 |  | 0 | 0 | 80.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.04 | Inspector (1250) |  |  | Gabriel Fernandez | BCM | 0 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 176000 | 16000 | 16000 | 16000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64000 | 0 | 0 | 0 | 0 | 0 | 80.04 | Inspector (1250) | 0 | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 240000 |  | 80.04 | 80.04: 240000 |  | 0 | 0 | 80.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.04 | Inspector (1250) |  |  | Terrance Huey | BCM | 0 | 0 | 0 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 122400 | 13600 | 13600 | 13600 | 13600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54400 | 0 | 0 | 0 | 0 | 0 | 80.04 | Inspector (1250) | 0 | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 176800 |  | 80.04 | 80.04: 176800 |  | 0 | 0 | 80.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.04 | Office Engineer Engineer (1250) |  |  | Peter Chin | BCM | 0 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 167200 | 15200 | 15200 | 15200 | 15200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60800 | 0 | 0 | 0 | 0 | 0 | 80.04 | Office Engineer Engineer (1250) | 0 | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 228000 |  | 80.04 | 80.04: 228000 |  | 0 | 0 | 80.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.04 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 80.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 |  |  | 80.04: 0 |  | 0 | 0 | 80.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 80.04 | Resident Engineer (1251) |  |  | TBD | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 18400 | 220800 | 18400 | 18400 | 18400 | 18400 | 18400 | 80.04 | Resident Engineer (1251) | 0 | BCM | 18400 | 0 | 0 | 0 | 0 | 0 | 0 | 110400 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 18400 | 331200 |  | 80.04 | 80.04: 331200 |  | 92000 | 18400 | 80.04 | 0 | 0 | 0 | 18400 | 0 | 0 | 0 | 0
| 80.04 | Inspector (1251) |  |  | TBD | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 16000 | 192000 | 16000 | 16000 | 16000 | 16000 | 16000 | 80.04 | Inspector (1251) | 0 | BCM | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 96000 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 16000 | 288000 |  | 80.04 | 80.04: 288000 |  | 80000 | 16000 | 80.04 | 0 | 0 | 0 | 16000 | 0 | 0 | 0 | 0
| 80.04 | Inspector (1251) |  |  | TBD | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 13600 | 163200 | 13600 | 13600 | 13600 | 13600 | 13600 | 80.04 | Inspector (1251) | 0 | BCM | 13600 | 0 | 0 | 0 | 0 | 0 | 0 | 81600 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 13600 | 244800 |  | 80.04 | 80.04: 244800 |  | 68000 | 13600 | 80.04 | 0 | 0 | 0 | 13600 | 0 | 0 | 0 | 0
| 80.04 | Office Engineer Engineer (1251) |  |  | TBD | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 182400 | 15200 | 15200 | 15200 | 15200 | 15200 | 80.04 | Office Engineer Engineer (1251) | 0 | BCM | 15200 | 0 | 0 | 0 | 0 | 0 | 0 | 91200 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 15200 | 273600 |  | 80.04 | 80.04: 273600 |  | 76000 | 15200 | 80.04 | 0 | 0 | 0 | 15200 | 0 | 0 | 0 | 0
| 80.04 | Inspectors (Stations and Systems) |  |  | TBD | BCM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 48000 | 64000 | 64000 | 80.04 | Inspectors (Stations and Systems) | 0 | BCM | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 64000 | 672000 | 192000 | 192000 | 192000 | 192000 | [8 empty] | 768000 | 240000 | 240000 | 240000 | 240000 | [8 empty] | 960000 | 240000 | 240000 | 240000 | 240000 | [8 empty] | 960000 | 240000 | 240000 | 240000 | 240000 | [8 empty] | 960000 | 192000 | 192000 | 96000 | 96000 | [8 empty] | 576000 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 4672000 | 4896000 |  | 80.04 | 80.04: 4896000 |  | 224000 | 4672000 | 80.04 | 0 | 0 | 0 | 4672000 | 0 | 0 | 0 | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
[41 empty] | 0 | [99 empty] | 0 | [13 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  | 0
|  | Subtotals - Department Of Public Works (DPW) |  |  |  |  | 92000.1139 | 137043.2331 | 141417.5473 | 207988.0345 | 201362.8303 | 230035.2538 | 239017.672 | 242846.1664 | 195686.1145 | 201487.3402 | 201749.0082 | 151868.7368 | 2242502.0511 | 221387.6369 | 220259.9209 | 222686.1609 | 222686.1609 | 159486.1609 | 177033.7127 | 176830.8047 | 176830.8047 | 177230.6207 | 177027.7127 | 177027.7127 | 177027.7127 | 2285515.1214 | 148051.8983 | 171042.4362 | 171042.4362 | 172549.5156 | 200587.4024 |  |  |  |  | 179609.2467 | 109585.4387 | 125773.3236 | 125773.3236 | 132912.3286 | 132912.3286 | 133256.0366 | 1803095.7148 | 192000 | 192000 | 192000 | 192000 | [8 empty] | 768000 | 240000 | 240000 | 240000 | 240000 | [8 empty] | 960000 | 240000 | 240000 | 240000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000 | 240000 | 240000 | 240000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960000 | 192000 | 192000 | 96000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 576000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5163822.0262 | 10555112.8873 |  |  |  | 3600712.8873 | 0 | 6954400 | 0 | 0 | 0 | 0 |  |  | 863273.6886 | 5163822.0262 |  | 0 | 428622.0262 | 0 | 4735200 | 0 | 0 | 0 | 0
Group: City and County of San Francisco
|  | Arts Commission |  |  | Various | CCSF
|  | City Attorney's Office |  |  | Various | CCSF
|  | SFFD |  |  | Corbett/Stephenson/Fields | CCSF
|  | SFPD |  |  | Michael Connolly | CCSF
|  | Real Estate |  |  | TBD | CCSF
|  | Dept of Public Health |  |  | TBD | CCSF
|  | SFPUC |  |  | TBD | CCSF
|  | SFCTA |  |  | TBD | CCSF
CCSF
CCSF
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [42 empty] | 0 | [64 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [55 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
[6 empty] | CCSF | [12 empty] | 0 | [12 empty] | 0 | [16 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 0
|  | Subtotals - Group: City and County of San Francisco |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 80.02: 0; 80.03: 0
[145 empty] | PE | FD | PM | CM | Non-Constr | Legal, Rev | Test | S-U |  | Real Estate
[145 empty] | 80.01 | 80.02 | 80.03 | 80.04 | 80.05 | 80.06 | 80.07 | 80.08 | 80 | 60
[118 empty] | BART Reviews | [23 empty] | Staffing Plan |  |  | 52512369 | 65710859.8457 | 131503807.3167 | 12384424.675 | 7019120 | 3000000 | 2000000 | 7041906.79 | 281172487.6273
[142 empty] | CCE |  |  | 52512369 | 89508154 | 171988680 | 18342582 | 7019120 | 8127762 | 14888039 | 22524792 | 384911498 | 4000000
[145 empty] | 0 | -23797294.1543 | -40484872.6833 | -5958157.325 | 0 | -5127762 | -12888039 | -15482885.21 | -103739010.3727
[145 empty] | -3000000 | 3000000 |  |  |  | Placeholders
|  | GRAND TOTALS | [16 empty] | 36667286.7966 | [12 empty] | 38552830.9227 |  |  |  |  | 2184717.86 | [11 empty] | 25034943.5969 | [12 empty] | 28711008.7488 | [12 empty] | 27293588.4177 | [12 empty] | 25866837.0948 | [12 empty] | 19011924.9294 | [12 empty] | 14299657.4658 | [12 empty] | 13089164.612 | [12 empty] | 1110878.427 | 149581357.9833 | 234867057.2232 | [13 empty] | 149581357.9833 |  | 0 | 21482320.621 | 58222000.9754 | 60917260.9879 | 0 | 0 | 0 | 8358534.649 | 148980117.2333
[7 empty] | Hourly Rates by Year | [11 empty] | $ | Hrs | Rate | ODCs | Opt/AC
[5 empty] | Position # |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 |  | DP1 | 5530612 | 36195 | 152.8004 | 264388 | 705000 | 6500000 | 201295 | 1317.3718 | 8.2336 | [116 empty] | 231822838.8715
[5 empty] | Sr Program Manager (5508) | 1 | 280.4442 | 280.4442 | 280.4442 | 280.4442 | 280.4442 | 280.4442 | 280.4442 | 280.4442 | 280.4442 | 280.4442 |  | DP2 | 34157952 | 251922 | 135.5894 | 1802600 | 3989407 | 39949959
[5 empty] | Sr Clerk Typist (1426) | 2 | 77.1669 | 77.1669 | 77.1669 | 77.1669 | 77.1669 | 77.1669 | 77.1669 | 77.1669 | 77.1669 | 77.1669 |  | DP3 | 14896400 | 94692 | 157.3142 | 424400 | 4598725 | 19919525
[5 empty] | Secretary II MPMS (1446) | 3 | 85.0585 | 85.0585 | 85.0585 | 85.0585 | 85.0585 | 85.0585 | 85.0585 | 85.0585 | 85.0585 | 85.0585 | [5 empty] | ODCs & 2009 Chgs
[5 empty] | Exec Secretary (1450) | 4 | 92.6391 | 92.6391 | 92.6391 | 92.6391 | 92.6391 | 92.6391 | 92.6391 | 92.6391 | 92.6391 | 92.6391 |  | PMCM | 107079723 | 612634.88 | 174.7855 | 32000000
[5 empty] | Sr Admin/Analyst (1823) | 5 | 135.5182 | 135.5182 | 135.5182 | 135.5182 | 135.5182 | 135.5182 | 135.5182 | 135.5182 | 135.5182 | 135.5182 |  | PCC | 17112873 | 170077 | 100.6184
[5 empty] | PM III MPMS (5506) | 6 | 251.4435 | 251.4435 | 251.4435 | 251.4435 | 251.4435 | 251.4435 | 251.4435 | 251.4435 | 251.4435 | 251.4435
[5 empty] | PM II MPMS (5504) | 7 | 207.126 | 207.126 | 207.126 | 207.126 | 207.126 | 207.126 | 207.126 | 207.126 | 207.126 | 207.126
[5 empty] | Program Manager Project Services (5212) | 8 | 259.996 | 259.996 | 259.996 | 259.996 | 259.996 | 259.996 | 259.996 | 259.996 | 259.996 | 259.996
[5 empty] | Construction Manager (5211) | 9 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534
[5 empty] | Quality Assurance Manager (5211) | 10 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534
[5 empty] | QA Support (5207) | 11 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222
[5 empty] | Environmental Manager (5502) | 12 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416
[5 empty] | Finance/Grants Manager (5502) | 13 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416 | 178.9416
[5 empty] | Finance Support (5380) | 14 | 69.5863 | 69.5863 | 69.5863 | 69.5863 | 69.5863 | 69.5863 | 69.5863 | 69.5863 | 69.5863 | 69.5863
[5 empty] | Dep Dir II - (9187) | 15 | 270.57 | 270.57 | 270.57 | 270.57 | 270.57 | 270.57 | 270.57 | 270.57 | 270.57 | 270.57
[5 empty] | Contracts Manager (1824) | 16 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995
17
[5 empty] | Constr Inspectors | 18 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136
[5 empty] | Principal Engineer MCEQ (5212) | 19 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260
20
[5 empty] | Project Controls Manager (9181) | 21 | 223.0647 | 223.0647 | 223.0647 | 223.0647 | 223.0647 | 223.0647 | 223.0647 | 223.0647 | 223.0647 | 223.0647
[5 empty] | Real Estate Manager (9182) | 22 | 238.6536 | 238.6536 | 238.6536 | 238.6536 | 238.6536 | 238.6536 | 238.6536 | 238.6536 | 238.6536 | 238.6536
[5 empty] | Real Estate (1824) | 23 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995 | 156.8995
[5 empty] | Real Estate (1054) | 24 | 172.0219 | 172.0219 | 172.0219 | 172.0219 | 172.0219 | 172.0219 | 172.0219 | 172.0219 | 172.0219 | 172.0219
[5 empty] | Real Estate (9174) | 25 | 179.5247 | 179.5247 | 179.5247 | 179.5247 | 179.5247 | 179.5247 | 179.5247 | 179.5247 | 179.5247 | 179.5247
Plan
[18 empty] | group | scc |  | 2010 | 2011 | Through 5/31/12 |  | 4021
[18 empty] | Project Mgmt | 80.03 | SFMTA | 1807915.152 | 1725318.528 | 708841.152 |  | 4242074.832
[7 empty] | Hourly Rates by Year 2013: 3.11 |  | Project Mgmt | 80.04 | SFMTA | 418613.832 | 594869.832 | 247862.43 |  | 1261346.094
[18 empty] | Project Mgmt | 60 | SFMTA | 287308.02 | 156236.448 | 0 |  | 443544.468
[7 empty] | Hourly Rates by Year 2012: 24.8125; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 1426; Hourly Rates by Year 2016: Nacion, Joery R | [8 empty] | 0
[7 empty] | Hourly Rates by Year 2012: 27.35; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 1446; Hourly Rates by Year 2016: Secretary II MPMS |  | Engineering | 80.02 | SFMTA | 1791192.06 | 1234674.354 | 223808.04 |  | 3249674.454
[7 empty] | Hourly Rates by Year 2012: 29.7875; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 1450; Hourly Rates by Year 2016: Exec Secretary I MCES |  | Engineering | 80.03 | SFMTA | 310823.352 | 310823.352 | 129509.73 |  | 751156.434
[7 empty] | Hourly Rates by Year 2012: 43.575; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 1823; Hourly Rates by Year 2016: Sradminanalyst MPMS | [8 empty] | 0
[7 empty] | Hourly Rates by Year 2012: 38.0125; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5201; Hourly Rates by Year 2016: Junior Engineer MCEG | [8 empty] | 0
[7 empty] | Hourly Rates by Year 2012: 38.0125; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5201; Hourly Rates by Year 2016: Junior Engineer MCEO |  | Start-Up; Safety & Security; Other | 80.08 | OPS | 0 | 21120 | 8800 |  | 29920
[18 empty] | Start-Up; Safety & Security; Other | 80.08 | DPT | 0 | 0 | 0 |  | 0
[7 empty] | Hourly Rates by Year 2012: 42.95; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5203; Hourly Rates by Year 2016: Assistant Engineer MCEN |  | Start-Up; Safety & Security; Other | 80.03 | SFMTA | 0 | 153600 | 115200 |  | 268800
[7 empty] | Hourly Rates by Year 2012: 42.95; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5203; Hourly Rates by Year 2016: Assistant Engineer MCEP |  | Start-Up; Safety & Security; Other | 80.03 | DPT | 250880 | 302400 | 126000 |  | 679280
[7 empty] | Hourly Rates by Year 2012: 42.95; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5203; Hourly Rates by Year 2016: David, Chris R | [8 empty] | 0
[7 empty] | Hourly Rates by Year 2012: 42.95; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5203; Hourly Rates by Year 2016: Lee, Timothy C |  | PM/CM | 80.03 | PM/CM | 8111168.0377 | 8335005.4014 | 3186270.6191 |  | 19632444.0582
[7 empty] | Hourly Rates by Year 2012: 42.95; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5203; Hourly Rates by Year 2016: Seng, Wuthea |  | PM/CM | 80.04 | PM/CM | 1754119.7904 | 3696336.7957 | 2105396.7926 |  | 7555853.3786
[7 empty] | Hourly Rates by Year 2012: 49.975; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5207; Hourly Rates by Year 2016: Associate Engineer MCEG | [8 empty] | 0
[7 empty] | Hourly Rates by Year 2012: 49.975; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5207; Hourly Rates by Year 2016: Associate Engineer MCEN |  | PCC | 80.03 | PCC | 85485.3796 | 2903605.0958 | 984450.2751 |  | 3973540.7505
[7 empty] | Hourly Rates by Year 2012: 49.975; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5207; Hourly Rates by Year 2016: Associate Engineer MCEP | [8 empty] | 0
[7 empty] | Hourly Rates by Year 2012: 49.975; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5207; Hourly Rates by Year 2016: Pong, Sanford C |  | DP1 | 80.02 | DP1 | 3513673.4013 | 999092.3427 | 235486.3586 |  | 4748252.1026
[7 empty] | Hourly Rates by Year 2012: 49.975; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5207; Hourly Rates by Year 2016: Wilson, Prester |  | DP2 | 80.02 | DP2 | 13721382.2774 | 12168070.1486 | 266434.2493 |  | 26155886.6752
[7 empty] | Hourly Rates by Year 2012: 66.9625; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5211; Hourly Rates by Year 2016: Eng, Foo O |  | DP3 | 80.02 | DP3 | 2372223.4432 | 3666163.5032 | 864248.1854 |  | 6902635.1318
[7 empty] | Hourly Rates by Year 2012: 66.9625; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5211; Hourly Rates by Year 2016: Nguyen, Roger Q | [8 empty] | 0
[7 empty] | Hourly Rates by Year 2012: 66.9625; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5211; Hourly Rates by Year 2016: Senior Engineer MCEQ |  | DPW | 80.02 | DPW | 1574502.0511 | 1274315.1214 | 323273.6886 |  | 3172090.8611
[7 empty] | Hourly Rates by Year 2012: 66.9625; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5211; Hourly Rates by Year 2016: Wang, Jane M |  | DPW | 80.04 | DPW | 668000 | 1011200 | 540000 |  | 2219200
[7 empty] | Hourly Rates by Year 2012: 66.9625; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5211; Hourly Rates by Year 2016: Wong, Arthur G | [8 empty] | 0
[7 empty] | Hourly Rates by Year 2012: 66.9625; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5211; Hourly Rates by Year 2016: Wong, Clifton C |  |  |  |  | 36667286.7966 | 38552830.9227 | 10065581.5206 |  | 85285699.2399
[7 empty] | Hourly Rates by Year 2012: 83.6; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5212; Hourly Rates by Year 2016: Neilson II, William |  |  | Cum |  | 36667286.7966 | 75220117.7193 | 85285699.2399 |  | 197173103.7558
[9 empty] | 83.6 | 0 | 5212 |  | Principal Engineer MCEQ
[9 empty] | 57.8375 | 0 | 5241 |  | Engineer MCEG
[9 empty] | 57.8375 | 0 | 5241 |  | Engineer MCEN
[7 empty] | Hourly Rates by Year 2012: 57.8375; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5241; Hourly Rates by Year 2016: Engineer MCEP |  |  |  |  | 2010 | 2011 | 2012 - 3 mos
[7 empty] | Hourly Rates by Year 2012: 57.8375; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5241; Hourly Rates by Year 2016: Hoe, Albert |  | project mgmt |  | sfmta | 2513837.004 | 2476424.808 | 956703.582
[9 empty] | 57.8375 | 0 | 5241 |  | Huey, Lang A
[9 empty] | 57.8375 | 0 | 5241 |  | Lau, Frank W
[9 empty] | 57.8375 | 0 | 5241 |  | Phang, Tee S
[7 empty] | Hourly Rates by Year 2012: 35.5125; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5364; Hourly Rates by Year 2016: Civil Eng Assoc I MCET |  | Engineering |  | sfmta | 2102015.412 | 1545497.706 | 353317.77
[9 empty] | 57.5375 | 0 | 5502 |  | Ames
[9 empty] | 57.5375 | 0 | 5502 |  | Greenaway
[9 empty] | 66.6 | 0 | 5504 |  | PM II MPMS
[7 empty] | Hourly Rates by Year 2012: 80.85; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5506; Hourly Rates by Year 2016: PM III MPMS |  | Start-Up; Safety & Security; Other |  | sfmta | 250880 | 477120 | 250000
[9 empty] | 90.175 | 0 | 5508 |  | Funghi
[9 empty] | 52.35 | 0 | 9141 |  | Rosen
[18 empty] | pmcm |  | pmcm | 0 | 0 | 0
[9 empty] | 55.3125 | 0 | 1054
[9 empty] | 50.45 | 0 | 1824
[7 empty] | Hourly Rates by Year 2012: 22.375; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5380 |  | pcc |  | pcc | 85485.3796 | 2903605.0958 | 984450.2751
[9 empty] | 57.725 | 0 | 9174
[7 empty] | Hourly Rates by Year 2012: 71.725; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 9181 |  | dp1 |  | dp1 | 3513673.4013 | 999092.3427 | 235486.3586
[7 empty] | Hourly Rates by Year 2012: 76.7375; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 9182 |  | dp2 |  | dp2 | 13721382.2774 | 12168070.1486 | 266434.2493
[7 empty] | Hourly Rates by Year 2012: 87; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 9187 |  | dp3 |  | dp3 | 2372223.4432 | 3666163.5032 | 864248.1854
[7 empty] | Hourly Rates by Year 2012: 35.5125; Hourly Rates by Year 2013: 0; Hourly Rates by Year 2014: 5364 |  | dpw |  | dpw | 2242502.0511 | 2285515.1214 | 863273.6886
[18 empty] | dpw |  | dpw | 0 | 0 | 0
[21 empty] | 26801998.9685 | 26521488.7256 | 4773914.1089
[19 empty] | Cum |  | 26801998.9685 | 53323487.6942 | 58097401.8031
Hourly Rates by Year
[7 empty] | Position # |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
[7 empty] | Deputy Program Manager | 1 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 2019
[7 empty] | Associate Engineer (5207) | 2 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 179.8746
[7 empty] | Associate Engineer (5207) | 3 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222
[7 empty] | Associate Engr MCEG (5207) | 4 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222
[7 empty] | Associate Engr MCEN (5207) | 5 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222
[7 empty] | Associate Engr MCEP (5207) | 6 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222 | 155.4222
[7 empty] | Assistant Engineer (5203) | 7 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 155.4222
[7 empty] | Assistant Engineer (5203) | 8 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745
[7 empty] | Assistant Engineer (5203) | 9 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745
[7 empty] | Assistant Engineer MCEN (5203) | 10 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745
[7 empty] | Assistant Engineer MCEP (5203) | 11 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745 | 133.5745
[7 empty] | Junior Engineer MCEG (5201) | 12 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 133.5745
[7 empty] | Junior Engineer MCEO (5201) | 13 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189 | 118.2189
[7 empty] | Engineer MCEG (5241) | 14 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 118.2189
[7 empty] | Engineer MCEN (5241) | 15 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746
[7 empty] | Engineer MCEP (5241) | 16 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746
[7 empty] | Engineer (5241) | 17 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746
[7 empty] | Engineer (5241) | 18 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746
[7 empty] | Engineer (5241) | 19 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746 | 179.8746
[7 empty] | Sr Engineer (5211) | 20 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 179.8746
[7 empty] | Sr Engineer (5211) | 21 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534
[7 empty] | Sr Engineer MCEQ (5211) | 22 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534
[7 empty] | Civil Engr Assoc MCET (5364) | 23 | 110.4439 | 110.4439 | 110.4439 | 110.4439 | 110.4439 | 110.4439 | 110.4439 | 110.4439 | 110.4439 | 208.2534
[7 empty] | Intern? (5380) | 24 | 102.63 | 102.63 | 102.63 | 102.63 | 102.63 | 102.63 | 102.63 | 102.63 | 102.63 | 110.4439
|  |  |  | 6319 |  |  | JOC Oversight | 25 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 155 | 102.63
155
|  | 5241 |  | Hoe, Albert |  |  | 57.8375 | 179.8746
|  | 5207 |  | Pong, Sanford C |  |  | 49.975 | 155.4222
|  | 5207 |  | Wilson, Prester |  |  | 49.975 | 155.4222
|  | 5207 |  | Associate Engineer MCEG |  |  | 49.975 | 155.4222
|  | 5207 |  | Associate Engineer MCEN |  |  | 49.975 | 155.4222
|  | 5207 |  | Associate Engineer MCEP |  |  | 49.975 | 155.4222
|  | 5203 |  | Seng, Wuthea |  |  | 42.95 | 133.5745
|  | 5203 |  | Lee, Timothy C |  |  | 42.95 | 133.5745
|  | 5203 |  | David, Chris R |  |  | 42.95 | 133.5745
|  | 5203 |  | Assistant Engineer MCEN |  |  | 42.95 | 133.5745
|  | 5203 |  | Assistant Engineer MCEP |  |  | 42.95 | 133.5745
|  | 5201 |  | Junior Engineer MCEG |  |  | 38.0125 | 118.2189
|  | 5201 |  | Junior Engineer MCEO |  |  | 38.0125 | 118.2189
|  | 5241 |  | Engineer MCEG |  |  | 57.8375 | 179.8746
|  | 5241 |  | Engineer MCEN |  |  | 57.8375 | 179.8746
|  | 5241 |  | Engineer MCEP |  |  | 57.8375 | 179.8746
|  | 5241 |  | Huey, Lang A |  |  | 57.8375 | 179.8746
|  | 5241 |  | Lau, Frank W |  |  | 57.8375 | 179.8746
|  | 5241 |  | Phang, Tee S |  |  | 57.8375 | 179.8746
|  | 5211 |  | Eng, Foo O |  |  | 66.9625 | 208.2534
|  | 5211 |  | Wong, Clifton C |  |  | 66.9625 | 208.2534
|  | 5211 |  | Sr Engineer MCEQ |  |  | 66.9625 | 208.2534
|  | 5364 |  | Civil Eng Assoc I MCET |  |  | 35.5125 | 110.4439
[9 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
|  | 5211 |  | Jane Wang |  |  | 66.9625 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 208.2534 | 2019
|  | 5380 |  | Intern? (Becker) Allowance |  |  | 33 | 102.63 | [9 empty] | 208.2534
1 |  | Start-Up Mgr | [6 empty] | 2011: 220
2 |  | Senior Operations Manager | SFMTA |  | SFMTA |  | 11064 | 3.05 | 2010: 69.15; 2011: 210.9075
3 |  | Senior Operations Manager | SFMTA |  |  |  | 11064 | 3.05 | 2010: 69.15; 2011: 210.9075
4 |  | Transit Manager II | SFMTA |  |  |  | 9028 | 3.05 | 2010: 56.425; 2011: 172.0962
5 |  | Transit Manager I | SFMTA |  |  |  | 7996 | 3.05 | 2010: 49.975; 2011: 152.4238
6 |  | Transit Operator | SFMTA |  |  |  | 4468 | 3.05 | 2010: 27.925; 2011: 85.1713
7 |  | Station Agent | SFMTA |  |  |  | 5612 | 3.05 | 2010: 35.075; 2011: 106.9788
8 |  | Senior Stationary Engineer | SFMTA |  |  |  | 6558 | 3.05 | 2010: 40.9875; 2011: 125.0119
9 |  | Electronic Maint Tech Asst Sup | SFMTA |  |  |  | 8412 | 3.05 | 2010: 52.575; 2011: 160.3537
10 |  | Parking Control Officer | DPT |  | DPT |  | 4076 | 3.05 | 2010: 25.475; 2011: 77.6988
11 | [8 empty] | 2011: 160
12 | [8 empty] | 2011: 160
13 | [8 empty] | 2011: 133
14 | [8 empty] | 2011: 155
15 | [8 empty] | 2011: 70
Hourly Rates by Year
[5 empty] | Position # |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019
[5 empty] | Mike Acosta | 1 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115
[5 empty] | Gabriel Fernandez | 2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
[5 empty] | Terrance Huey | 3 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
[5 empty] | Peter Chin | 4 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95
5
[5 empty] | Lesley Wong | 6 | 151.64 | 151.64 | 151.64 | 151.64 | 151.64 | 151.64 | 151.64 | 151.64 | 151.64 | 151.64
[5 empty] | Yua Wu | 7 | 103.5528 | 103.5528 | 103.5528 | 103.5528 | 103.5528 | 103.5528 | 103.5528 | 103.5528 | 103.5528 | 103.5528
[5 empty] | Kevin Day | 8 | 109.244 | 109.244 | 109.244 | 109.244 | 109.244 | 109.244 | 109.244 | 109.244 | 109.244 | 109.244
[5 empty] | Cheung/Fong/Etc | 9 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
[5 empty] | Mike Smith | 10 | 126.8175 | 126.8175 | 126.8175 | 126.8175 | 126.8175 | 126.8175 | 126.8175 | 126.8175 | 126.8175 | 126.8175
[5 empty] | Lee/Wong/Others | 11 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95
[5 empty] | Steve O'Sullivan | 12 | 149.6573 | 149.6573 | 149.6573 | 149.6573 | 149.6573 | 149.6573 | 149.6573 | 149.6573 | 149.6573 | 149.6573
[5 empty] | Yu/Hernandez/Others | 13 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95
[5 empty] | Joseph Elek | 14 | 122.6612 | 122.6612 | 122.6612 | 122.6612 | 122.6612 | 122.6612 | 122.6612 | 122.6612 | 122.6612 | 122.6612
[5 empty] | Others | 15 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95
[5 empty] | Carmen Ynami | 16 | 123.0675 | 123.0675 | 123.0675 | 123.0675 | 123.0675 | 123.0675 | 123.0675 | 123.0675 | 123.0675 | 123.0675
[5 empty] | others |  | Hourly Rates by Year 2010: 85
88
100
122

## Graphic
FTEs |  | 2010-01-10 | 2010-02-10 | 2010-03-10 | 2010-04-10 | 2010-05-10 | 2010-06-10 | 2010-07-10 | 2010-08-10 | 2010-09-10 | 2010-10-10 | 2010-11-10 | 2010-12-10 | 2011-01-11 | 2011-02-11 | 2011-03-11 | 2011-04-11 | 2011-05-11 | 2011-06-11 | 2011-07-11 | 2011-08-11 | 2011-09-11 | 2011-10-11 | 2011-11-11 | 2011-12-11 | 2012-01-11 | 2012-02-11 | 2012-03-11 | 2012-04-11 | 2012-05-11 | 2012-06-11 | 2012-07-11 | 2012-08-11 | 2012-09-11 | 2012-10-11 | 2012-11-11 | 2012-12-11 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | 1Q19 | 2Q19 | 3Q19 | 4Q19
| DP3 | 0 | 0 | 0 | 0 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 17.1358 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 8.5679 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 6.442 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | 11.4668 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 14.0246 | 2.984 | 2.984 | 2.984 | 2.984 | 0 | 0 | 0 | 0
| DP2 | 0 | 0 | 0 | 23.8226 | 50.0274 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 79.8054 | 0 | 0 | 0 | 1.125 | 1.125 | 1.125 | 1.125 | 1.125 | 1.125 | 7.7813 | 7.7813 | 7.7813 | 7.7813 | 6.6563 | 6.6563 | 11.0938 | 11.0938 | 25.8856 | 22.187 | 21 | 21 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 19.9689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0
| DP1 | 5.6493 | 6.9324 | 10.5211 | 12.1218 | 14.3491 | 13.7782 | 12.3663 | 14.9526 | 15.849 | 14.0429 | 11.9291 | 11.2279 | 8.1016 | 3.6164 | 3.0364 | 2.7813 | 7.2015 | 3.0343 | 2.649 | 2.5303 | 2.7296 | 2.0485 | 1.985 | 1.152 | 1.3472 | 1.3355 | 1.2569 | 2.1771 | 3.5154 | 1.6824 | 1.9534 | 1.7564 | 1.7271 | 1.7271 | 1.7229 | 1.774 | 3.9132 | 3.58 | 3.3712 | 3.3712 | 1.1988 | 1.1988 | 1.1988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DPW | 4.51 | 7.24 | 7.54 | 11.12 | 10.75 | 12.29 | 12.87 | 13.11 | 10.72 | 11.11 | 11.13 | 8.43 | 12.75 | 12.67 | 12.77 | 12.77 | 8.77 | 9.62 | 9.61 | 9.61 | 9.63 | 9.62 | 9.62 | 9.62 | 8.22 | 10 | 10 | 10.29 | 11.64 | 10.56 | 6.2 | 6.98 | 6.98 | 7.31 | 7.31 | 7.33 | 12 | 12 | 12 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 12 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.31 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 15.03 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 12.23 | 34.08 | 34.08 | 34.08 | 34.08 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 34.21 | 12.78 | 12.78 | 12.78 | 12.78 | 0 | 0 | 0 | 0
| PMCM | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 29.397 | 33.504 | 33.504 | 33.504 | 33.504 | 33.504 | 33.504 | 34.504 | 34.504 | 34.504 | 41.894 | 41.894 | 41.894 | 37.844 | 37.844 | 37.844 | 37.844 | 37.844 | 38.537 | 38.537 | 38.537 | 38.537 | 38.537 | 39.147 | 39.147 | 115.441 | 178.081 | 184.081 | 184.081 | 168.99 | 168.99 | 150.99 | 150.99 | 149.49 | 145.93 | 146.13 | 143.13 | 134.13 | 131.13 | 82.83 | 82.83 | 82.83 | 72.9 | 72.1 | 65 | 49.7 | 40.5 | 33.25 | 16.5 | 0 | 0 | 0 | 0
| SFMTA | 13.9 | 13.9 | 14.8 | 14.8 | 14.8 | 16.3 | 15.4 | 15.4 | 15.4 | 16.3 | 16.3 | 16.3 | 17.35 | 17.35 | 17.35 | 17.35 | 17.35 | 12.55 | 12.55 | 12.55 | 12.55 | 12.55 | 12.55 | 11.85 | 11.77 | 11.77 | 11.77 | 11.77 | 11.77 | 12.77 | 12.77 | 12.77 | 12.77 | 12.77 | 12.77 | 12.77 | 35.75 | 35.75 | 35.75 | 35.75 | 31.25 | 31.25 | 31.25 | 31.25 | 30.75 | 30.75 | 30.75 | 30.75 | 30.75 | 30.75 | 32.25 | 32.25 | 36.55 | 40.4 | 40.4 | 40.4 | 100.8 | 110.8 | 110.8 | 110.8 | 24.15 | 14.85 | 0 | 0
|  | 53.4563 | 57.4694 | 62.2581 | 91.2614 | 127.8914 | 160.1385 | 158.4066 | 161.2329 | 159.7393 | 167.7911 | 165.6973 | 167.6062 | 183.6768 | 179.1116 | 178.6317 | 178.3765 | 178.7967 | 162.1116 | 162.7164 | 82.7923 | 83.0115 | 89.7104 | 90.7719 | 89.2389 | 81.1041 | 80.7466 | 80.6679 | 81.8781 | 91.2227 | 90.0027 | 85.9137 | 86.4967 | 85.3424 | 85.6724 | 90.7158 | 90.7868 | 238.5366 | 297.1448 | 301.7491 | 301.7491 | 282.0845 | 282.0845 | 264.0845 | 262.8857 | 263.4435 | 259.8835 | 260.0835 | 257.0835 | 248.0835 | 245.0835 | 198.2835 | 178.3146 | 179.6146 | 173.5346 | 166.7346 | 159.6346 | 166.264 | 167.064 | 159.814 | 143.064 | #VALUE! | 14.85 | 0 | 0

## sum fr $labor
thru 05/31/12
Plan
group | scc | ORG | 2010 | 2011 | Thru 5/31/12 | Staffing SCC3 | TOTAL | SCC |  |  |  |  | Values
Project Mgmt | 80.03 | SFMTA | 1807915.152 | 1725318.528 | 708841.152 | 8003.11 | 4242074.832 | 8003 | SCC2 | Staffing SCC3 | scc | ORG | Sum of 2010 | Sum of 2011 | Sum of Thru 5/31/12 | Sum of TOTAL
Project Mgmt | 80.04 | SFMTA | 418613.832 | 594869.832 | 247862.43 | 8004.13 | 1261346.094 | 8004 | 8002 | 8002.12 | 80.02 | SFMTA | 1791192.06 | 1234674.354 | 223808.04 | 3249674.454
Project Mgmt | 60 | SFMTA | 287308.02 | 156236.448 | 0 | TBD | 443544.468 | TBD |  |  | 80.03 | SFMTA | 310823.352 | 310823.352 | 129509.73 | 751156.434
[7 empty] | 0 |  |  | 8002.31 | 80.02 | DPW | 1574502.0511 | 1274315.1214 | 323273.6886 | 3172090.8611
Engineering | 80.02 | SFMTA | 1791192.06 | 1234674.354 | 223808.04 | 8002.12 | 3249674.454 | 8002 |  | 8002.811 | 80.02 | DP1 | 3513673.4013 | 999092.3427 | 235486.3586 | 4748252.1026
Engineering | 80.03 | SFMTA | 310823.352 | 310823.352 | 129509.73 | 8002.12 | 751156.434 | 8002 |  | 8002.821 | 80.02 | DP2 | 13721382.2774 | 12168070.1486 | 266434.2493 | 26155886.6752
[7 empty] | 0 |  |  | 8002.831 | 80.02 | DP3 | 2372223.4432 | 3666163.5032 | 864248.1854 | 6902635.1318
[7 empty] | 0 |  | 8003 | 8003.11 | 80.03 | SFMTA | 1807915.152 | 1878918.528 | 824041.152 | 4510874.832
Start-Up; Safety & Security; Other | 80.08 | OPS | 0 | 21120 | 8800 | 8008 | 29920 | 8008 |  | 8003.14 | 80.03 | DPT | 250880 | 302400 | 126000 | 679280
Start-Up; Safety & Security; Other | 80.08 | DPT | 0 | 0 | 0 | 8008 | 0 | 8008 |  | 8003.631 | 80.03 | PM/CM | 8111168.0377 | 8335005.4014 | 3186270.6191 | 19632444.0582
Start-Up; Safety & Security; Other | 80.03 | SFMTA | 0 | 153600 | 115200 | 8003.11 | 268800 | 8003 |  |  | 80.04 | PM/CM | 1754119.7904 | 3696336.7957 | 2105396.7926 | 7555853.3786
Start-Up; Safety & Security; Other | 80.03 | DPT | 250880 | 302400 | 126000 | 8003.14 | 679280 | 8003 |  | 8003.634 | 80.03 | PCC | 85485.3796 | 2903605.0958 | 984450.2751 | 3973540.7505
[7 empty] | 0 |  | 8004 | 8004.13 | 80.04 | SFMTA | 418613.832 | 594869.832 | 247862.43 | 1261346.094
PM/CM | 80.03 | PM/CM | 8111168.0377 | 8335005.4014 | 3186270.6191 | 8003.631 | 19632444.0582 | 8003 |  | 8004.33 | 80.04 | DPW | 668000 | 1011200 | 540000 | 2219200
PM/CM | 80.04 | PM/CM | 1754119.7904 | 3696336.7957 | 2105396.7926 | 8003.631 | 7555853.3786 | 8003 | 8008 | 8008 | 80.08 | DPT | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | OPS | 0 | 21120 | 8800 | 29920
PCC | 80.03 | PCC | 85485.3796 | 2903605.0958 | 984450.2751 | 8003.634 | 3973540.7505 | 8003 | Grand Total |  |  |  | 36379978.7766 | 38396594.4747 | 10065581.5206 | 84842154.7719
0
DP1 | 80.02 | DP1 | 3513673.4013 | 999092.3427 | 235486.3586 | 8002.811 | 4748252.1026 | 8002
DP2 | 80.02 | DP2 | 13721382.2774 | 12168070.1486 | 266434.2493 | 8002.821 | 26155886.6752 | 8002
DP3 | 80.02 | DP3 | 2372223.4432 | 3666163.5032 | 864248.1854 | 8002.831 | 6902635.1318 | 8002
0
DPW | 80.02 | DPW | 1574502.0511 | 1274315.1214 | 323273.6886 | 8002.31 | 3172090.8611 | 8002
DPW | 80.04 | DPW | 668000 | 1011200 | 540000 | 8004.33 | 2219200 | 8004
0
|  |  | 36667286.7966 | 38552830.9227 | 10065581.5206 |  | 85285699.2399
| Cum |  | 36667286.7966 | 75220117.7193 | 85285699.2399
|  |  | 2010 | 2011 | 2012 - thru 05/31
project mgmt |  | sfmta | 2513837.004 | 2476424.808 | 956703.582
Engineering |  | sfmta | 2102015.412 | 1545497.706 | 353317.77
Start-Up; Safety & Security; Other |  | all | 250880 | 477120 | 250000
pmcm |  | pmcm | 9865287.828 | 12031342.1971 | 5291667.4117
pcc |  | pcc | 85485.3796 | 2903605.0958 | 984450.2751
dp1 |  | dp1 | 3513673.4013 | 999092.3427 | 235486.3586
dp2 |  | dp2 | 13721382.2774 | 12168070.1486 | 266434.2493
dp3 |  | dp3 | 2372223.4432 | 3666163.5032 | 864248.1854
dpw |  | dpw | 2242502.0511 | 2285515.1214 | 863273.6886
dpw |  | dpw | 0 | 0 | 0
|  |  | 36667286.7966 | 38552830.9227 | 10065581.5206
| Cum |  | 36667286.7966 | 75220117.7193 | 85285699.2399

## May12 Cost Rpt published Jun12
May 2012 Cost Repost published in June 2012
Data
csmt.scc_code | SCC3 | Staffing - SCC3 | csmt.cost_code | csmt.title | Id# | Sum of CCE | Sum of AFE | Sum of ACTUALS
080.01 | 8001 | 8001 |  |  |  | 46220113.54 | 48436628.53 | 46220113.54
080.01 Total | [5 empty] | 46220113.54 | 48436628.53 | 46220113.54
080.02 | [5 empty] | 0 | 0 | 0
| 8002.1 | 8002.11 | 1.2.012.01.080.02 | FD:SFMTA Labor-Engineering Service | 562 | 8081775.24 | 7368763 | 8081775.24
| 8002.2 | 8002.23 | 1.2.021.01.080.02 | FD-CTYCO-Arts Commission | 384 | 653000 | 4314799 | 653000
|  | 8002.24 | 1.2.024.01.080.02 | FD:CTYCO-Risk Management | 393 | 45000 | 45000 | 0
|  | 8002.25 | 1.2.029.01.080.02 | FD:CTYCO-City Auditor | 399 | 200220 | 200220 | 121897
|  | 8002.26 | 1.2.402.01.080.02 | Department of Technology | 406 | 140534 | 166756.46 | 124613.49
|  | 8002.27 | 1.2.022.01.080.02 | FD:CTYCO-Fire Department | 390 | 34540 | 95505 | 34540
|  | 8002.28 | 1.2.028.01.080.02 | FD:CTYCO-Public Util Comm. (PUC) | 398 | 32959 | 17500 | 21727.6
|  | 8002.29 | 1.2.027.01.080.02 | FD:CTYCO-Depart. of Public Health | 397 | 1267.43 | 50459 | 1267.43
| 8002.3 | 8002.31 | 1.2.032.01.080.02 | FD:DPW-Bureau of Engineering (BOE) | 400 | 3327836 | 3592573 | 2706761.11
|  |  | 1.2.034.01.080.02 | FD:DPW-Bureau of Cnst. Mgmt. (BCM) | 402 | 185000 | 0 | 61017.87
|  |  | 1.2.036.01.080.02 | FD:DPW-Bureau of St Use&Map(BSM) | 404 | 100000 | 0 | 76548.83
| 8002.4 | 8002.411 | 1.2.332.01.080.02 | FD:CTYCO-SFCntyTrsp. Auth. (SFCTA) | 458 | 20000 | 79405 | 0
|  |  | 1.2.332.97.080.02 | FD:CTYCO:AC-SFCntyTrsp. (SFCTA) | 405 | -10285 | 0 | 0
[5 empty] | 459 | 10285 | 0 | 0
| 8002.6 | 8002.61 | 1.2.051.01.080.02 | FD:ODC's - 821 Howard | 507 | 1154228 | 1106151.32 | 689554.95
|  |  | 1.2.055.01.080.02 | FD:ODC's - 651 Brannan Street | 508 | 2993075 | 2993075 | 2028132.82
| 8002.8 | 8002.811 | 1.2.071.01.080.02 | PROF:DP1 Base Contract | 318 | 6491482.59 | 6355584.59 | 6015977.4
|  |  | 1.2.071.97.080.02 | PROA:DP1 Contract Options | 320 | 8517.41 | 0 | 0
|  | 8002.821 | 1.2.072.01.080.02 | PROF:DP2 Base Contract | 322 | 36436012 | 27510958 | 24312059.79
|  |  | 1.2.072.97.080.02 | PROA:DP2 Contract Options | 324 | 3513947 | 0 | 0
|  | 8002.831 | 1.2.073.01.080.02 | PROF:DP3 Base Contract | 326 | 16633987 | 10673580 | 7534124.27
|  |  | 1.2.073.97.080.02 | PROA:DP3 Contract Options | 328 | 3285539 | 0 | 0
| 8002.7 | 8002.71 | 1.2.070.97.080.02 | PROA:AC-Final Design | 511 | 352786.64 | 0 | 0
080.02 Total | [5 empty] | 83691706.31 | 64570329.37 | 52462997.8
080.03 | [5 empty] | 0 | 0 | 0
| 8003.1 | 8003.11 | 1.8.011.01.080.03 | PM:SFMTA Labor-Project Management | 587 | 18034926 | 7082073.51 | 6874675.98
|  | 8003.14 | 1.8.016.01.080.03 | PM:SFMTA Labor-DPT | 592 | 639776.29 | 498080 | 639776.29
|  |  | 1.8.016.07.080.03 | DPT/SSD ds/CN:1UTL | 593 | 38450 | 38450 | 38450
|  |  | 1.8.016.08.080.03 | DPT/SSD ds/CN, CN:2UTL | 594 | 259120 | 259100 | 159632.01
| 8003.2 | 8003.23 | 1.8.021.01.080.03 | PM-CTYCO-Arts Commission | 431 | 4186488 | 0 | 303103.83
| 8003.6 | 8003.61 | 1.8.051.01.080.03 | PM:ODC's - 821 Howard Street | 529 | 3502737 | 0 | 0
|  | 8003.631 | 1.8.063.01.080.03 | AECOM-EPC JV CS-149 | 531 | 132791859 | 29992662 | 23161674.83
|  | 8003.632 | 1.8.067.01.080.03 | PROF: Hill Intl. CS-156 | 536 | 17112873 | 4379655 | 3681727.54
|  | 8003.634 | 1.8.066.01.080.03 | PM:Anil Verma | 535 | 395270.12 | 395270 | 395203.94
|  | 8003.64 | 1.8.063.97.080.03 | PROA:AC: Project Management | 533 | 13905844.69 | 0 | 0
|  | 8003.62 | 1.8.181.01.080.03 | PM: Aon Risk Ins. Study | 365 | 25000 | 25000 | 25000
080.03 Total | [5 empty] | 190892344.1 | 42670290.51 | 35279244.42
080.04 | [5 empty] | 0 | 0 | 0
| 8004.1 | 8004.121 | 1.3.013.01.080.04 | CM:SFMTA Labor-Constr. Management | 570 | 3902473 | 502275 | 533057.37
|  | 8004.151 | 1.3.012.01.080.04 | CM:SFMTA Labor-Engineering Service | 569 | 50000 | 50000 | 7262.66
| 8004.3 | 8004.311 | 1.3.032.01.080.04 | CM:DPW-(BOE) Design Support/CN | 415 | 1727944 | 0 | 0
|  | 8004.331 | 1.3.034.01.080.04 | CM:DPW-Bureau of Cnst. Mgmt. (BCM) | 417 | 6752300 | 2300000 | 2052256.24
|  | 8004.341 | 1.3.039.01.080.04 | CM:DPW-Environmental Support (BCM) | 422 | 1672046 | 342574 | 293878.62
|  |  | 1.3.039.02.080.04 | CM:1252 DPW-Environ. Support (BCM) | 423 | 510000 | 0 | 0
|  | 8004.351 | 1.3.036.01.080.04 | CM:DPW-Bureau of St Use&Map(BSM) | 419 | 417129 | 90000 | 9267.78
| 8004.6 | 8004.611 | 1.3.051.01.080.04 | CM:ODC's - 821 Howard | 514 | 417129 | 0 | 0
| 8004.7 | 8004.71 | 1.3.333.01.080.04 | CM:APTA - IRP | 464 | 100000 | 100000 | 27307.79
080.04 Total | [5 empty] | 15549021 | 3384849 | 2923030.46
080.05 | [5 empty] | 0 | 0 | 0
| 8005 | 8005 | 1.8.068.01.080.05 | PROF:OPPI Arthur Gallagher | 537 | 6800000 | 6800000 | 6045933.22
080.05 Total | [5 empty] | 6800000 | 6800000 | 6045933.22
080.06 | [5 empty] | 0 | 0 | 0
| 8006.1 | 8006.11 | 1.1.023.01.080.06 | PE:CTYCO-City Attorney's Office | 373 | 96980.75 | 110000 | 96980.75
|  | 8006.12 | 1.3.023.01.080.06 | PROF:CN Legal-City Attorney Office | 409 | 280000 | 280000 | 0
|  | 8006.13 | 1.2.023.01.080.06 | PROF:FD Legal-City Attorney Office | 392 | 705187 | 396535 | 532723
|  | 8006.14 | 1.2.026.01.080.06 | FD:CTYCO-Planning Department | 396 | 236666 | 40000 | 0
|  | 8006.15 | 1.3.142.97.080.06 | PROA:AC:Legal; Permits | 519 | 1159557 | 0 | 0
|  | 8006.16 | 1.2.331.01.080.06 | Bay Area Rapid Transit (BART) | 457 | 1797783 | 1797783 | 146426.79
|  | 8006.17 | 1.3.404.01.080.06 | Dept. of Building Inspection (DBI) | 429 | 1039943.14 | 1039943.14 | 0
|  | 8006.18 | 1.3.142.01.080.06 | PROF:Legal; Permits | 518 | 2023203.86 | 0 | 0
080.06 Total | [5 empty] | 7339320.75 | 3664261.14 | 776130.54
080.07 | [5 empty] | 0 | 0 | 0
| 8007.1 | 8007.11 | 1.3.028.07.080.07 | SV:PUC CM Inspection Services-UR#1 | 411 | 55936.04 | 65000 | 55936.04
|  | 8007.12 | 1.3.037.01.080.07 | CM:DPW-Material Testing Lab (BCM) | 421 | 83100 | 83100 | 20020.65
|  | 8007.13 | 1.3.028.08.080.07 | SV:PUC CM Inspection Services-UR#2 | 414 | 120784.47 | 95000 | 120784.47
| 8007.T | 8007.TBD | 1.1.202.01.080.07 | JOC15&22 Potholing Utl1, Lght Fnds | 445 | 63937.8 | 0 | 63937.8
080.07 Total | [5 empty] | 323758.31 | 243100 | 260678.96
080.08 | [5 empty] | 0 | 0 | 0
| 8008.1 | 8008.11 | 1.3.144.01.080.08 | PROF: Startup | 524 | 7041907 | 0 | 0
|  | 8008.14 | 1.3.144.97.080.08 | PROA: AC Startup | 526 | 1358422 | 0 | 0
080.08 Total | [5 empty] | 8400329 | 0 | 0
Grand Total | [5 empty] | 359216593.01 | 169769458.55 | 143968128.94

## spread
| TBD item |  |  |  | Thru 05/31/12 CCE
|  | Tot Prog | FD = 30 | AdvConst = 24
| month | 108 | 30 | 24
Spread (SP=Staff Plan)
Sum of CCE Total
SCC1 | SCC GROUP DESC | SCC2 | SCC2 Desc | SCC3 | Group | Total |  |  | % of FD
8001 | Prelim Engrg | 8001 | (blank) | 8001 | Prelim Engrg | 46220114 |  | n/a
|  | 8001 Total |  |  |  | 46220114
8001 Total | [5 empty] | 46220114
8002 | Final Design | 8002.1 | SFMTA | 8002.11 | SFMTA-PM
|  |  |  | 8002.12 | SFMTA-Engrg | 8081775 |  | SP | 100 | 8081775
|  |  |  | 8002.13 | SFMTA-CM | 0
|  |  |  | 8002.14 | SFMTA-DPT | 0
|  | 8002.1 Total |  |  |  | 8081775
|  | 8002.2 | City/County | 8002.21 | City Attorney | 0
|  |  |  | 8002.23 | Arts commission | 653000 |  | Per Kerri | 100 | 653000
|  |  |  | 8002.24 | Risk | 45000 |  | FD | 100 | 45000
|  |  |  | 8002.25 | City Auditor | 200220 |  | FD | 100 | 200220
|  |  |  | 8002.26 | Dept. of Tech | 140534 |  | Per Kerri | 100 | 140534
|  |  |  | 8002.27 | Fire Dept. | 34540 |  | FD | 100 | 34540
|  |  |  | 8002.28 | Dept. of Tech | 32959 |  | ?? Per Kerri - FD | 100 | 32959
|  |  |  | 8002.29 | Dept of Public Health | 1267 |  | Per Kerri | 100 | 1267
|  | 8002.2 Total |  |  |  | 1107520
|  | 8002.3 | DPW | 8002.31 | DPW | 3612835.8873 |  | SP | 100 | 3612835.8873
|  | 8002.3 Total |  |  |  | 3612835.8873
|  | 8002.4 | SFCTA | 8002.41 | SFCTA | 20000 |  | n/a
|  | 8002.4 Total |  |  |  | 20000
|  | 8002.6 | Project ODCs | 8002.61 | Project ODCs | 4147303 |  | FD | 100 | 4147303
|  | 8002.6 Total |  |  |  | 4147303
|  | 8002.7 | Alloc Cntcy | (blank) | Alloc Cntcy | 352787 |  | ----
|  | 8002.7 Total |  |  |  | 352787
|  | 8002.81 | DP1 | 8002.811 | DP1 - Labor | 6227095 |  | SP | 100 | 6227095
|  |  |  | 8002.812 | DP1 - ODCs | 264388 |  | 95% FD | 95 | 251168.6
[5 empty] | Alloc cntcy/Options | 8517 |  | FD | 100 | 8517
|  |  |  | 8002.812 | DP1 - ODCs |  |  | 5% Const | 5 | 13219.4
|  | 8002.81 Total |  |  |  | 6500000 |  |  |  | 6500000
|  | 8002.82 | DP2 | 8002.821 | DP2 - Labor | 34633412 |  | SP | 100 | 34633412
|  |  |  | 8002.822 | DP2 - ODCs | 1802600 |  | 90% FD | 90 | 1622340
|  |  |  | 8002.823 | Alloc cntcy/Options | 3513947 |  | 85% FD | 85 | 2986854.95
|  |  |  | 8002.822 | DP2 - ODCs |  |  | 10% const | 10 | 180260
|  |  |  | 8002.823 | Alloc cntcy/Options |  |  | 15% const | 15 | 527092.05
|  | 8002.82 Total |  |  |  | 39949959 |  |  |  | 39949959
|  | 8002.83 | DP3 | 8002.831 | DP3 - Labor | 16075680 |  | SP | 100 | 16075680
|  |  |  | 8002.832 | DP3 - ODCs | 424400 |  | 55% FD | 55 | 233420
|  |  |  | 8002.833 | Alloc cntcy/Options | 3419445 |  | 95% FD | 95 | 3248472.75
|  |  |  | 8002.832 | DP3 - ODCs |  |  | 45% Const | 45 | 190980
|  |  |  | 8002.833 | Alloc cntcy/Options |  |  | 5% Const | 5 | 170972.25
|  | 8002.83 Total |  |  |  | 19919525 |  |  |  | 19919525
8002 Total | [5 empty] | 83696520.8873
8003 | Project Mgmt | 8003.1 | SFMTA | 8003.11 | SFMTA-PM | 18034926 |  | SP
|  |  |  | 8003.12 | SFMTA-Engrg | 0
|  |  |  | 8003.13 | SFMTA-CM | 0
|  |  |  | 8003.14 | SFMTA-DPT | 927580 |  | SP | 100 | 927580
|  | 8003.1 Total |  |  |  | 18962506
|  | 8003.2 | City/County | 8003.23 | Arts commission | 4186488 |  | Kerri - Tot prog | 100 | 4186488
|  | 8003.2 Total |  |  |  | 4186488
|  | 8003.61 | Project ODCs | 8003.611 | Project ODCs | 3502737 |  | Tot Prog | 100 | 3502737
|  | 8003.61 Total |  |  |  | 3502737
|  | 8003.62 | Aon Risk Ins. Study | 8003.621 | Aon Risk Ins. Study | 25000 |  | FD | 100 | 25000
|  | 8003.62 Total |  |  |  | 25000
|  | 8003.63 | Consultants | 8003.631 | PMCM-Labor | 107079723 |  | SP
|  |  |  | 8003.634 | PCC | 17112873 |  | SP
|  |  |  | 8003.632 | PMCM-ODCs | 25712136 |  | Tot Prog | 100
|  |  |  | 8003.633 | Anil Verma | 395270 |  | FD | 100
|  | 8003.63 Total |  |  |  | 150300002
|  | 8003.64 | Contingency | 8003.641 | Contingency | 14038076 |  | ----
|  | 8003.64 Total |  |  |  | 14038076
8003 Total | [5 empty] | 191014809
8004 | Constr Mgmt | 8004.1 | SFMTA | 8004.11 | SFMTA-PM | 0
|  |  |  | 8004.12 | SFMTA-Engrg | 0
|  |  |  | 8004.13 | SFMTA-CM | 3902472.675 |  | SP | 100 | 3902472.675
|  |  |  | 8004.14 | SFMTA-DPT | 0
|  |  |  | 8004.15 | SFMTA-Engrg IRP | 50000 |  | FD+ Tun | 100 | 50000
|  | 8004.1 Total |  |  |  | 3952472.675
|  | 8004.3 | DPW | 8004.31 | BOE | 1727944 |  | ???
|  |  |  | 8004.32 | BOA | 0
|  |  |  | 8004.33 | BCM | 6752300 |  | SP
|  |  |  | 8004.34 | BCM | 2182046 |  | SP
|  |  |  | 8004.35 | BSM | 417129 |  | ??
|  | 8004.3 Total |  |  |  | 11079419
|  | 8004.61 | ODCs | 8004.61 | Project ODCs | 417129 |  | Tot Prog
|  | 8004.61 Total |  |  |  | 417129
|  | 8004.71 | Consultants | 8004.711 | IRP APTA | 46500 |  | FD+Tun | 100 | 46500
|  |  |  | 8004.712 | PMCM | 0 |  | SP | 100 | 0
|  |  |  | 8004.713 | PCC | 0 |  | SP | 100 | 0
|  | 8004.71 Total |  |  |  | 46500
8004 Total | [5 empty] | 15495520.675
8005 | Non-Constr Insurance | 8005 | Non-Constr Insurance | (blank) | Non-Constr Insurance | 6800000 |  | ???
|  | 8005 Total |  |  |  | 6800000
8005 Total | [5 empty] | 6800000
8006 | Legal, Permits, Reviews | 8006.1 | BART | 8006.16 | BART | 1797783 | 13 mo | FD+Tun / Jan 2010 - Jan 2011 | 100 | 1797783
|  |  | City Attorney - Const. | 8006.13 | City Attorney - Const. | 280000 |  | Const | 100 | 280000
|  |  | City Attorney - FD | 8006.12 | City Attorney - FD | 705187 |  | FD | 100 | 705187
|  |  | City Attorney-PE | 8006.11 | City Attorney-PE | 96981 |  | n/a
|  |  | Dept. of Bldg. Inspection | 8006.17 | Dept. of Bldg. Inspection | 1039943 |  | FD | 100 | 1039943
|  |  | Legal Permit Contingency | 8006.18 | Legal Permit Contingency | 1159557 |  | Tot Prog
|  |  | Remaining Allowance | 8006.15 | Remaining Allowance | 2219870 |  | Tot Prog
|  |  | SF Plannning | 8006.14 | SF Plannning | 40000 |  | FD | 100 | 40000
|  | 8006.1 Total |  |  |  | 7339321
8006 Total | [5 empty] | 7339321
8007 | Survey, Tests, Investigations | 8007.1 | DPW - Matls Testing | 8007.12 | DPW - Matls Testing | 83100 |  | 1250/51 | 100 | 83100
|  |  | PUC 1251 | 8007.13 | PUC 1251 | 120784 |  | 1251 | 100 | 120784
|  |  | JOC | 8007.14 | JOC | 63938 |  |  | 100 | 63938
|  |  | Remaining Allowance | 8007.15 | Remaining Allowance | 0
|  |  | SFPUC - CM 1250 | 8007.11 | SFPUC - CM 1250 | 55936 |  | 1250 | 100 | 55936
|  | 8007.1 Total |  |  |  | 323758
8007 Total | [5 empty] | 323758
8008 | Start-up | 8008.1 | Contingency | 8008.14 | Contingency | 1358422 |  | 2017-2018 | 100 | 1358422
|  |  | DPT | 8008.12 | DPT | 49727.2 |  | SP | 100 | 49727.2
|  |  | Escalcation on Base | 8008.15 | Escalcation on Base | 0
|  |  | PMCM | 8008.13 | PMCM | 0
|  |  | Remaining Allowance | 8008.16 | Remaining Allowance | 0
|  |  | SFMTA | 8008.11 | SFMTA | 6992179.59 |  | SP | 100 | 6992179.59
|  | 8008.1 Total |  |  |  | 8400328.79
8008 Total | [5 empty] | 8400328.79
Grand Total | [5 empty] | 359211641.3523